Plan for PHENIX FVTX Disk and Cage Assembly

Stephen Pate, New Mexico State University

September 2008

Scope:  The scope of the FVTX assembly task, in broad terms, is to receive the assembled sensor wedges from SiDet (at FNAL), as well as the final (tested) ROC’s, and produce the four FVTX half-cages.   The locations of the sensors inside the cages must be known for event reconstruction purposes; this means careful metrology and surveying must be done in the process of assembly.  The assembled half-cages will be tested using a DAQ system incorporating the new ROC and FEM modules being designed for the FVTX.  Coordination of the installation of the FVTX in the PHENIX IR also falls into this task.

Overview of this Document:  First the important project dates are reviewed, then follows a discussion of each of the project tasks.  A phased schedule and workforce discussion puts these tasks in relation to each other.  Finally the workforce needs and commitments are summarized.

Important Dates [with WBS indices] from MS Project file:

Assembly jigs manufactured  [1.6.5.6]  by 6/17/09

Support structures manufactured  [1.6.2.3.6]  by 7/29/09

Q/A of Production ROC’s  [1.5.2.3.2]  1/7/10 - 3/15/10

Testing of wedge assemblies  [1.4.1.3.6]  5/18/10 - 12/13/10

Assemble and Survey Wedges onto Cooling Plates [1.7.1]  6/5/10 – 1/24/11

Install and Survey into Cage Enclosure  [1.7.2]   9/7/10 - 3/10/11

Install Cages into VTX Enclosure  [1.7.3]  10/28/10 - 3/31/11

Install 2 Cages in Enclosure into IR  [1.7.4]  3/31/11 - 4/7/11

Test and Verify Functional Requirements  [1.7.5]  4/7/11 – 6/3/11

Install Remaining Half Cages Enclosure into IR  [1.7.6]  6/2/11 – 6/8/11

Test and Verify Remaining Half Cages  [1.7.7]  6/9/11 – 6/29/11

Support Structures and Assembly Jigs:

Here, “support structures” refers to the mechanics that will hold the wedges and ROC’s together in a unit half-cage (WBS 1.6.2-1.6.4); “assembly jigs” refers to a set of temporary supports used in the process of assembly (WBS 1.6.5).

In order to make sure that mechanical problems will not occur at later stages, "dummy wedges" will be manufactured to make possible a mock assembly of half-disks and half-cages.  These dummies can be made from metal plate or G-10.   The final ROC’s will already be available at this time and can be used in the mock assembly too.

Assembly Lab at BNL:

The lab space for the final assembly will be ready by 7/29/09 so that the support structures and assembly jigs can have a place to be delivered and additional QA checking can be done on them.  The first wedge assemblies and ROC’s will become available a few months later and at that point some preliminary cage assembling can be done.

Some equipment and requirements for this lab:

(a)  This lab should be "clean" at the level of having a sticky-pad on the floor at the entrance, and there will be specific handling requirements for the completed wedges.  We have determined that we do not need HEPA filters or other special air-handling measures.

(b)  A "dry box" will be used for the storage of the wedges before assembly.

(c)  Basic electronic testing equipment; oscilloscope, multi-meters, appropriate connectors and test leads, etc. to be determined.  We are seeking institutional contributions to provide this kind of generic equipment.

(d)  Benches and chairs to allow about 4 people to work comfortably at one time.

(e)  Metrology equipment for locating the wedges with respect to survey targets on the half-disks; Robert Pak has indicated that BNL should have the appropriate equipment onsite.

(f)  A "mini-DAQ" system for testing the assembled half-disks and half-cages.

(g)  A cooling system will be needed to operate the detector system for long periods.   We plan to use the old PHENIX MVD cooling system, or a stand-alone cooling system in the Chemistry Department, for such tests.

The location of this lab space at BNL is being determined with the help of Robert Pak.

A "mini-DAQ" System:

We will have a DAQ system available to test the assembled FVTX half-cages in the assembly lab.  This system will use the new ROC and FEM electronics being built for the FVTX.  LANL will support the setup and operation of the mini-DAQ, and other groups involved in the assembly will learn how to use it.

Proposed Assembly Process:

(a)  Finished wedges will arrive from SiDet.  Some re-testing of the wedges should be done after arrival at BNL to make sure they have not been damaged in transit.

(b)  When sufficient wedges of a given type exist, then a half-disk can be assembled.  Any mechanical problems can be addressed at this time; this is a critical issue to look at in the first wedges to be delivered, but presumably the "dummy wedges" mock assembly test will have found these problems out already.

(c)  Electronic testing of the assembled half-disk is appropriate at this point; the final ROC’s will be available and are an integral part of a half-disk.  The precise test protocol remains to be determined; that protocol will be determined by our experiences with testing the wedges at Nevis, and from testing experience with the ROC’s.  If all systems are go, then the next steps can take place.

(d)  The final metrology of the wedges on a half-disk will take place after it is determined that there is no need to remove and replace any of the wedges; metrology and alignment are described in the next section.

(e)  As half-disks become available, one can look to the assembly of a half-cage.  This is another area where mechanical problems may arise; the mock assembly using "dummy wedges" should have already found out any problems of this type.

(f)  A survey crew will be brought in to survey the half-disks in the half-cages --- see next section.

(g)  Completed half-cages will be subjected to additional testing with the "mini-DAQ" and then stored until transportation to PHENIX.

Alignment, metrology and survey:

Based on the experience at RIKEN with the VTX sensors, we know that sensors can be placed on a wedge with an internal precision on the order of a micron or better.  Based on our requirements for track reconstruction, we are requiring that the sensors be placed and surveyed into a detector plane to an accuracy of 10 microns in x and y.  This suggests the following assembly and survey plan:

(1) There are 6 survey targets on each sensor, which are printed during the lithographic stage of the construction of the sensor.  The locations of these targets, with respect to the strips on the sensor, will be known to better than 1 micron.

(2) Using a CMM at BNL, we will verify the location of these survey marks on each sensor, and then locate these sensor marks with respect to survey marks on each half-disk.  One possibility is to have a precision hole on the outside radius of the three support tabs that accepts an alignment flag with a crosshair on it.  All wedges are referenced to these 3 flags.  The flags would extend through the support cage and would serve as reference points for the location of the disks within the cage.  The flags are removable.   The measurement accuracy of the CMM at BNL is 5 microns along each of the x and y axes.

(3) Survey the half-disks into the half-cages in the assembly lab.  This will be done using a theodolite operated by the BNL survey crew.  This survey establishes the locations of the half-disks with respect to each other, in a half-cage.

(4) Survey the half-cages into the IR during the final installation there; this step is also done by the BNL survey crew.

Phased Schedule and Workforce Needs

Phase Ia:  Assembly Lab Preparation

Timeframe:  October 2008 – May 2009

Task:  Prepare assembly lab to receive wedges from SiDet and to perform Q/A on ROCs and on support structures and assembly jigs.

Workforce Estimate:  One senior person working with two postdocs and/or grad students should be able to organize the material and space for the upcoming assembly tasks.

On-Project:  0

Off-Project:  3 FTE

Phase Ib:  Q/A on Mechanics and ROCs

Timeframe:  June 2009 – May 2010

Task:  Perform Q/A on ROCs and on support structures and assembly jigs.

Workforce Estimate:  The people from Phase Ia can perform Q/A on the ROCs and support structures and assembly jigs which are scheduled to be delivered during this time frame.  One additional part-time person (from LANL) will be needed to prepare the specialized mini-DAQ equipment and integrate it with the received ROCs.

On-Project:  0

Off-Project:  3.5 FTE

Phase IIa:   Receive and test wedges from SiDet

Timeframe:  June – December 2010

Task:  Test wedges coming from SiDet to make sure they are in a good working condition after transport.

Workforce Estimate:  The mini-DAQ may be used for this.  One part-time person will be needed to verify proper operation of the mini-DAQ.  Two other persons should be able to test the wedges as they come in.  It is important to have at least two people working on this so that we begin to develop expertise in a group of people.  We need to place a high priority on safe transportation of wedges from SiDet so that this task does not become a bottle-neck.

On-Project:  0

Off-Project:  2.5 FTE

Phase IIb:  Place wedges on cooling plate

Timeframe:  June 2010 – January 2011

Task:  Begin to assemble wedges on cooling plates; this is the beginning of the production of half-disks.  Use the mini-DAQ to test completed half-disks.

Workforce Estimate:  This task happens in parallel with Phase IIa.  All the wedges should have arrived from SiDet by 10/18/2010, so this task can be expected to complete by11/29/2010 as stated in the project schedule.  The same two (at a minimum) people should be able to put together the half-disks; but I would recommend that more than two be involved so as to bring more brainpower to this important task and again to develop expertise.

On-Project:  0

Off-Project:  2 FTE (not the same as in Phase IIa)

Phase IIc:  Survey wedges on cooling plates

Timeframe: July 2010 – January 2011

Task:  Locate sensor strips on a half-disk using precision equipment.

Workforce Estimate:  This happens in parallel with Phase IIb.   The first setup may be time-consuming, but subsequent setups should be more efficient.  The people who do this can be drawn from Phases IIa-b, but work must continue on Phase IIb.  A survey table is available at BNL, and so the participation of some BNL staff will be required in addition.

On-Project:  BNL Survey Crew --- $5k

Off-Project:  2 FTE (can be from Phases IIa-b)

Phase IId:  Place cooling plates in cage

Timeframe:  September 2010 – March 2011

Task:  After sufficient cooling plates (also called half-disks) have been assembled and surveyed, then we can begin to assemble a half-cage.   The mini-DAQ will test the completed half-cages.

Workforce Estimate:  This is a complex task that may not take very much time in total but must be done carefully to prevent damage to the sensors.  Probably all people (from Phases IIb-c) should participate, at least for the first half-cage.

On-Project:  0

Off-Project:  4.5 FTE (combined from Phases IIa-c)

Phase IIe:  Survey plates in cage

Timeframe:  October 2010 – March 2011

Task:  Surveyors from BNL will locate the cooling plates inside the half-cages.

Workforce Estimate:  Each cooling plate will need to be surveyed as it goes in; this means four surveys per half-cage.  Each survey will take about two days maximum, with a day for the surveyors to set up and a part of a day to do the survey --- perhaps all of that can be done in one day.  Just two FVTX people should be able to arrange and supervise this, while two others continue with Phase IIb work.

On-Project:  BNL Survey Crew --- $5k

Off-Project:  2 FTE (from Phase IId)

Phase III:  Install Cages in VTX Enclosure

Timeframe:  November 2010 – March 2011

Task:  Put half-cages in VTX enclosure and have a full system test

Workforce Estimate:  After a half-cage has been assembled and surveyed, it can be placed into this system test.   This test is expected to take place in Building 1008, so some transport by PHENIX techs will be involved.  New people will probably need to be involved in this part of the project, so that Phase IId can continue.

On-Project:  PHENIX techs

Off-Project:  2 FTE (not from Phase IId)

Phase IV:  Install 2 cages in IR

Timeframe:  April 2011

Task:  Take two completely surveyed, completely functional half-cages and put them in the PHENIX IR.

Workforce Estimate:  Phases II and III are completed at this point, so all of the people who were working on those projects should devote themselves to this new Phase.  It will anyway involve the full complement of PHENIX techs to do the installation.  FVTX people should supervise the installation and then begin to hook up cables and make preparations for testing.

On-Project:  PHENIX Tech Crew --- $5k

Off-Project:  6 FTE (from Phase II-III)

Phase V:  Test and verify functional requirements

Timeframe:  April – May 2011

Task:  Make sure the two FVTX half-cages in IR are completely functional.

Workforce Estimate:  The experts from the Phases II and III tasks will need to participate in this task to make sure that all available talent and knowledge can be brought to bear in this first in-situ test of the equipment.  Phases II and III are finished at this point.

On-Project:  0

Off-Project:  6 FTE

Phase VI:  Install remaining half-cages into IR; verify operation

Timeframe:  June 2011

Task:  The remaining two cages are installed in the PHENIX IR.

Workforce Estimate:  PHENIX techs again have leading role in the actual installation, and FVTX people have to hook up cables and carry out testing.

On-Project:  PHENIX Tech Crew --- $5k

Off-Project:  6 FTE

Workforce for Assembly:  The critical time period for the assembly is from 3/23/10 through 5/12/11, about 13-1/2 months.  During this time the critical pieces of hardware (the finished wedges and the disk and cage parts) will become available and can be assembled, tested, surveyed, and installed  Here is a summary of known workforce commitments.

NMSU:  Vipuli Dharmawardane (NMSU postdoc) will be in residence at BNL during this time and will take the lead in getting the assembly tasks done.  There will also be at least one NMSU grad student (to be named) in residence at BNL to work on this project.  Three NMSU Faculty (Kyle, Papavasiliou, Pate) will make trips to BNL during this period to assist in the assembly.

Columbia:  Dave Winter estimates they can contribute 1 faculty FTE, 1-2 scientific staff, 2-3 students, 1 postdoc, and perhaps 1 technician.

UNM:  A post-doc will be made available.

LANL:  A post-doc will be made available, with the assistance of other LANL staff traveling to BNL during the period of assembly.

BNL:  Robert Pak and Angelika Drees have offered their help in the assembly process.

It is important to note that some personnel, especially people from NMSU and Columbia, will spend time on both wedge assembly and the final detector assembly, and that these two assembly processes overlap somewhat in time.

Comparing this list of commitments with the summary charts (in separate excel file), it seems we have sufficient off-project workforce committed to cover the FVTX assembly tasks.

Workforce for Movement and Installation into the PHENIX IR:  This activity will be planned in close cooperation with BNL/PHENIX scientists and technicians.  The PHENIX technical crew has a tremendous amount of experience installing equipment in the PHENIX IR, and we depend on them to perform the large-scale movement and installation.  The survey and alignment of the FVTX also falls into this activity.  The vast majority of the collaboration scientists mentioned above in “Workforce for Assembly” will follow the detector to the IR and be responsible for the other detailed work (hooking up cables, testing detector and DAQ functions, commissioning, etc.).

LANL, NMSU, and UNM worked very closely together on the construction, installation, survey, commissioning and operation of the north and south muon tracker arms a few years ago, in close collaboration with BNL and the rest of PHENIX, and we are already drawing on those experiences as we plan the FVTX project.