## Slide 1
FVTX Commissioning Plan
1.71
Jon S Kapustinsky

## Slide 2
4 half-cages assembled and tested in the FVTX lab in the Physics Building (metrology and survey complete).
Full data acquisition system chain tests and cosmic runs on the bench and with bias and low voltage and cooling system, and in the IR.
Integrate the FVTX into the VTX support structure outside the IR.
Install the VTX/FVTX into the IR with PHENIX techs and engineers (Coordination with the PHENIX Integration Group led by Don Lynch).
Installation and Commissioning Overview

## Slide 3
One half-cage of the FVTX – 3 views
4 detector stations per FVTX assembly, each off-set in phi.
Each station has its own cooling circuit.

## Slide 4
Installation FVTX/VTX in PHENIX IR
Installation procedure developed by BNL tech staff
Installation procedure approved by CAD

## Slide 5
FVTX rack layout in the IR
Services installed in the IR
Chillers will be installed in the assembly hall
Dry gas storage tank outside PHENIX

## Slide 6
Timing calibration, performance optimization, pulser calibration and cosmic runs on the bench
  Dave Winter, Doug Fields, Sergey Butsyk, Imran Younas, Melynda Brooks, Pat McGaughey, Hubert van Hecke, Jon Kapustinsky, Steve Pate, students and PD’s
Install and populate electronics racks in the IR with LV/HV power supplies and power distribution cards
  BNL techs, Eric Mannel, Robert Pak, Walt Sondheim, Don Lynch
Connect FVTX cooling system and dry gas system and safety interlocks
  BNL techs, Eric Mannel, Robert Pak, Walt Sondheim, Don Lynch
Install cabling and optical fibers from the IR to the DAQ in the PHENIX rack room
  BNL techs, Eric Mannel, Robert Pak, Steve Boose
Major tasks and personnel (1)

## Slide 7
Test cooling system, thermocouples and interlocks
  BNL techs, Eric Mannel, Robert Pak, Walt Sondheim, Don Lynch
Test power distribution systems, bias and low voltage and interlocks
  Eric Mannel, Paul Giannotti, Pat McGaughey, Steve Boose
Test fiber optics and signal integrity for all channels
  BNL techs, Eric Mannel
Slow controls and integration into the PHENIX DAQ
  Eric Mannel, Martin Purschke, John Haggerty, Ed Desmond
Timing calibration, performance optimization, pulser calibration and cosmic runs in the IR
  Dave Winter, Doug Fields, Sergey Butsyk, Imran Younas, Melynda Brooks, Pat McGaughey, Hubert van Hecke, Jon Kapustinsky, Steve Pate, students and PD’s
Major tasks and personnel (2)

## Slide 8
*Requirement | Metric | Method
Mini strips active | >80% (expect ~99%) | calibration/cosmics
Hit efficiency | >85% (expect~99%) | cosmics
Radiation length per wedge | < 2.4 % | by design
Detector hit resolution | < 25 mm | cosmics
Random noise hits/chip | <0.1% | calibration (threshold:noise~5:1)
Level-1 latency | 4 ms | 
Level-1 Multi-Event buffer depth | 4 events | 
Read-out time | < 40 ms | 
Read-out rate | > 10 kHz | 
*Primary bench test requirements from the Management Plan. The last four have been validated by extensive tests of the FPGA code.
FVTX Functional Requirements

## Slide 9
Additional goals to complete commissioning
FVTX fully integrated into PHENIX DAQ.
~99% channels operational, timed in and calibrated.
Fully operational on-line monitoring.
Expert shift procedures developed for beam runs, detector operations and data acquisition.
  The FVTX collaboration

## Slide 10
Task | Start-Finish | Comments
Mechanical support structure and installation hardware | Done for VTX | 
Cable trays in IR | Done for VTX | 
Chiller in Assembly Hall | Done for VTX | 
Dry gas system | Done for VTX | 
Install cables and plumbing and racks (pre-populated) | 07/01/11-08/01/11* | will start asap after the shutdown
Cages fully bench tested First cage complete Last cage complete | 04/08/11-04/22/11 06/09/11-06/16/11 | Bench system tests with cooling and power distribution
All FVTX detector, support, installation, alignment and survey parts and assemblies complete, ready for installation | 06/16/11-07/1/2011 | 
Install FVTX into the VTX support structure | 08/01/11-08/10/11 | Assembly will be done outside the IR
Install and align FVTX/VTX assembly in the IR | 08/10/11-08/24/11 | Installation nearly identical to VTX in 2010
Connect cables and plumbing | 08/24/11-08/31/11 | 
Test and commission | 08/31/11-09/27/11 | FVTX manpower
FVTX Installation and Commissioning Schedule
*Shutdown is a month later than even recently expected
Assumption is that IR will close 10/01/11

## Slide 11
Summary
Before installation into the IR – FVTX personnel
  Assembled, pre-surveyed, bench-tested FVTX installed into the VTX support.
Before Installation into the IR BNL techs and integration personnel
  Cooling and dry gas system, HV/LV racks, cables and fibers , FVTX/VTX installation hardware installed in the IR.
After installation of the FVTX/VTX in the IR – FVTX and BNL techs and integration personnel
  Services hookup and testing, cabling and testing, timing, calibration and integration into the PHENIX DAQ.

## Slide 12
Backup Slides

## Slide 13
On-line monitoring commissioning tasks
Histogram sensor hits
  hot channels
  dead channels
  thresholds vs noise
  update chip registers as needed
Pulser timing
  adjust clock to readout (~20 ns window)
Cosmics tracking
  refine alignment constants
Charge sharing/ clusters
  tracking software
Much of this was already developed for the FVTX cosmic ray tests at LANL