## Slide 1: IT3 Report of Work Package 5
Mechanics and cooling
ITS plenary:
Tuesday 12 May 2020
M.Angeletti, R.Barthel, G.Fiorenza, C.Gargiulo, P.Ijzermans, G.Lahu, G.Ledey, A.Lafuente, E.Laudi, P.J. Secouet, J.Van Beelen,…

## Slide 2: IT3 Report of Work Package 5
WP5 group and overall plan
Breadboard model
Engineering model

## Slide 3: ITS3 WP5: Group and collaboration
Work Package:
  WP responsible: C.Gargiulo.
  CERN group: M.Angeletti, G.Fiorenza, P.Ijzermans, G.Lahu, G.Ledey, A.Lafuente Mazuecos, E.Laudi, P.J. Secouet, J.Van Beelen.
Institutes collaboration:
  Carbon structure & cooling: St. PietersburgG.Fieofilov, S.Igolkin
  Layer Assembly: NikhefR.Barthel; INFN Bari
  Testing : INFN Frascati  A. Saputi, first contact, collaboration terms to be finalised
  …

## Slide 4: ITS3 WP5: Plan
Milestone | Description | Date
1 | Breadboard Model (BBM) | 
 | Selection of carbon materials based on structural and thermal properties. Production of samples for material characterization. Development of FE and CFD models for structural and thermal simulations. | Q2 2020
2 | Engineering Model (EM) | 
 | Production of one half-layer with dummy chips. Thermal and dynamic stability tests (including wind tunnel). Development of half-barrel assembly procedures and jigs. Production of first half-barrel with dummy chips. Thermal and dynamic stability tests (including wind tunnel). Drawings, FE and CFD reports. | Q1 2022
3 | Qualification Model (QM) | 
 | Production of two half-barrels with prototype chips Thermal and dynamic stability tests (including wind tunel) Electrical functional tests. Final assembly and test procedures, technical specifications and drawings. | Q4 2023
4 | Final Model (FM) | 
 | Production of four half barrels with final chips. Electrical and mechanical acceptance tests. | Q4 2024
ITS3 R&D is part of the CERN R&D programme on new Detector Technologies

## Slide 5: ITS3 WP5: Plan
Milestone | Description
1 | Breadboard Model (BBM)
 | Selection of carbon materials based on structural and thermal properties.
 | On-going Procurement of carbon foam samples for characterization test. On-going Investigation of ultralight CFRP support starting.
 | Development of FE and CFD models for structural simulations.
 | On-going FE Modal analysis performed and dynamic analysis under development. On-going Development of CFD models for thermal simulations.
2 | Engineering Model (EM)
 | Production of one half-layer with dummy chips. On-going procurement
Breadboard Model (BM): This is the initial prototype and is only functionally representative of the final module.
Engineering Model (EM): This model is form, fit, and functionally close to the final model; however, it will use a mixture of final-grade components and commercial components.
Qualification Model (QM): This is the model that is subjected to the qualification campaign. This usually includes design updates from the EM and uses identical components to final; however, these components do not need to be screened to the final standard
Final Model (FM): The models actually to install in the Experiment; these are tested to acceptance-level testing (lower level than qualification).

## Slide 6: ITS3 WP5 Breadboard model: Carbon foam & CFRP
Carbon material selection and production:
COOLING: Low dry air/pre-cooled gas flow*
CFRP*
CARBON FOAM
Material | Density [g/cm3] | CTE [ppm/oC] | K-In plane [W/mK] | K -Out of plane [W/mK] | Pore volume | [PPI] (Pores Per Inch) [µm] cell size | Elastic modulus [MPa]
Duocel® Carbon Foam | 0,03 | 2,2 | < 0,05 | < 0,05 | 97% | 5 to 100 PPI | 101,84
K9 Hi-K | 0,20-0.26 0.45-0.68 |  | 20 / 60 | 20 / 60 |  | 130 PPI | 
CFOAM 35 HTC | 0.4-0.5 | 1.9-2.1 | 140-180 | 140-180 | >70% | 1200 µm | 100 (Compr.)
POCO HTC | 0.9 | ̴1 | 70 | 245 | 61% | 400µm | >100 (Compr)
* Design solution under discussion with St, Pietersburg
Stress relief gas nozzles

## Slide 7: ITS3 WP5 Breadboard model: carbon foam characterisation test
Carbon material selection and production:
(1) Prototype production  ONGOING
(2) Thermal conductivity test  ASAP (CERN opening)
(3) Particles removal test from carbon foam  ASAP (CERN opening)
(4) Pressure drop by means of wind channel  ASAP (CERN opening)
2
3
4
CARBON FOAM
Sample
Several samples
90mm x 50mm x 10mm
with different foam cell size
Filter
for carbon particle collection
Air
flow
Heater 
Cooler 
4 Temp.
sensors
In vacuum
1
Wind tunnel
@ CERN

## Slide 8: ITS3 WP5 Engineering models: layout
EM H-layer
EM H-barrel
Assembly with dummy material: Glassfiber/epoxy (chips) and milled foam (rings)
Nikhef- Rene Barthel
Si chip
Carbon ring
Carbon rings

## Slide 9: ITS3 WP5 Engineering models: dummy silicon chip
Dummy Si chip production:
Layer | Diameter [mm] | Thickness [µm] | Length [mm] | Semi-circ. [mm]
L0 | 36 | 50 | 280 | ̴56.55
L1 | 48 | 50 | 280 | ̴75.4
L2 | 60 | 50 | 280 | ̴94.25
12 inch wafer
D=300m (11.8inch)
<100> P-type
Th. = 775um
L0
L1
L2
Dicing blade 35-40um
Strip
Strip
Strip
Strip
Strip
Strip
12 inch Si wafer thinned down to 50 um.
Company: DISCO HI-TEC EUROPE GmbH, Germany, http://www.discoeurope.com
Dicing Before Grinding (DBG) procedure
Grinder DFG8560 (Thin down 30-40um)
Production: (2x) 3 different dummy chips (L0,L1,L2)
+ strips (different width) for gluing/assembly test.
Price 3350 Euro

## Slide 10: ITS3 WP5 Engineering models: Carbon foam ring
Company | Foam Name | Material Ordered | Order status | T. value (CHF) | Estimated delivery
ERG | Duocel® | 3 sets of rings + 1 sample | Approved on 24.04.2020 | 2087 | 19.06
ALLCOMP | K9 Hi-K | 1 set of rings + 1 sample for 2 different density (0.20-0.26 and 0.45-0.68) | Approved on 29.04.2020 | 5360 | 29.05
CFOAM | 35HTC | 3 sets of rings + 1 sample | Approved on 07.05.2020 | 1500 | 11.06
ENTEGRIS | POCO HTC | 3 sets of rings + 1 sample | Waiting for approval | 2735 | TBD
Carbon rings are purchased with no holes. Holes drilling or specific radiator features will be decided based on pressure drop test results on the breadboard models.
Material order:
10 different companies have been contacted for the production of half annular rings sample in carbon foam.
4 out of the 10 companies have been selected for the production of the first prototypes which will be used for thermal-mechanical and assembly tests.

## Slide 11: ITS3 WP5 Engineering model: FEA analysis stiffness and modal
Th2
Th3
Th1
For a fist assessment of the behaviour of a large chip, the mechanical properties of a pure Si material has been considered. Young modulus theorical values are in good agreement with specific bending test.
 | INPUT |  |  | OUTPUT |  |  |  |  |  | 
Case | Th1[mm] | Th2[mm] | Th3[mm] | Sag[µm] | F1[Hz] | F2[Hz] | F3[Hz] | F4[Hz] | F5[Hz] | F6[Hz]
2 Carbon rings | 5 | 5 | // | 1.2 | 248 | 252 | 421 | 422 | 599 | 599
3 Carbon rings | 5 | 5 | 5 | 0.21 | 514 | 514 | 514 | 514 | 877 | 877
Si material: Anisotropic crystalline material, (100) Oriented silicon wafer.
X
ALPIDE chip
50 μm-thick
Preliminary 3 point bending test
Model: shell element
E~140GPa
Carbon ring

## Slide 12: ITS3 WP5: Engineering model: Carbon foam characterisation test
Carbon material selection and production:
Half-Layer assembly NEXT
Half-layer vibration test NEXT
Half-Layer thermal test NEXT
Half-barrel assembly NEXT
Half-barrel vibration test NEXT
Half-Layer thermal test NEXT
EM H-layer
EM H-barrel

## Slide 13: Next 
Bread board model BBM
  -produce samples for the different characterization test
  -wind tunnel test sections BBM samples
  -perform characterization test
Engineering model EM
  Develop chip handling procedure finalized to EM
  Develop wind tunnel test set-up
  -wind tunnel test sections EM h-layer, EM h-barrel
  -thermal chip heaters, thermocamera,..
  -mechanical laser system for vibration acquisition
  Perform FEA
  Static shape uniformity of constrained chip
  Dynamic seismic and cultural noise
  Perform CFD
  Thermal air/gas flow cooling