## Slide 1: Dark Photon LDRD/ER Plan
—a list of all major technical tasks that need to be completed between now and collection of data (procurements, assemblies, reviews, installations, commissioning, milestones)
—for each task, give the estimated schedule for that task (best would be a project-like format showing interdependencies of things)
—for each task, the resources needed and currently identified (people), the cost estimated for each task
—specifically point out if there is anything that could occur more quickly with more resources (people or funds)
Also, a sensitivity plot that you could produce if you collected data from March-July, which we understand would result in a smaller data set than was used for the sensitivity plot that we were shown at the review. Along with this, give us an idea of how to scale the plot for shorter run times.

## Slide 2: FY-17 Plan
Complete DAQ and Trigger upgrade for E906 Run-5
  By March 2017
  Parasitic data taking April – July, 2017 with E906
  People: Kun, PD(Sho), and collaboration (Femrilab Engineer and student)
Trigger detector construction at LANL and Fermilab
  Mechanical structure safety calculation and documentation (LANL student Kenney?)
  Fermilab safety review (by the end of 12/2016)
  Ship to Femrilab in mid of January 2017
  Installation (end of January 2017)
  People: Hubert, Ming, PD, Fermilab student
Readout electronics
  Femrilab preamps production (by mid January 2017)
  LeCroy 4413 from Fermilab, test (by 11/2017)
  Lemo cables (520) and 17-ch ribbon cables (35)
  Trigger detector installation and commissioning (Feb 2017)
  People: Ming, PD(Sho), Pat and collaboration (Fermilab and ANL)
V1495 trigger look-up table
  MC simulation, Collaboration (Univ. Of Michigan)
  PD (Sho), Kun
Integration and commissioning trigger electronics system
  Feb – March, 2017
  PD(sho), Kun, Ming and collaboration

## Slide 3: FY17 Timeline: Hardware Effort
Nov
Dec
Jan
Feb
Mar
Apr---Jul
DAQ
Upgrade
V1495 trigger algo implementation & Integration into DAQ
80/20 frame assembly
@LANL
trigger detector assembly & Fermilab safety review
@FNAL
SiPM readout
Integration;
Trigger
Commissioning with data
Offline analysis
Data taking,
Offline analysis
Manpower:
Kun, PD/Sho, Ming, Student/Alex, Fermilab student/Engineer/collaboration
Hubert, Pat, Ming, PD, Alex, Fermilab student/E906 collaboration
Additional Engineer & Tech support (w/ $$) could help to reduce the schedule risk

## Slide 4: DAQ & Trigger Integration and Commissioning
DAQ upgrade
  By the end of November
V1495 and DAQ integration
  By mid Feb 2017
Commissioning
  By mid March 2017
Data taking
  April – July 2017
Manpower
  PD (Sho), Kun, Ming, Alex and collaboration

## Slide 5: FY-17 Trigger Detector Construction & Installation
Timeline:
  Complete and installed by the end of January 2017
All Scintillators (at Fermilab) and WLSF (at LANL) in hand
All 80/20 Al frames in hand, 4 frames completed, need to assemble 4 more (identical)
  At LANL
  Hubert, PD, Ming
Frames assembled at LANL, ship to Femrilab for final assembly in December 2016
Fermilab mechanical structure safety review before installation
  Kenney to help ?
  Hubert, Ming
  By mid of Jan 2017

## Slide 6: SiPM readout electronics
Femrilab premap cards production
  Cost: 600 x $50 (20?) = $30K
  By early January 2017
Discriminator
  LeCroy 4413 and NIM crates available from Fermilab pool
  Tested by the end of December
New Taiwan TDCs
  Being produced in Taiwan
  available by the end of March 2017, partial delivery possible
Cables
  Recycle from previous Fermilab experiments
    Lemo cables, 550
    34-ch ribbon cables
    By mid of January 2017
V1495 and VME crate and Controller CPU
  In hand, need to update firmware based on E906 trigger code
  Integration starts early December, complete by mid Feb 2017
People
  PD/Sho, Kun, Pat, Ming and Collaboration

## Slide 7: Sensitivity from 2017 E906 Run
April – July 2017

## Slide 8: FY-18+ Plan
  Continue data taking with polarized Drell-Yan (E-1039) in FY18 as originally planned.
Physics analysis and publication
  E906 data from 2017
Plan to develop a full Dark Photon and Dark Higgs Search proposal for future dedicated runs at Fermilab for many years to come
  EM Calorimeter upgrade to measure electrons to allow us to access low mass below dimuon mass threshold (200MeV)
  Dedicated runs with much higher luminosity beyond 2017
Received strong support from Fermilab PAC, Director and the Dark Sector Physics community on such proposal
Update on Fermilab beam schedule:
  There is an on-going discussion with DOE to run E-1039 for two years after 2017 E906 run. Will know the answer early 2017.
Regardless the outcome of polarized Drell-Yan running, we will work toward the realization of a dedicated dark photon and dark Higgs program at Fermilab, seek additional fund from DOE NP and HEP

## Slide 9: With 2-year run with E-1039
Parasitic run with polarized Drell-Yan
  2018-2019

## Slide 10: If additional fund available in FY17
Given the uncertainty of future run beyond 2017, it would be very helpful to have additional $$ and technical resoruce support to speed up the trigger upgrade to take maximal data out of current E906 run
More manpower to speed up assembly, trigger algorithm development, testing readout and installation, in particular in the following tasks:
  Trigger logic FPGA programing support
  Electronic tech to help SiPM readout, LV/HV, installation and debugging
  Mechanical engineer to complete the safety document for the Fermilab review
Procurements of small items
  Fiber-SiPM adaptors
  Lemo and ribbon cables
  Big frame to hold 4-frames per plane
Other tasks