## Slide 1: Dark Photon LDRD Progress Updates
Detector scintillator + WLSF assembly
  All 8 modules assembled
SiPM readout preamp cards
  All produced and tested, also in 1/4T B-field
  To be installed this week
Full readout test with 7-channel completed and confirmed the design performance
Trigger firmware and lookup table
  V1495 I/O tested, Initial trigger firmware developed
  MC events produced, lookup tables and algorithm developed
DAQ upgrade completed
  x10+ improvement, parasitical data taking with E906/E1039 possible
Fermilab safety document for detector installation
  Work in progress, discussed installation details with Fermilab, to be completed ~2 weeks.
Full detectors to be shipped to Fermilab in the week of 3/12
  Targeted date: 3/16 departure
Project is on track
  New trigger system installed at Fermilab in March
Progress in theory and program development
  Cross check calculations, plan a joint paper
  An invited experimental review paper submitted to Modern Physics Letters A (MPLA, ~18 pages)
  Invited for a presentation at the upcoming DOE/HEP new initiative small-medium scale dark matter workshop

## Slide 2: Excellent progress in the last a few weeks
Detector assembly, SiPM readout and calibration system
  Hubert, Alex, Sanghoon, Shaun, Pat et al
DAQ and Trigger firmware
  Kun, Sho and Andi et al
Full system readout chain test at LANL
  Sho, Xuan, Kun et al
More information at the Dark Photon project web page
https://p25ext.lanl.gov/darkphoton/

## Slide 3: All 8 scintillator trigger modules assembled
Timing-calibration system
Fiber + LED pulsor

## Slide 4
A full detector
Module;
7-channel readout
LeCroy4413
discriminators
E906 DQ
V1495 Trigger
Logic & TDC
4-chan wave
form digitizer
System test @LANL
Cosmic rays

## Slide 5: System test and analysis @LANL
Readout 7 channels from a full module
  Cosmic rays
  7-chan SiPM readout
  LeCroy4413 discriminators
  V1495 trigger logic + TDC read out
  (also full 4-channel waveform readout with a scope)
  E906 upgraded DAQ and firmware
Plan to move the whole standalone DAQ system to Fermilab for the commissioning
Also offline data analysis!
TDC_1
TDC_2

## Slide 6: Results from system test Detector meets the design specs!
Efficiency vs threshold
  Eff = 96~98% @20mV
Time resolution vs threshold
  Better than 1nS @20mV
  Fermilab RF = 19nS
Desired: Eff. > 95% (Eff_min > 90%)
Low amplitude,
optical coupling problem?
Low amplitude,
optical coupling problem?
Desired Time-resolution: better than 5nS
Threshold: ~ 20mV

## Slide 7: Pre-installation Test @Fermilab
Beam test of a single channel bar to check/confirm background rate etc.
  Open access this week, Mon-Wed
Single channel readout integration and test in E906

## Slide 8: Installation Plan
Visited and discussed installation plan with Fermilab in Feb, 2017
4 boxes joined
2 vertical beams hold this assembly
Anchored to floor and overhead I-beams, details under analysis (St-1); default =2B
In progress:
Details of mounting points
Safety review document in progress

## Slide 9: To-do and Plan
Complete SiPM installation this week
  Readout plates available Monday
  Install the calibration clear fibers
Fully assembled detector shipped to Fermilab for installation
  Shipping in the week of March 12 (~3/16 departure)
  Complete Fermilab safety document for review, to be ready for installation
Work in progress at Fermilab
  CAMAC crates & LeCroy 4413 installation
  Pre-installation beam test
  LV/HV PS and distribution boards test & installation
  To be ready for installation and commissioning

## Slide 10: MAPS LDRD Progress Updates
MVTX Pre-proposal submitted to DOE through BNL
  A milestone achieved early!
  Build MVTX collaboration, and growing
  Cost and schedule updated
  BNL directors review planned, ~ mid April 2017
LDRD transition plan developed
  Reviewed and discussed a plan, Jan 12, 2017
Readout Electronics R&D
  Single chip MAPS evaluation board tested at LANL, low speed readout
  High-speed readout MOSAIC test bench arrived @LANL, being installed
  5 single-chip MAPS boards with high-speed readout adaptors ordered
  Ordered 2 Readout Units (RUv1), will be available April/May, 2017
  Obtained 2 Altera evaluation boards – CRU emulation
  An EE postdoc candidate identified – Dr. Wei LU from BNL instrumentation
  A joint R&D with TPC group to explore ATLAS FELEX readout option for sPHENIX
Mechanical integration
  Conceptual design being developed
  Interface to possible INTT intermediate tracker
MAPS staves and readout test @CERN
  Send LANL staff/pd to work at CERN to assemble and test MPAS modules
  Planned: April – September, 2017

## Slide 11: MVTX Pre-Proposal Submitted to DOE

## Slide 12: High-speed MAPS readout test bench @LANL
MOSAIC board
  Readout two staves, 20 channels total
  Will allow to test FireFly cables

## Slide 13: R&D at LANL:MAPS Chips
- Have one chip with slow readout working;
- 5 more on the way to build a telescope at LANL
A single chip:
15 x 30 mm active area
A 5-single-chip MAPS telescope

## Slide 14: ALICE Readout Unit – Prototype 0
Expect to get 2 next version RUv1 ~April/May, 2017

## Slide 15
From Pat McGaughey
Two being tested at LANL

## Slide 16: sPHENIX Readout and Controls
RUv1: will be available ~April/May, 2017
CRU: available ?? 2 Altera Evaluation boards being used for R&D
UT-Austin and LBNL: on RU and slow controls, LV, HV

## Slide 17: ALICE/ITS Current Status

## Slide 18: ALICE/ITS Current Status

## Slide 19: ALICE/ITS Current Status
LANL@CERN
LANL staff working at CERN to
produced and test staves: April – Sept. 2017
RUv1

## Slide 20: New Physics ideas and simulations
A new physics probe: beyond b-jet
  B-hadron physics at low pT
  low pT B interaction with QGP
  B-hadron identification

## Slide 21: To-do and Plan
Feasibility review report
Transition plan report
Readout R&D @LANL
  MOSAIC test bench,
  high-speed read out of multiple MAPS chips
  Test Firefly cables, 5m, 10m etc.
  Readout with RUv1 for single MAPS chip
  LV, HV and slow controls with RUv1 on a single MAPS chip
  CRU/Altera evaluation boards emulation
  Follow up FELIX development
MAPS stave production and test at CERN
  Produce 4 staves
  April – Sept., 2017
  Train LANL staff/postdoc
Physics simulations
  B-jet and B-hadron identification
Pre-proposal review etc
  BNL Directors review, ~mid April 2016
  Develop a full proposal

## Slide 22: LDRD Project Overview Ming Liu, P-25 December 5th, 2016
LDRD Goals
  Develop a new QGP physics program with heavy flavor b-jet measurements in sPHENIX at RHIC
  Carry out key detector R&D and develop a new MIE proposal to DOE to build a state-of-the-art MAPS-based high precision vertex detector to support the b-jet physics program in sPHENIX
Project Scope, Plan and Milestones
  Experimental tasks
  Theoretical tasks
Cost, Schedule, Procurement and Risk Management
Organization
sPHENIX/MAPS Project Web page:
https://p25ext.lanl.gov/maps/

## Slide 23: MAPS-sPHENIX Electronics Integration
ALICE readout path
Plan B: sPHENIX readout path (held as contingency)
MAPS FEM
busy out
DCM2
EvB
existing design
existing sPHENIX design
modified design,
starting with ALICE boards
existing ALICE design
trigger in
Plan A:
reprogram
New development:
- Joint TPC & MAPS readout R&D
ATLAS FELIX Readout Unit
vs ALICE/CRU?