## Slide 1: St4 prop tube progress
Last visit to Fermilab: 10/18-22
  Imran and Ming
Work done
  Assembled 80-20 frames for one plane
  Established frame assembling procedure
  Identified missing pieces, T-nuts, L-straps …
  Tried to directly read out modules with TDC…

## Slide 2: Putting them together …

## Slide 3: Frame with one module (8 or 9 modules total for one plane)

## Slide 4: Needed: custom T-nuts for Al plates/straps

## Slide 5: Needed: L-shape module stoppers

## Slide 6: One completed 80/20 frames

## Slide 7: Supporting I-beam structure

## Slide 8: Supporting frame

## Slide 9: Attach frame to the cross I-beam

## Slide 10: Prop tube frame and the cross I-beam

## Slide 11: Parts list – need to make/buy them …
Custom T-nuts for side AL plates
  Strap #1: hole spacing = 1. 66?
  Strap #2: hole spacing = 1.5”
Long Al plate/bar to attach the 80/20 frame to cross I-beam.
  L-shape ½” thick Al plate?, similar to strap #2
Cables from module front-end to patch panel connectors:
  LV cables: 9 per plane, total 9(8)x4=34
  HV cables: 9 per plane, total 9(8)x4 = 34
  Signal cables: 9 per plane, total 9(8)x4 = 34
  Gas tubs: 2(3) lines per plane, total 10 tubes

## Slide 12: Schedule and progress
Work in progress @LANL
  Assembling patch panels : a few weeks
    HV feed through panels
    LV panels
    ECL signal panels
  Will order custom T-nuts, L-shapes stoppers ~< 2 weeks
  Need to order short LV cable “green connectors”: ~<2 weeks
  Order short HV cables (module to patch panel) : ~< 2 weeks
Fermilab
  Make LV and ECL cables:
    short ones (module to patch panels)
    long ones (PS /rack to patch panels)
    LV wires from KTEV?
    ECL cables from KTEV?
  Make long Al plate/bar to attach 80/20 frame to I-beam?
Travel and work plan
  12/8 is the earliest for me..
  Need to check others who can help
  Chuck and Paul offered to help to speed up things at Fermilab…