## Slide 1: Experimental hall as of 07/30/2010

## Slide 2: E906 Status

## Slide 3: Gas rack

## Slide 5: Ion absorbers

## Slide 6: TDC spectra: Mod. #35 Ar/Co2 =80/20 HV=1900V ΔTmax = 2.5 uS
Trig.
Comm. Stop
signal
Time
TDC
Drift Time

## Slide 7: ST4 Pre-Installation work
Need more absorbers to cover the ends of ST4 tuebs + electronics
  Current ion blocks: 126” x 39”(99cm)
  St4 tubes: 144” long (156” frame)
  Need to add 9” absorbers on both sides
  This will affect the design of the support structure
Support structure: will be available end of Sept/early Oct ?
  Wide enough to allow drop-in of the whole chamber/plane from the top
  Patch panel be attached to the 80-20 frame
  Allow enough clearance along z-direction, ½’ per plane?
  Attached the 80-20 frame to an I-beam before the installation
  Directly drop in the whole plane with the I-beam
Cables layout
  LV
  HV
Schedule: depends on the beam schedule, assuming mid of Oct. test beam
  Start assembly in middle of Sept? (Andrew + Ming/others)
  Complete the installation in middle of Oct.
Plan – B
  Slide-in requires asymmetric support structure and more complicated design

## Slide 8: Plan-B: installation
Wall to ion block = 171”
With shortened A-frame on the loading side to the edge of the ion block, we could have 170” clearance
Frame lifting points:
  at least +15” in on both sides
Patch panel
  SHV 9 channels
  LV: 3 channels (+5V, 2A fuse; -5V, 3A fuse)
  Signal: 9/8 connectors

## Slide 9: ST-4 Scint. Frame

## Slide 10: Prop Tube Lifting Points (similar to ST-2 chambers)

## Slide 11: Assembling area

## Slide 12: Installation – drop in w/ crane

## Slide 13: One Power rack for ST-4
HV PS:
  17 modules = 4 NIM crates
LV PS:
  +5V and -5V
  Distribution to 4 planes with fuses

## Slide 14: Patch panel on the detector
9 SHV feed-throughs
3 gas feed-throughs
  3 working gas inputs: ¼” line
  1 pressure feed back: 3/8” line
  1 exhaust: ½”
  1 N2/dry air input: 3/8” line
  Hole sizes?
9 ECL signal connectors
9-chan LV Distribution cards
  +5V with 1A fuse
  -5V with 2A fuse
  Ground line
Cables from module to patch panel
Feed through connectors
  LV
  HV
  ECL

## Slide 15: HV PS
+2500V (1800~2200V)
34 channels total
17 dual channel PS
  4 crates (<6 per crate)
Cables
  Module to patch panel
  PS to patch panel

## Slide 16: LV distribution card

## Slide 17: 64-channel TDC & ECL connectors:
Need low profile connectors
Amphenol PART# CAT 812
#842-812-3422-134

## Slide 18: 30’ ECL cable test (40’ longest)
Timing
  < 5nS smearing (NIM leading edge time)
  dT0 = 2.5nS +/-0.5, (NIM signal output from a pocket pulser)
  dT1 = 4.0 ns +/- 0.5 (10’ cable), NIM output
  dT2 = 4.5 ns +/- 0.5 (30’ cable), NIM output
X-talk
  Adjacent channel <= 3mV/@1V = 0.3%
  Next adjacent < 1mV, undetectable
ECL to TDC
  Need low profile connectors, double layers, 64 channels per TDC
  Connectors:
    Amphenol PART # CAT:812
    842-812-3422-134

## Slide 19: LV PS
+5V: 0.3A => 9x0.3 = 3.0A
-5V: 0.8 A => 9x0.8 = 7.5A
Total 4 planes:
  +5V: 4x3= 12 A
  -5V: 4x7.5 = 30 A
Cables
  Module to patch panel
  PS to patch panel

## Slide 20: schedule
A/T-frame availability
  End of Sep or early Oct ?
ST4 assembly work
  1 week / per plane
  4 weeks total
Gas rack & location
  Sept or later?
Test beams delivered to Exp Hall?
  mid Oct or later?

## Slide 21: E906 to do list
Chamber installation
  Identify 34 good modules for the final assembly
  Obtain engineering approval from Fermilab for the mechanical supporting structure
  Develop LV, HV and signal cable layout plan
  Make LV, HV and signal cables
  Design and make LV, HV and signal patch panels
  Detector installation
  Continue flowing gas and conditioning tubes with + and – HV.
Commissioning
  Check ECL signal quality at rack input
  Optimize electronics thresholds for each board with the final gas
  Determine optimal operating HV level
  Test prop tubes with cosmic rays (or source?), study drift time, efficiency etc.
  Readout with the final TDC boards, fix timing relative to trigger etc
  channel mapping, be part of the offline tracking
  Slow control and monitoring
    LV, HV, Temperature, Pressure, drift time, gain …
Get ready for beams in Oct. 2010
  Timing in the detector

## Slide 22: E906 Summer Work Plan http://projects-docdb.fnal.gov:8080/cgi-bin/DisplayMeeting?conferenceid=32
June: 1 week + 1 Summer ACU Student
  Work to do
    Test 7 wrong shaped modules, identify best 4 for final assembly
    Replace frontend board and preAmp card for two modules
    Develop installation plan – cable layout etc
    Design LV distribution cards
  Picture frame
    Order supporting frame materials from 80-20, and get them in ~2 weeks.
  Manpower
    Lei, Ming, Pat + local ACU students
  Schedule: middle of June
July: 1 week + 1 Summer ACU student?
  Work to do
    Test and conditioning all modules with good gas, determine the optimal operating HV for all modules
    Make and layout LV, HV and readout cables
    Complete the tech note and obtain Fermilab Engineering approval for the supporting structure
    Develop detector installation plan
  Manpower
    Lei, Andrew, Ming, Pat, Melynda + local ACU students?
  Schedule: early-mid July?
Aug. + Sept: 2~3 weeks
  Assemble the modules, install detector
  Test readout, optimize signal to noise ratio, study electric ground, timing etc.
  Need full readout cards ( when? )
  Manpower
    Andrew, Ming, Melynda, Christine …
  Schedule: mid/late Sept. ? dep. on the availability of DAQ and final gas
Ready for Experiment in Oct. /Nov. ? ~ 3week
  Other subsystems, Station-1 chambers particularly, won’t be ready until Oct.

## Slide 23: Future Projection
Hardware support: 2011 – 2013
  1/2 FTE
  Detector calibration and monitoring
Physics analyses: 2011-2014
  Fermilab FY 2012 long shutdown?
  1PD + 1/4ST
  Quark energy loss: p+A/p+p
  Parton distributions: p+d/p+p
  Simulations and data analysis
  Final publication