## Slide 1: E905 Prop tube status 03/06/2011
First two X and Y planes
  Y-plane installed Monday 2/28
  X-plane installed Tuesday 3/1
3rd plane (X) installed Wed. 3/2/2011
4th plane (Y) installed Friday 3/4/2011

## Slide 2: Y1-plane installation 2/28/2011

## Slide 3: X1 plane installation 3/1/2011

## Slide 4: 1st X and Y planes installed
St-4 Y and X planes

## Slide 5: Installing the X2 plane

## Slide 6: The last plane
One module with wrong shape
One module with wrong gas tubing

## Slide 7: The only wrong shaped module
Installed on the top of the last Y-plane

## Slide 8: Installing the last plane

## Slide 9: X and Y planes
X1 and Y1
X2 and Y2

## Slide 10
16 15 14 13 12 11 10 9
8 7 6 5 4 3 2 1
NIM channel map
16 15 14 13 12 11 10 9
8 7 6 5 4 3 2 1
IP, Top View
16 15 14 13 12 11 10 9
8 7 6 5 4 3 2 1
16 15 14 13 12 11 10 9
8 7 6 5 4 3 2 1
X1
……
16 15 14 13 12 11 10 9
8 7 6 5 4 3 2 1
16 15 14 13 12 11 10 9
8 7 6 5 4 3 2 1
16 15 14 13 12 11 10 9
8 7 6 5 4 3 2 1
……
X2
Y1
Y2
READOUT
ELECTRONICS
X
Z

## Slide 11
16 15 14 13 12 11 10 9
8 7 6 5 4 3 2 1
NIM channel map
IP, Side View
X1
16 15 14 13 12 11 10 9
8 7 6 5 4 3 2 1
16 15 14 13 12 11 10 9
8 7 6 5 4 3 2 1
16 15 14 13 12 11 10 9
8 7 6 5 4 3 2 1
……
9 10 11 12 13 14 15 16
1 2 3 4 5 6 7 8
16 15 14 13 12 11 10 9
8 7 6 5 4 3 2 1
16 15 14 13 12 11 10 9
8 7 6 5 4 3 2 1
……
X2
Y1
Y2
Ground Floor
Y
Z
Wrong
Shpd mod.

## Slide 12: The old test area

## Slide 13: LV system
Delta LV PS:
  5V & 20A each
  Need connectors
Per plane
  +5V, 0.5x9=4.0A
  -5V, 0.75x9=6.8A
Two Delta
  +5V and -5V
Ground configuration

## Slide 14: LV system (cont.)

## Slide 15: HV modules
36 channels
18 modules

## Slide 16: Patch panels
LVs, HV
ECL signals

## Slide 17: Station-4
Prop tubes
  X1, Y1, X2, Y2
Hodoscopes
  X, Y

## Slide 18: E906 as of 3/4/2011

## Slide 19: To do list
LV system
  PS: Delta 5V supplies from Fermilab, have 5 of them, not fully tested yet
    need a minimal of 4 for (X1Y1) and (X2Y2), but can use more if available
    Need some small connectors for master LV cables, cable to PS
    Long/gauge-8 (?) LV master cables are recycled from previous LANL Exp.
HV system
  Have 2 modules right now, a total of 4 HV channels, good for one channel per plane
    Like to have 16 more
    Independent HV channel for each module
    Long HV cables recycled from precious Fermilab Exp.
ECL cables to TDC boards
  Need to make 36 ECL cables, length TBD
  Cables from previous Fermilab Exp.
Gas:
  to be worked on by DaveN.
  D0 muon gas?
  Ar/Co2 for cosmic ray?

## Slide 20: Many Thanks to …
E906 collaboration and particularly people
@ Fermilab:
Chuck, Paul, Tom, Kevin, Dave Christian, Dave Northack, Kaz, Grass, Ting, Donald and more…
@ LANL:
Walt, John, Mat, Andrew Green, Jackie and Jose and more
E906 members from LANL