## Slide 1: St4 Muon detectors: status 06/11/2011
All patch panels and cables installed and connected
The system is ready for commissioning!
  LV, HV, Signal, Gas
HV:
  4 cables connected to HVPS,
    1A and 1B for first two planes
    2A and 2B for the two backplanes
LV:
  PS: 3 working KTeV/UCLA
  +/-5V, 18A each channel
  made 4 LV cables, no feedback sensors connected yet
  Voltages at patch panels:
    +4.7V and -4.7V for single LVPS
    +4.6V and – 4.4V for doubled ones (two front planes)
ECL cables
  36 of 35’ long ECL cables made, tested and connected, ACU students
Gas lines
  4 lines connected, now flowing Ar/Co2 @0.5CFH per plane
Ming: 6/7-11
Christine: 6/10-16

## Slide 2: Signal ECL cables 36 x 35’ long
Thanks ACU !

## Slide 3: St4 prop tubes

## Slide 4: LV and HV PS

## Slide 5: Gas System 3-input and 1-output per plane

## Slide 6: Multi-module TDC Readout Test

## Slide 7: Other subsystems

## Slide 8: Issues and Commissioning Plan
System grounding and electronics noise
  Start to work on it
External pulser and calibrations
  Some bad T-connectors? Bad pulser signal propagation
  Some modules show no pulser signals
    But Can see cosmic signal with HV on
    Run 9 calibration cables per plane?
Multi-module TDC readout
  5 TDC cards available, good for two planes (18 ECL cables)
    Unstable TDC and controllor, need FPGA code update
  Were able to read out 2 cards and confirmed the prop tube/TDC timing was right
Cosmic data with the Hodoscope trigger

## Slide 9: E906 beam schedule
Originally: beams ~ after mid of June
Beam line vacuum leak discovered two weeks ago
  Various options are being explored
  Probably insert a new smaller beam pine
Beam possible/likely after July 4th break,