## Slide 1: E1039 DP & PropTube Work Plan 1/13-17, 2020
DP detector commissioning
  ORC recommendations
  Detector check out and operation
  DAQ integration of Taiwan TDCs
  Timing-in DP detectors
Prop tube commissioning
  Fix 3 bad modules
  Improving readout with new preamp cards
  9 working spare preamp cards available now
  Threshold scan & optimization
Cristina, Ming, Kun et al
Helen, Ming et al
Misha, Sho, Zongwei, Kenichi
Mindy, Forhad, Rick et al

## Slide 2: End of the Week Summary – a Great Success 1/17/2020
Proptube detectors
  all 3 bad modules recovered, as good as before
    P1X, M9 and M3
    P1Y, M8
  Threshold scan for optimization
    Check noise rate vs threshold - In progress
Dark photon detectors
  All detectors are working
  3 low light yield channels
  Integrated Taiwan TDCs into main DAQ
    initial TDC spectrum show DP detectors are timed in.
Work by:
Helen and Ming, with help from
Mindy, Forhad, Rick, Kun et al
Crisitina, Sho, Zongwei, Kenichi, Kun, Ming et al

## Slide 3: Accomplished – Fixed all bad prop tube moudles
Checked hits and TDC timing distributions
Ready for beam commissioning!

## Slide 4: Accomplished - DP commissioning
Completed ORC recommendations
Turned on the whole detector
  Checked all channels with calib LED
  Fixed all lose/disconnected cables
Setup the LDE pulsar system
Integrated Taiwan TDC into the main DAQ
Took data with cosmic, with E1039 Hodo Triggers, with the rest of the E1039 detectors
Ready for beam commissioning!
DP St-1 TDC
DP St-2 TDC

## Slide 5: Day-1: DP Commissioning Work Plan – 1/13/2020
Address recommendations from ORC
  Rearrange power cables etc.
  Done today, see photos
To turn on DP detectors
  Standalone readout with NUC
  Use calibration system to check all channels
  Use V1495 to do “TDC” in standalone mode
Integrate TDC readout into DAQ
  By the end of this week
Trigger integration next week
  Work with Michigan Trigger group
  Cristina + Michigan
Cristia, Sho, Zongwei, Misha, Kun, Ming

## Slide 6: DP ORC Recommendations

## Slide 7: ST-2 Rack: #1, #2, #4 and #5 - Put ST-2 Rack Power Cables inside the Rack, all cable tied to the rack frame - Covered 3 unused outlets with electrical tape

## Slide 8: #3 and #6 Moved DC power cables separated out from other signal cables

## Slide 9: St-1 Rack: #1 - AC power cords tied to the rack frame

## Slide 10: #2 VME power cables tied to the Rack frame and Al-frame

## Slide 11: #3 Top power cord tied to the rack frame - Could take a better picture to show the tie

## Slide 12: DP detector response to the external pulsar
NIM (trigger) -> TTL (~10kHz, 100nS wide) -> lights ->SiPM signal

## Slide 13: DP Work Photos

## Slide 14: DP Operation and Monitoring

## Slide 15: Prop Tube Work, Tuesday +
Replace front panel for threshold
Replace preamp cards to improve “noise” & “oscillations”
Retune or scan threshold for each module
  Scanning
  Check existing data
Do HV scan
  Cosmic data with H2 (H3) & H4 trigger
Helen, Mindy, Kun, Ming et al
Prop tube cosmic signal

## Slide 16: Prop Tube Work Photos
P1X, M9
P1Y, M8

## Slide 17: Trigger Hodoscope Timing Study - Later this week if possible
Use DP calibration system to send light to all 4 Hodo planes
  Long fibers are needed, 4+,
  Check timing
Setup DP calibration self pulse generator
  10kHz trigger rate, can be adjusted through the top gate generator
  100nS TTL pulse to LED board, can be adjusted through the bottom gate generator
  4 LED spares for the HODO timing check
The system is ready for this 1/17/2020
  Will do it at next trip to Fermilab
Kun, Forhad, Ming et al