## Slide 1: E1039 Summer Work Plan
Kun, Mindy, Andrew, Xuan, Matt, Zongze, Ming
5/26/2019
Updated 5/28/29
- DP trigger system
- Prop tubes

## Slide 3
DP-1
DP-2
KMAG
RACK-1
RACK-2
Rack-3/DP Trigger
(L2 rack)
-VME:
4xV1495
L1 trigger
DC-2
DC-2
RACK-3 (exists)
DP/V1495
L2 rack/V1495 (Rack-3)
DP trig(OR)
DY trig(AND FPGA trig’s)
beam
(4 Qs)
DP Trigger New Layout (5/28/2019)
Rack-1/ST-1: 4x 80 ch
-CAMAC (10 x LeCroy 4413)
-CAMAC (10 x LeCroy 4413)
-NIM/BlueLogic trigger
Calibration
SiPM PS
Rack-2/ST-2: 4x 50ch
-CAMAC (8 x LeCroy 4413)
-CAMAC (8 x LeCroy 4413)
-NIM
-SiPM PS
Possible extended SMA-Lemo, ~5’; cable tray
New Rack-2, SMA-Lemo unchanged, cable tray, new power to Rack-2
Existing cable
tray
- Run all cables under
the KMag, with cable tray
RACK-4 (exists)
VME/TDC (6)
VME/TDC (6)
Signal cables (40’), under kMag

## Slide 4: ST-1 Cables: 40’ long
Run all cables under the Kmag?
ST-1 cables:
40’ SMA-Lemo
(under KMag)
Length = (8+4)/down + 17 + 6/up
= 35’ to CAMAC crates
Rack-1

## Slide 5
Signal cables

## Slide 6: Rack-1: Station-1
Rack -1:
- DP/V1495 move to
East L2 trigger rack
Bring all ST-1 CAMAC (2) to here
Keep NIM
Keep SiPM PS
Rotate the rack 180dgr, cables facing beam
To reduce the overall length of ST-1 readout cables
Install cable tray:
run all power/signal cables over the KMAG
36’ required (cables = 40’)
Layout: top-down (remove 4 V1495 module )
CAMAC, 10 LeCroy 4413 discriminators
CAMAC, 10 LeCroy 4413
NIM for blue logics
VME for calibration system
SiPM power and control system
Power & Cooling:
2 CAMAC,
NIM
VME
SiPM PS

## Slide 7: Rack-2 for Station 2
Move from West to East side, close to DP-2
(no change of configuration )
Layout: top-down
CAMAC, 9 LeCroy 4413 modules
CAMAC, 9 LeCroy 4413 modules
NIM logics
SiPM PS and control
Rack-2
Rack-1

## Slide 8
48”
New DP cable tray on ground
Install Station-2 Cable Tray
New DP ST-2 rack
here
Cable length = 12 + 15 + 6 = 33’. (40’ cables)

## Slide 9: Rack-3/4: DP V1496 L1 Trigger & TDCs
Rack-3
DP
V1495
DP
2 VMEs
(12 TDCs)
Rack-4
Run 25’ 17-chan ribbon cables :
CAMAC -> TDC;
CAMAC -> V1495;
25’ 17-chan twist-pair ribbon cables

## Slide 10: Rack-4: TDC Crates
Install 2 VME for 12 TDC modules in this rack
VME: CPU +6TDCs + TS
VME: CPU +6TDCs + TS
Run ribbon cables from ST-1/ST-2 CAMAC modules
Rack-1
25’ ribbon cables

## Slide 11
Overhead Cable Tray:
TDC ribbon cables

## Slide 12: Prop-tube Plan
4 good modules are available
Shortage of readout cards
Install 4 bubblers
Schedule

## Slide 13: DP Work Plan – To Do’s
DP trigger detector work
  Re-arrange Readout Crates
    All CAMAC on East
      Discriminates: 10x2 + 8 x 2
    All TDC/VME on East
      8+4 TDCs
    All VME on East (TDC & V1495)
      V1495: 4
      Calibration system:
  Re-cabling
    TDC ribbon cables (25’+)
    SMA-Lemo cables (40’)
  Check channel mapping
  Check grand loop
SMA-Lemo cable extension
  160+100=260, 5~10’ cables for St-1(?)
  ACU students help installation and mapping
Slow control
  Resb. Pi @IR
    1 Master + 6 slaves
  ssh link from counting house
    SpinQuest LAN/Gate2 access
    One command
    SiPM HV table
    Set HV, readback (I, T) for each SiPM
  Online monitoring?
    (I,V,T) of SiPM
TDC boards: 64 chan/TDC
  2(80)+ 1(50) = 3 each quadrant
  Total 12 TDCs
  2 VME crates (6+6)
V1495: 4
SMA-Lemo cable = 40’

## Slide 14: DP Work Schedule
May 26-29
  Move CAMAC crates from W->E
  Re-cable SMA-Leom, ST1, determine extension length
  Re-cable Control cables (R. Pi) for ST-1
  Plan cable tray for ST-1, ST-2
Lemo extension cables
  10~20’/TBD, 320 ? From Fermilab?
  ACU student?
  New cables? $$?
July 8 – 19
  Collab. Meeting 7/15-16(Mon-Tue)
  Install and map cables
  Operation and calibration
Aug 1-15
  Cosmic run?
  Provide trigger to readout other detectors
    DC 2/3..
    Prop-tube
Software work
  Integrate into global tracking
    Include DP hits in the tracking code (masking)
  Slow control display
    SiPM (V, I, T) for all DC, PorpTubes
Physics & detector simulation
  DY & J/Psi target
  DY & J/Psi beam dump
  Lookup tables

## Slide 15: Prop Tube Plan & Schedule, and more
Replaced 2 modules
  July 8-19
  Coll. Meeting @FNAL 7/15-16
  Jeff B. or Hubert
  Xuan, Matt, Ming et al
Commissioning with cosmic trigger (DP + Hodos)
  August 1-15?
  DP+Hodc trigger
  Readout Prop-Tube + DC2/33
E1039 detector commissioning
  9/1-15?
  Full spectrometer,
  all chambers
  Slow control system
Beam @SpinQuest
  Mid October 2019

## Slide 17: DP Trigger & PropTube Work Plan

## Slide 18
DP ST-2 rack?
Move
DC-2 rack upstream
DP cable tray above ground
SMA-Lemo cable:
2x(48 + 48) + (46 + 12) + “12” = 262”
= 21.8’
For ST-1:
Additional a few ft to ST-1 rack

## Slide 19
DP/V1495 move to
East L2 trigger rack
Bring ST-1 CAMAC
& TDC to here
Keep SiPM PS
New DP cable tray above ground

## Slide 20
CAMAC, SiPM PS
move to East

## Slide 21
DP-1
DP-2
KMAG
RACK-1
Location?
RACK-2
ST0-1: 4x 80 ch
-CAMAC (10 x LeCroy 4413)
-VME/TDC(CPU+TS+4TDC)
-VME/TDC(CPU+TS+4TDC)
-CAMAC (10 x LeCroy 4413)
-NIM/BlueLogic trigger
-SiPM PS
ST-2: 4x 50ch
-CAMAC (8 x LeCroy 4413)
-VME/TDC (CPU+TS+4TDC)
-CAMAC (8 x LeCroy 4413)
-NIM
-SiPM PS
DP Trigger
-VME:
4xV1495 L1 trigger
Calibration
-NIM/BlueLogic
Trigger
DC-2
DC-2
RACK-3
L2/V1495
DP trig(OR)
DY trig(AND FPGA trig’s)
beam
(4 Qs)
DP Trigger New Layout-2
East
West