## Slide 1: DP Status
Halen, Zongwei, Kun, Andrew, Sho, Cristina, Dylan, Ming et al
07/19/2019

## Slide 2: Progress on 7/19/2019
ST1/Rack
  PS layout plan developed, calibration fibers are ready for installation
  installed all CAMAC modules
  Installed VME crate to host 6 Calib boards
  Connected all ST-2 calibration fibers (6 x 2) to the calib boards
  A NIM crate is ready for installation
  St-1 readout cables are ready to be connected to CAMAC modules
ST-2/Rack
  Rack-2 is fully instumented
  ST-2 calib fibers all plugged into the cailb boards installed in Rack-1
  ST-2 PS are installed and connected, including the master node;
  ST-2 readout cables being plugged into CAMAC module
TDC rack
  A good/previous VME with 4 V1495 installed
  A good VME is ready for installation
  TDCs and controllers available (Andrew/Kun)
Cristina and Dylan visited the hall and
discussed future work plan with Kun et al:
Cristina will be the local expert
for DP detector! Thank you!

## Slide 3: To Do List for Coming Weeks
Connect St-1 readout cables to CAMAC modules
Install St-1 4 PS slaves
Install St-1 calibration fibers
Install a NIM crate in Rack-1, setup trigger/pulser for calib boards;
Install cable trays under Kmag
Build/find a Al support frame for ST-1 PS slave nodes
Connect remaining St-2 readout cables to CAMAC modules
TDC crate
  Install all TDC modules, a VME crate will be shipped from LANL
  Connect ribbon cables to both TDC and V1495 modules
Complete simulation for DP trigger
  DP signal
  DY & J/Psi signals from target
ORC review in late ~July
Test DP detector
Run DP with rest of other
subsystem in Aug-Sep

## Slide 5: DP Detector Work Update
07/18/2019
Halen, Zong-Wei, Kun, Dylan, Ming

## Slide 6: Status as of Today: 7/18/2019
ST-1:
  Rack wheels removed
  Rack in the location good for both ST-1 readout cables and ST-2 calibration fibers
  Calibration system will be installed at the bottom of Rack-1.
  To Do’s
    Install CAMAC modules
    Install readout cables
    Install PS cables, leave PS boxes on the floor, build z box to hold 4 PS boxes under the KMag
    Install calibration optical fibers
    Identify and install a VME crate at the bottom of Rack-1 for Calib system (need backplane power)
    Order two cable trays
ST-2:
  Rack-2 wheels removed
  V1495 crate moved to the TDC rack (bottom)
  Installed ST-2 Power supplies, including Master mode
  To-Do’s
    Install CAMAC modules, install readout cables
    Install calibration optical fibers
TDC rack:
  Installed VME crate with 4 V1495 modules
  Removed unused panel
  To-Do’s
    Install 2 VME crates
    Install Ribbon cables for TDC and V1495
Identified all misc. items
  Calibration fibers, 25’ ribbon cables (26+26+24, 4th box is missing)
  7 PS boxes, with cables (25~29’ long)
  LeCroy 4413 modules
  Calibration fibers : ~40’ long

## Slide 7
25’ ribbon cables
Identified: 76 cables
- one more box of cables
4 PS and 25-29’ Cables
Under KMag, for ST-1
ST-2 rack reconfigured
VME/V1495 and Calib removed
PS master + 2 slaves installed
Photos of the Day : 7/18/2019
Zong-Wei, Halen & Dylan at work

## Slide 8: New Rack Locations: ST-1 & ST-2
ST-1
ST-2
Rack-1, removed wheels, against the kMag;
Readout cables are long enough,
no need of extensions!
Readout cables are run under the kMag now; but not connected
SiPM cables are short, 27’~29’ only; a new location for PS?
Rack-2 moved close to ST-2
Readout cables are long enough
SiPM power cables are short, but long enough to reach the new Rack-2 location

## Slide 9: ST-2 Rack and Cables

## Slide 11: SiPM Power Boxes & Cables
SIPM power box provide LV and HV for SiPM and preamps
  LV = +5V
  HV = 52V(various from SiPM to SiPM)
ST-2 power cables are already installed
  Length ~ 280” ~ 24’
ST-1 power canbles are in the CH dark photon cabinet;
  One Master node
  4 salves nodes, for each quadrant;
  Only 25~29’ long, can’t reach the current ST-1 rack

## Slide 12
- 1 Master node
4 power boxes for ST-1
Cable length: 25~29’
Need to make a small Al-frame to hold 4 ST-1
PS boxes under the kMag;
(2+1)” x 4 = 12” toal;
Clearance under kMag = 30”

## Slide 13
DP-1
DP-2
KMAG
RACK-1
RACK-2
Rack-3/DP Trigger
(L2 rack)
-VME:
4xV1495
L1 trigger
DC-2
DC-2
RACK-3 (exists)
DP/V1495
L2 rack/V1495 (Rack-3)
DP trig(OR)
DY trig(AND FPGA trig’s)
beam
(4 Qs)
DP Trigger New Layout (7/18/2019)
Rack-1/ST-1: 4x 80 ch
-NIM/trigger logic
-CAMAC (10 x LeCroy 4413)
-CAMAC (10 x LeCroy 4413)
-VME/Calibration
Rack-2/ST-2: 4x 50ch
-NIM/trigger logic
-CAMAC (8 x LeCroy 4413)
-CAMAC (8 x LeCroy 4413)
-SiPM PS for ST-2 only + Master
Cable trays
New Rack-2, SMA-Lemo unchanged, cable tray, new power to Rack-1,2
Existing cable
tray
- Run all cables under
the KMag, with cable tray
RACK-4 (exists)
VME/TDC (6)
VME/TDC (6)
Signal cables (40’), under kMag
St-1 SiPM PS(4),
under kMag

## Slide 14: To Do List 7/18/2019
Remove Rack-2 wheels
  Reinstall SiPM PS (Master + 2 slaves), 2 CAMAC, 1 VME/Calib, 1 NIM crate
Put 2 cable trays under KMag, (Kun will get two AL cable trays deon Lab 16/?)
  Run all cables under the kMag
Install power system and cables
Install optical calibration system
Run calibration system
  Check the signal yield for all channels, with a scope
Install all CAMAC modules
  Connect all readout cables to CAMAC
Install 2 VME crates (to be shipped from LANL?) and all TDCs, with CPUS
Install 4 V1495
Connect ribbon cables, CAMAC -> TDC, V1495
Integrate TDC into DAQ
Integrate DP trigger into E1039 global trigger
Find a new location for ST-1 SIPM power boxes:
Within 25’ cable length

## Slide 15: Misc. Items
LeCroy 4413 discriminators (in downstairs)
  ST1: 10 + 10
  ST2: 8 + 8
  Check with Marshall
2 VME crates for TDC boards - TDC(64ch)
  ST-1: 2x8
  ST-2: 1x4
  2 VME controllers (check with Andrew)
  (2 at LANL, ship one to Fermilab; use the current V1495 crate for the 2nd TDC, and add one VME to provide Power to Calib.)
New ribbon cables for TDC and V1495 from CAMAC
  25’ 17-chan twist-pair ribbon cables
  Found 3 boxes in CH (26+26+24 = 76 cables), Kun will search for the 4th one.
Calibration optical fiber length = 40’

## Slide 16: Cable Mapping Docs
General note from Sho:
https://docs.google.com/document/d/1GCfWciYzyofXXVpVOjkVvYq3BZp9g7cztyc5k015Yp4/edit?usp=sharing
Detector patch panel mapping,
https://p25ext.lanl.gov/darkphoton/hardware/cable_mappings.html
CAMAC crate = 12”;
VME crate = 14”, with fan;
NIM crate = 9”
Power box = 2”
LANL Dark Photon home page:
General information about the dark photon trigger detector:
https://p25ext.lanl.gov/darkphoton/

## Slide 18: E1039 Summer Work Plan
Kun, Mindy, Andrew, Xuan, Matt, Zongze, Ming
5/26/2019
Updated 5/28/29
- DP trigger system
- Prop tubes

## Slide 20
DP-1
DP-2
KMAG
RACK-1
RACK-2
Rack-3/DP Trigger
(L2 rack)
-VME:
4xV1495
L1 trigger
DC-2
DC-2
RACK-3 (exists)
DP/V1495
L2 rack/V1495 (Rack-3)
DP trig(OR)
DY trig(AND FPGA trig’s)
beam
(4 Qs)
DP Trigger New Layout (5/28/2019)
Rack-1/ST-1: 4x 80 ch
-CAMAC (10 x LeCroy 4413)
-CAMAC (10 x LeCroy 4413)
-NIM/BlueLogic trigger
Calibration
SiPM PS
Rack-2/ST-2: 4x 50ch
-CAMAC (8 x LeCroy 4413)
-CAMAC (8 x LeCroy 4413)
-NIM
-SiPM PS
Possible extended SMA-Lemo, ~5’; cable tray
New Rack-2, SMA-Lemo unchanged, cable tray, new power to Rack-2
Existing cable
tray
- Run all cables under
the KMag, with cable tray
RACK-4 (exists)
VME/TDC (6)
VME/TDC (6)
Signal cables (40’), under kMag

## Slide 21: ST-1 Cables: 40’ long
Run all cables under the Kmag?
ST-1 cables:
40’ SMA-Lemo
(under KMag)
Length = (8+4)/down + 17 + 6/up
= 35’ to CAMAC crates
Rack-1

## Slide 22
Signal cables

## Slide 23: Rack-1: Station-1
Rack -1:
- DP/V1495 move to
East L2 trigger rack
Bring all ST-1 CAMAC (2) to here
Keep NIM
Keep SiPM PS
Rotate the rack 180dgr, cables facing beam
To reduce the overall length of ST-1 readout cables
Install cable tray:
run all power/signal cables over the KMAG
36’ required (cables = 40’)
Layout: top-down (remove 4 V1495 module )
CAMAC, 10 LeCroy 4413 discriminators
CAMAC, 10 LeCroy 4413
NIM for blue logics
VME for calibration system
SiPM power and control system
Power & Cooling:
2 CAMAC,
NIM
VME
SiPM PS

## Slide 24: Rack-2 for Station 2
Move from West to East side, close to DP-2
(no change of configuration )
Layout: top-down
CAMAC, 9 LeCroy 4413 modules
CAMAC, 9 LeCroy 4413 modules
NIM logics
SiPM PS and control
Rack-2
Rack-1

## Slide 25
48”
New DP cable tray on ground
Install Station-2 Cable Tray
New DP ST-2 rack
here
Cable length = 12 + 15 + 6 = 33’. (40’ cables)

## Slide 26: Rack-3/4: DP V1496 L1 Trigger & TDCs
Rack-3
DP
V1495
DP
2 VMEs
(12 TDCs)
Rack-4
Run 25’ 17-chan ribbon cables :
CAMAC -> TDC;
CAMAC -> V1495;
25’ 17-chan twist-pair ribbon cables

## Slide 27: Rack-4: TDC Crates
Install 2 VME for 12 TDC modules in this rack
VME: CPU +6TDCs + TS
VME: CPU +6TDCs + TS
Run ribbon cables from ST-1/ST-2 CAMAC modules
Rack-1
25’ ribbon cables

## Slide 28
Overhead Cable Tray:
TDC ribbon cables

## Slide 29: Prop-tube Plan
4 good modules are available
Shortage of readout cards
Install 4 bubblers
Schedule

## Slide 30: DP Work Plan – To Do’s
DP trigger detector work
  Re-arrange Readout Crates
    All CAMAC on East
      Discriminates: 10x2 + 8 x 2
    All TDC/VME on East
      8+4 TDCs
    All VME on East (TDC & V1495)
      V1495: 4
      Calibration system:
  Re-cabling
    TDC ribbon cables (25’+)
    SMA-Lemo cables (40’)
  Check channel mapping
  Check grand loop
SMA-Lemo cable extension
  160+100=260, 5~10’ cables for St-1(?)
  ACU students help installation and mapping
Slow control
  Resb. Pi @IR
    1 Master + 6 slaves
  ssh link from counting house
    SpinQuest LAN/Gate2 access
    One command
    SiPM HV table
    Set HV, readback (I, T) for each SiPM
  Online monitoring?
    (I,V,T) of SiPM
TDC boards: 64 chan/TDC
  2(80)+ 1(50) = 3 each quadrant
  Total 12 TDCs
  2 VME crates (6+6)
V1495: 4
SMA-Lemo cable = 40’

## Slide 31: DP Work Schedule
May 26-29
  Move CAMAC crates from W->E
  Re-cable SMA-Leom, ST1, determine extension length
  Re-cable Control cables (R. Pi) for ST-1
  Plan cable tray for ST-1, ST-2
Lemo extension cables
  10~20’/TBD, 320 ? From Fermilab?
  ACU student?
  New cables? $$?
July 8 – 19
  Collab. Meeting 7/15-16(Mon-Tue)
  Install and map cables
  Operation and calibration
Aug 1-15
  Cosmic run?
  Provide trigger to readout other detectors
    DC 2/3..
    Prop-tube
Software work
  Integrate into global tracking
    Include DP hits in the tracking code (masking)
  Slow control display
    SiPM (V, I, T) for all DC, PorpTubes
Physics & detector simulation
  DY & J/Psi target
  DY & J/Psi beam dump
  Lookup tables

## Slide 32: Prop Tube Plan & Schedule, and more
Replaced 2 modules
  July 8-19
  Coll. Meeting @FNAL 7/15-16
  Jeff B. or Hubert
  Xuan, Matt, Ming et al
Commissioning with cosmic trigger (DP + Hodos)
  August 1-15?
  DP+Hodc trigger
  Readout Prop-Tube + DC2/33
E1039 detector commissioning
  9/1-15?
  Full spectrometer,
  all chambers
  Slow control system
Beam @SpinQuest
  Mid October 2019

## Slide 34: DP Trigger & PropTube Work Plan

## Slide 35
DP ST-2 rack?
Move
DC-2 rack upstream
DP cable tray above ground
SMA-Lemo cable:
2x(48 + 48) + (46 + 12) + “12” = 262”
= 21.8’
For ST-1:
Additional a few ft to ST-1 rack

## Slide 36
DP/V1495 move to
East L2 trigger rack
Bring ST-1 CAMAC
& TDC to here
Keep SiPM PS
New DP cable tray above ground

## Slide 37
CAMAC, SiPM PS
move to East

## Slide 38
DP-1
DP-2
KMAG
RACK-1
Location?
RACK-2
ST0-1: 4x 80 ch
-CAMAC (10 x LeCroy 4413)
-VME/TDC(CPU+TS+4TDC)
-VME/TDC(CPU+TS+4TDC)
-CAMAC (10 x LeCroy 4413)
-NIM/BlueLogic trigger
-SiPM PS
ST-2: 4x 50ch
-CAMAC (8 x LeCroy 4413)
-VME/TDC (CPU+TS+4TDC)
-CAMAC (8 x LeCroy 4413)
-NIM
-SiPM PS
DP Trigger
-VME:
4xV1495 L1 trigger
Calibration
-NIM/BlueLogic
Trigger
DC-2
DC-2
RACK-3
L2/V1495
DP trig(OR)
DY trig(AND FPGA trig’s)
beam
(4 Qs)
DP Trigger New Layout-2
East
West