## Slide 1: Progress since last Presentation 11/05/2016
MoU discussion continues with ALICE/ITS
  LANL “Express of Interest” submitted in early October and reviewed by ALICE
  Associate Membership expected after ALICE Collaboration Board Meeting next week (11/11)
  Luciao/ALICE working on Cost & Schedule of sPHENIX “MoU”
  Walt and Ming visit ALICE next week
    MoU and procurements of R&D test stand etc.
Continue building collaboration
  More new members
A separate MIE idea being explored
  A small group meeting 10/21
  Visit MIT/Bates 10/27
  A near term plan developed

## Slide 2: Possible Additional Collaborations
Czech Group (PHENIX, FVTX )
  Expressed interest - M. Finger/Mike Finger
  possible engineering and student support
  A meeting w/ Ming and Walt scheduled next week at CERN, Nov. 10-15
China Central Normal Univ. (CCNU, ALICE/ITS 5th layer)
  Expressed interest and possible collaboration on sPHENIX MAPS tracker - Nu Xu
  Cesar visited CCNU ITS/MAPS labs
  Many good students already at ALICE/CERN
  Could help on assembly and testing etc.

## Slide 3: A Separate MIE Proposal for the sPHENIX MAPS Inner Tracker?
This idea of a separate MIE has been brought up and discussed at several meetings recently
sPHENIX collaboration proposed “cost reduced” baseline configurations, (I) & (II).
  Still waiting for decisions/inputs from ALD
  In both scenarios, we need MAPS!
MAPS is considered by BNL ALD to have the best chance to get additional fund for sPHENIX:
  With strong consortium of outside institutions (LANL+MIT+LBNL? + UT..), thus there is a strong push/desire from ALD/sPHENIX project office to get a separate MIE for MAPS

## Slide 4: Challenges of a new MIE
What do we know from DOE?
  From what ALD described, DOE (Jehanne and Tim) thought this was a good idea but it is too early to say more than that.
  Not very clear DOE will be ready to provide $$ for this, and also the timeline given the 2-year Federal Budget Cycle even if “mission need” approved --- earliest MIE fund FY20
The separate MAPS MIE timeline needs to be tied to the ALICE/ITS production and also the sPHENIX schedules
  ALICE/ITS production ends summer 2018
  The early funding opportunity from normal MIE ~10/2019, a special case must be made to meet the ALICE/ITS production schedule
Potential high impacts on the sPHENIX-ALICE “MoU”
  Resources, lab space and man power
  Schedules

## Slide 5: Project Task and Timeline
Det. Install.
@BNL
Readout R&D
Mech. design
@LANL/ALICE
Mech. Integr.
& Prototype
@BNL/LANL
Production
Key R&D
FY2017
FY2018
FY2019
FY2020
FY2021
FY2016
CD-1
11/1
CD-2/3
8/1
CD-0
11/1
Ready for
Beam
6/1
MoU w/ ALICE: 12/2016
To produce staves, frames and FEMs
Det. Assembly & Test
@BNL
MAPS Prod. & QA
@ALICE
Stave Prod.&Test @CERN;
FEM Prod. @US
+2%
+50%
From Sep. 2016
Tracker Review
FY20:
MIE Fund available?
We need $$
here to start!
Some intermediate
solutions needed to
fill the gap!

## Slide 6: Had a Small Group Meeting on 10/21/2016
Ed, Dave M, Gunther and Ming
1. High level sPHENIX-ALICE “Agreement”:
“The document that we intend to have both CERN and DOE sign agreeing to cooperate on MAPS
development for sPHENIX, will not be a Memorandum of Understanding, but rather an
agreement to collaborate, an agreement to provide resources, or something similar. “ from Ed.
2. ALD plans to work on sPHENIX-ALICE Agreement with DOE and sPHENIX management, willing to go
to CERN for negotiation etc.
3. >$2M MIE as an individual federal budget item, there could be some flexibilities, we try to work out MAPS plan first then deal with this later
4. Develop a pre-proposal (a draft by 12/15/2016 sPHENIX collaboration meeting),
-- identify the timeline of M&S fund and manpower needs to match ALCIE/ITS and
sPHENIX schedules
--- > starting from Cost & Schedule documents we already have
5. To get all interested parties involved in the pre-proposal writing
6. Gunther will try to arrange a meeting with MIT folks on 27th to discuss MAPS involvement

## Slide 7: sPHENIX/MAPS MIE Discussion (Cont.)
sPHENIX/MAPS discussion at MIT, 10/27/16, many attended
  Gunther, Bolek W., Yen-Jie L, Bob R., Richard M., Bolek W. ,
  Bates Engineers Jason Besuille, James Kelsey.
  Dave M., John H, Ed dialed in
  Cesar and Ming
Discussed MIT’s interest and responsibility
  Major tasks to lead
    Mechanical system integration
    Assembly and system test
  MIT Physics and Bates Engineering Group
    excellent match to the capabilities
  Resource and timeline
    Engineers and Techs
    Students and postdocs

## Slide 8: A Near Term Plan
Consider a separate MIE proposal for MAPS
  Feasibility, start communication with DOE
  Have a pre-proposal soon, first draft by Dec 15
    Identify tasks, resources and timeline
    First full doc by Jan 2017, to be ready for discussions with DOE
Invite all interested parties to join the pre-proposal writing
  A draft: ~15 pages
  Update Resource, Cost and Schedules
  More discussion at Dec. collaboration meeting

## Slide 9: Note: a Typical MIE Timeline
Submitted and reviewed in FY17, establish DOE “mission need”
Federal budget request by DOE in Feb 2018,
Fund available FY20 for construction
Early construction fund needed by mid 2018
  Produce MAPS chips and staves following ALICE/ITS production at CERN
  About $1M, external funding opportunities?