## Slide 1: MVTX Review Report and Plan Maria, Grazyna, Bob and Ming
Define a clear procedure with ALD how to proceed with MVTX proposal
  MVTX group should propose a plan to ALD how to proceed with project milestones, and get feedback from ALD and DOE.
  MVTX group should update project funding & timeline with ALD and DOE after Oct. visit
    Updated 4 physics money plots
    Updated cost, schedule and risk
MVTX consortium updates the proposal, cost, schedule and resources
  Science and simulations
  Project cost & schedule
  Institutions’ roles
  Bi-weekly project progress discussion  starting from today!

## Slide 2: Path Forward - draft
Implement recommendations
  Follow up findings and recommendations
    Work with ALD in 2~4 weeks to develop a plan for DOE presentation
  Bi-weekly MVTX consortium meetings till full proposal submission
Milestones
  Update key elements of the proposal for ALD’s DOE visit, ~10/15
    4 physics highlight “Money Plots”: B-hadron and b-jet R_AA and V_2
    Cost, schedule and risks
  Work with ALD to communicate with DOE about budget & timeline, 11-12/2017
  Workout a preliminary MOU with CERN, ~12/2017
  Full proposal ready for submission, ~end of 12/2017
    Goal: secure at least partial funding in late FY18/early FY19 to continue stave production at CERN after ALICE ITS/IB production ~8/2018.
MVTX workfest Dec. 5-7 to push for the final proposal
  sPHENIX collaboration meeting @ Santa Fe, Dec. 8-10, 2017

## Slide 3: Draft Proposed Plan to ALD Action items from the MVTX DR (I)
1. Solicit multiple theory predictions – December 2017
- HF-Jet GW, Jin, Xin, Grazyna et al
- Workshops, all
2. Refine the three (four!) key physics plots – October 2017
- HF-Jet PWG, simulation team
3. MoU with CERN for stave production – December 2017
- Maria, Ming, Bob and Grazyna
4. Refine stave cost estimate with CERN – DONE
5. QA plan for tests
- readout and cooling needs at LBNL and BNL
- Giacomo, Ming, Maria
6. Cost of building two inner layers – DONE
7. Scenarios for repair and replacement – October 2017
- Giacomo and all
8. Refine estimates for engineering design - September- 2017
– Bob, Walter, et al, MIT-LANL–BNL
9. Include Cost of Extension cables --- related to #13
- Dave, Walt, Ming et al – September 2017
More help needed for
all these tasks
Priority for ALD’s DOE visit
- Any suggestions ?

## Slide 4: Draft Proposed plan to ALD Action items from the MVTX DR (II)
10. Consider including UV sterilization of demineralized water in cooling plant, October 2017
– Bob, Jim, MIT
11. MoU with key production sites – December 2017
- all, LANL, CERN, UT-Austin, LBNL, MIT
12. Optimize design of INTT and MVTX simultaneously – Feb-March 2018
– this will need sometime, BNL engineer + LANL + MIT
13. Re-evaluate mechanical engineering costs once INTT and MVTX are final, March 2018
- Here one should make sure that the contingency is properly estimated to absorb cost variations
due to different designs.  realistic contingency on carbon structures – September 2017
- Too late? Maybe OK for MVTX DOE review in early 2018 after sPHENIX CD-1 review?
14. Develop a Project Management Plan – September 2017
–Preliminary draft in progress, Dave, Maria, Ming
- No need of detailed plan at this stage of the project, If PMP needed draft by October 2017
15. Clearly define scope, WBS dictionary, deliverables – October 2017
- a preliminary document available from last year’s review
- Not sure if all this is needed at this stage of the project, but can be done – Maria/All
16. Evaluation and documentation of risks – October 2017
– Giacomo, Dave, Grazyna

## Slide 5: Priority List for ALD’s Oct. DOE Visit
Refine 4 physics plots
  B-hadron and b-jet R_AA & V_2
Refine cost estimate
  Contingency of engineering cost to modify carbon structures etc
  Include extension cables etc.
  Cost and schedule risks if not funded in time

## Slide 6: backup

## Slide 7: Summary of MVTX BNL Directors Review Report
Overall very positive
  Scientific case is compelling and drastically enhances the physics capabilities of sPHENIX
  The conceptual design is technically sound and will likely meet or exceed the expectations for the program
  The costs are reasonably well understood
  The technically driven schedule is well defined and well organized
  The resources are reasonably well defined
  the risks on hardware and electronics are well understood and actively being studied
  Overall integration is well understood. The mechanical integration is not fully defined.
Good recommendations

## Slide 8: Conclusions & Final Recommendations
We would like to thank the MVTX team for their hard work in preparing for the Review and we thank the three external laboratories (LANL, LBNL and MIT) for sending their speakers to BNL during these tight financial times.
The MVTX project has made excellent progress since the last review and it is worth noting that the Science case for the detector has been especially well articulated with up to date simulations and performance studies.
We recommend that the MVTX project proceed with the process of submitting a full proposal to the DOE Office of Nuclear Science.