## Slide 1: Topics for Today
Overview
  Ming et al
LDRD status and plan
  Cesar, Xuan
Detector constr. & assembly
  Giacomo, Grazyna, Leo, Walt et al
Physics and detector simulations
  Jin, Xin et al
Readout and controls
  Mark, Leo, Jo, Giacomo et al
Lunch break
MVTX integration
  Walt/Bob/George/Christopher et al
Cost & schedule & risk
  Dave et al
Discussions
https://indico.bnl.gov/conferenceDisplay.py?confId=3244

## Slide 2: MVTX Overview
Ming Liu
Los Alamos
BNL Director’s Review Dry Run
06/19/2017

## Slide 3: MVTX: MAPS-based Vertex Detector for sPHENIX
A separate MIE as a sPHENIX upgrade project, with
Compelling Science and;
Realizable cost & schedule

## Slide 4: Outline
Science
Scope of MVTX proposal
  Readout
  Integration
  Cost & schedule
Organization & plan

## Slide 5: MVTX Science
Use open heavy quarks to study QGP
  Upgrade sPHENIX baseline detectors
- Detailed study of quark energy loss mechanisms in QGP
- Detailed study of QGP properties: T, density, viscosity, couplings etc.
arXiv: 1502.02730

## Slide 6: Key Observables
B-jet quenching & correlations
  Energy loss mechanisms
  QGP density
B-hadron “flow”
  Bulk viscosity
  Coupling

## Slide 7: sPHENIX Approach
ALICE ITS;
Inner Tracker System
sPHENIX Inner Tracking
“Adopt” ITS Inner Tracker
Key challenges:
- Readout
- Mechanics

## Slide 8: Monolithic-Active-Pixel-Sensors (MAPS) A State of the Art Tracker
Advantages of MAPS:
  Very fine pitch (28x28 μm)
  High efficiency (>99%) and low noise (<10-6)
  Fast readout, 2~4 μS
  Ultra-thin/low mass, 50μm (~0.3% X0)
  On-pixel digitization, low power dissipation
An ideal detector for QGP b-jet physics!
50 μm
28 μm
A 9-chip MAPS stave, ITS/IB
ALPIDE design
FPC
Chips
Cooling plate

## Slide 9: MVTX Pre-proposal Submitted!
Pre-proposal submitted to DOE, 2/2017
  Follow-up discussions with DOE and BNL managers
  Weekly proj. leaders meeting BNL/LANL/LBNL/MIT
Plan to update proposal to DOE, late 2017
  Expanded science “CD0” + Cost & Schedule “CD1”
  Assumed funding starts in FY18
A growing collaboration
  15+ institutions from US and abroad
“Adopt” ALICE ITS Upgrade Inner Barrel 3-layer MAPS detector
  Mini. risk, Max. Physics
Precision vertexing for b-jet/B-hadron tagging in HI with high efficiency and high purity
B-jet modification in QGP at low-medium pT to determine QGP properties, study mass-dependence on collisional vs radiative energy loss, flow etc.
A separate DOE MIE to build the full detector, WBS 1.12, ~$5M for construction
Early R&D by LANL LDRD, $5M, FY17-19, readout and mechanical integration

## Slide 10: Scope of the MVTX Project
MAPS staves & Electronics
  MAPS staves
    “MoU” to build 68 ITS inner Barrel Staves
    No modification
  Readout Electronics
    Frontend: ALICE/ITS, RU
    Backend: ATLAS FELIX
    Modify/reprogram RU & FELIX for sPHENIX
    R&D by LANL LDRD
  Production
    Extend ALICE/ITS MAPS stave production
      sPHENIX personnel help assembly and testing staves at CERN
    Reproduce additional ALICE RU & FELIX for sPHENIX
    Final assembly and test in US, LBNL/BNL
  Ancillary systems, “copy” ALICE
    Power distribution, cables, crates, racks etc.
    Slow control, safety and monitoring
Mechanics & Cooling
  Some changes to ALICE/ITS inner tracker mechanical structures
    End Wheels
    Cylindrical structure shells
    Detector half barrels
    Detector and Service half barrels
  Mechanical Integration
    Conceptual design by LANL LDRD
    Prototype by sPHENIX R&D
    Design integration frames
    Carbon frames etc.
    Installation tooling etc.
  Copy ALICE cooling plant design
    Minor modification to fit sPHENIX
    Smaller heat load than ALICE ITS
  Metrology and Survey
WBS 1.12: a new MIE fund the full MAPS Vertex Detector, ~$5M

## Slide 11: Project Tasks and Timeline
Det. Install.
@BNL
Readout R&D
Mech. design
@LANL/ALICE
Mech. Integr.
& Prototype
@MIT/LBNL
Production
Key R&D
FY2017
FY2018
FY2019
FY2020
FY2021
FY2016
CD-1
CD-2/3
8/1
CD-0
9/2016
Ready for
Beam
6/1
“MoU” w/ ALICE/ITS: 11/2016
- Produce MAPS chips and Stave Space frames for sPHENIX as part of ALICE production!
- Full staves and RU & CRU production cost & schedule  MVTX MIE
Detector Assembly
& Test @LBNL
MAPS Prod. & QA
@ALICE
Stave prod.&test @CERN;
C-Stru. Prod.
@LBNL
“RU” prod @CERN
“FELIX” Prod. @US
+2%
+50%
A schedule driven project!
ALICE ITS/IB
Prod. ends
sPHENIX
baseline

## Slide 12: Stave Production & Test @ CERN
Preparation for final stave production
  Successful ITS Stave production readiness review on Apr/27, 2017
  Optimization of final configuration is underway
Final stave production: July 2017 – June 2018
  One stave per day
  1st set of full staves complete in Jan. 2018
Chip test and HIC assembly machine
Probe-card
Chip
pre-position
Chuck (PPC)
Chips tray
HIC assembly table
Chip gripper
Cesar’s talk
FPC
Chips
Cooling plate

## Slide 13: R&D @LANL on MAPS Single Chip Readout
MOSAIC test bench in operation
  Single MAPS chip with high-speed readout
  Threshold scan
  Noise scan
  External trigger
  Test data readout performance
    1.2Gb/sec
    0.6Gb/sec
    0.4Gb/sec
Test firefly cable performance
  5m (ALICE default)
  7m, 10m
  Short extension cables, +20~30cm
MAPS chip
MOSAIC test bench
10m FireFly cable
Cesar’s talk

## Slide 14: MVTX Readout and Control System: Status
Power Board
Filtering Board
(Capacitors)
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Regulated Power
FELIX (or CRU)
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
Flex
Cold Plate
regulators
Power
5 m
Optical Links
9-sensor Stave
RUv1 prototype:
~July
FELIX v1.5:
~June
Available:
~August
Prototype stave:
~June
Mark’s talk

## Slide 15: Detector Assembly
Precision positioning and installation of staves on end-wheels
IB CYSS
Layer 0
Layer 1
Layer 2
Assembly of layers and carbon fiber structure into half-detector
Stave testing at each step
Metrology survey
Giacomo’s talk

## Slide 16: System Integration
Walt’s talk
MVTX+INTT

## Slide 17: INTT-MVTX Conflict
INTT 4-layers
Currently a clear conflict between the INTT and MVTX
  INTT only includes ladder, no connectors, cooling barbs, etc
R&D items: 1) Extend cables to move the conical structure further out in z-direction; 2) Design/optimize INTT layers to fit current MVTX geometry;
  FPC data cable is the HDI and can’t be easily extended, short “firefly” cables possible?
  Reduce angle of cone – redesign C-structures and connectors
|η|<0.95
|η|<1.09
|η|<1.28
|η|<1.12
INTT Acceptance
@ |z|=10

## Slide 18: Alice ITS Cabling & Support similar for sPHENIX

## Slide 19: Cost Basis – Major Items
MAPS and Staves: ~$xx
  ALICE ITS production
Readout: ~$xx
  ALICE ITS RDO
  ATLAS FELIX (ALICE CRU)
  FVTX/PHENIX experience
PS and slow control etc. ~$xx
  ALICE ITS design
  FVTX/PHENIX experience
Mechanical structures and cooling: $xx
  ALICE ITS inner tracker design
  FVTX/PHENIX, HFT/STAR experience
x48
Dave Lee’s talk

## Slide 20: Updated Cost and Schedule WBS: 6/5/2017

## Slide 21
Electronics
WBS 1.1
Readout Units
WBS 1.1.1
Back-end
WBS 1.1.2
Power systems
WBS 1.1.3
Mechanics & Detector Assembly
WBS 1.2
Staves
WBS 1.2.1
Carbon Structures
WBS 1.2.2
Barrel Assembly
WBS 1.2.3
Integration & Infrastructures
WBS 1.3
Cooling
WBS 1.3.1
Safety System
WBS 1.3.2
Global Support
WBS 1.3.3
MVTX
Project Manager: M. Liu (LANL)
Lead Coordinator: M. Chamizo-Llatas (BNL)
Deputy Project Managers: G.Odyenic (LBNL),R.Redwine(MIT)
ES&H liason:
QA liason :
Installation & Commissioning
WBS 1.3.4
sPHENIX Project Manager: Ed O’Brien
sPHENIX Office:
D. Morrison &
G. Roland

## Slide 22
A growing collaboration!
new sPHENIX/MVTX members:
Czech groups
CCNU – lab
USTC
Peking Univ.

## Slide 23: Status, Plans and Issues
Agreement with ALICE/CERN
  Obtained ALICE readout test stand, MAPS and electronics for early R&D
  Obtained design files, electronics and mechanics
  Training sPHENIX personnel
  ALICE produces MAPS and stave space frames for sPHENIX as part of the contingency
  Provide prototype and final staves
  Availability of CERN facilities after ITS/IB production
Potential schedule/funding gap of stave production
  ITS/IB production: ~7/2017 - 6/2018
  Risk Mitigation:
    Early training through LDRD effort, maintain activity at low level
    Possible mortgage for sPHENIX production from ALICE/CERN with MoU
    Seek external foreign funding
sPHENIX readout and mechanical integration R&D
  Possible delay due to unavailability of key elements like staves and readout for R&D
  MVTX/INTT integration
  Risk mitigation:
    Early joint R&D with ALICE as associate members
    Start with prototype RDO and FELIX/CRU
    Early system integration R&D and mechanical system mockup

## Slide 24: Summary
Exciting science
No high risk R&D
Strong support from ALICE
LANL LDRD very important
Ready for beam summer 2021
Project has ~6 months float

## Slide 25: Backup

## Slide 26: Exciting Science: Physics of the 3rd Pillar
sPHENIX is the next flagship heavy ion physics experiment in US
  Jets
  Upsilons
  B-jets
MVTX will complete b-jet physics
Cannot be done at the LHC for lack of low pT reach and huge backgrounds
sPHENIX Three Physics Pillars
B-Jets Physics
Jets
Upsilons

## Slide 27: MAPS-based Vertex Detector (MVTX) for sPHENIX
“Adopt” ALICE ITS Upgrade Inner Barrel 3-layer MAPS detector
  Mini. risk, Max. Physics
Precision vertexing for b-jet/B-hadron tagging in HI with high efficiency and high purity
B-jet modification in QGP at low-medium pT to determine QGP properties, study mass-dependence on collisional vs radiative energy loss, flow etc.
A separate DOE MIE to build the full detector, WBS 1.12, ~$5M for construction;
Early R&D by LANL LDRD, $5M, FY17-19, readout and mechanical integration;
R = 2.4; 3.2; 3.9cm;
L = 27.1cm; @Z=|10|cm, eta =(1.2,0.94,0.81)
|eta| < 2.0

## Slide 28
Sensor Series Production
Stave Develop
2016
2017
2018
2019
2020
Commissioning @ Surface
Installation
Commissioning in ALICE
Stave Mechanics
HIC Production
CMOS processing, thinning & dicing, test
HIC and Stave
Stave Production
Mechanical Support Structures
Design & Prototyping
Design & Prototyping
Production & Test
PRR
PRR
Global Assembly
EDR
PRR
Development
Production
2016
2017
2018
2019
2020
EDR
PRR
Readout Electronics
Commissioning
11 months
Dry Assembly Test
ALICE ITS Upgrade
Overall ITS Planning (Simplified Global View)
From L. Musa, 4/27/2017
Stave PRR Presentation

## Slide 29
  Pixel Sensor Chip - EDR (Oct’ 15)
  Stave - EDR (May’ 16)
  Detector Barrel Mechanics - EDR (Jul ’16)
  Cooling – EDR (Jul ’16)
  Pixel Sensor Chip - PRR (Nov ’16)
  Detector Barrel Mechanics - PRR (Dec ’16)
  Service Barrel Mechanics - EDR (Dec ‘16): done
  Cooling – PRR (Dec ’16): done
  Readout Electronics – EDR (Jan ‘17): done
  Stave - PRR (Apr ‘17)
  Service Barrel Mechanics – PRR (May ‘17)
  Readout Electronics – PRR (Dec ’17)
Project Review Milestones
ALICE ITS Upgrade
Stave Production Readiness Review:
4/27/2017
Stave production starts ~May/June;
1st set of IB by Jan 2018;
2nd set of IB by July 2018
LANL people + others/MVTX work on stave production from May 2017 at CERN, prototype available soon at LANL
Fully working staves for R&D available ~Jan 2018;
Near final readout RU/CRU: ~12/2017
From L. Musa, 4/27/2017

## Slide 30: Detector Assembly
Carbon supporting structures
Stave assembly & test
Giacomo’s talk
Side view of MVTX

## Slide 31: INTT-MVTX Conflict
INTT 4-layers
Extend cables to move the conical structure further out in z-direction
  FPC data cable is the HDI and can’t be easily extended
  Possibly add short “firefly” cables to hook up to patch panel, R&D needed
Reduce angle of cone – redesign

## Slide 32: MVTX/INTT Integration Extend MVTX Service Cables?
506.2 mm
16 mm
41.9 mm
16.15 mm
The 9 silicon chips are read out in parallel: each chip sends its data stream to the end of Stave by a dedicated differential pair, 100 mm wide. Two additional differential pairs distribute the clock and configuration signals.
CHIP 1
CHIP 9
……
CHIP 2

## Slide 33: FPC Extension for Connection to Electrical Services
FPC
DVDD
AGND
DGND
DVDD
DGND
DVDD
AVDD
AVDD
AVDD
AGND
AGND
DGND
The connection to the service cables is achieved by a double FPC extension which is soldered to the HIC
x-section at interconnection between FPC and extensions
signal lines (FPC)
analogue power
digital power
FPC
AVDD
AGND
AVDD
AGND
AGND
AVDD
Flex power extension
FPC
DVDD
DGND
DVDD
DVDD
DGND
DGND
Flex power extension
Antonello Di Mauro, Stave PRR 4/27/2017

## Slide 36: Cost Basis For Electronics
48(+40%)
sPHENIX
J. Phys. G: Nucl. Part. Phys. 41 (2014) 087002

## Slide 37
48 RDO boards
Readout Units Required for ITS & sPHENIX
48 inner staves
ITS IB:
Produce 120 staves in one year
120% contingency
sPHENIX: 48 +40% = 68

## Slide 38: ALICE Stave and Global Support Structure Cost and Schedule Basis
J. Phys. G: Nucl. Part. Phys. 41 (2014) 087002
ALICE Stave

## Slide 39: HICs Assembly Lab @CCNU space ~ 70m2 (1K clean room); 20m2 (10K clean room, 2.9m head room)
Chip and FPC gluing
Gluing FPC/MAPS
Chip mounting
Wire Bonding
Electrical circuit testing
Storage
Not Doing at present:
Stave assembly
No carbon structures
storage
Gluing & assembly
tables
Test bench
Chip mounting
Wire bonding
Machine shop: (Sun, Daming, Tech.)
CNC etc.
Simple mechanical structures

## Slide 40: CCNU Plan – Cont.
Experts and Designers of ALICE MAPS/ALPIDE on-chip electronics
  Analogy circuit – Dr. Chaosong Gao
  Digital circuit – Dr. Ping Yang
  They will help us!
PLAC – Pixel Lab At CCNU
  Also interested in mechanical system integration
  Plan to hire a full time engineer to work on sPHENIX integration effort
    Visit LANL 6-12 months, work on preliminary conceptual design for the MVTX/INTT/TPC
Physics simulation and analysis
  Many students
Gao
Yang
PLAC Ass. Director
Dr. Xiangming Sun

## Slide 41: MVTX R&D Status and Plan
Readout R&D
  5 single-chip MAPS tested at LANL
  Workfest @UT-Austin, 4/19-20
  RUv1 available in July, will be used for LDRD telescope
  BNL/ATLAS FELIX being evaluated as the default backend
    Computer arrived, fibers/cables ordered
    Obtain one FELIX in a few weeks
    “CRU” being prototyped with Altera evaluation boards, able to communicate with the RUv0 board @ UT-Austin;
  LANL MOSAIC test bench in operation!
Tracker integration task force
  MVTX + INTT + TPC mechanical system integration
  Identified the major tasks
Stave production @CERN
  ALICE Stave Production Readiness Review 4/27, prod. Starts in June/July
  LANL people do assembly and testing at CERN, May – Sept. 2017
  MVTX plan

## Slide 42: ALICE/ITS Readout R&D 5 RUv1 available for LANL R&D ~July 2017

## Slide 43: Electronics R&D – Cont. FELIX and MVTX Power Distribution Boards
FELIX: visited BNL Labs and had FELIX system demo
  V1.5 boards, all functionalities available- data, slow control and Timing/Trigger/Busy, w/ GBT
  Multi-channel GBT links and PCIe interface code developed, with examples of user modules
  V2.0, available ~end of 2017, sPHENIX application
  A 1.5v FELIX board produced and tested, ready for shipment to LANL; Optical cables etc. to be ordered soon for LANL test bench
Power distribution boards and PS
  LBNL PS distribution board available for R&D from CERN/LBNL ~ August. Order placed, 4wks + testing
  R&D power supply and control system ordered (CAEN), available ~August
FELIX: tested @BNL
To be shipped to LANL

## Slide 44: Test under internal trigger (40MHz)
Readout speed 1.2 Gb/s and 50 injections.
Scan the noise per pixel and the average value is 7.47±1.80 (e).
From Xuan

## Slide 45: Test under internal trigger (40MHz)
Readout speed 600 Mb/s and 50 injections.
Scan the noise per pixel and the average value is 7.53±1.76 (e).

## Slide 46: External Trigger and Source
Single chip readout
Use a pulse generator as the external trigger
Use the Strontium-90 to produce beta rays.
  Vary the distance between the source and the silicon chip
Sr-90
1kHZ trigger
Xuan et al

## Slide 47: A Single-chip MAPS Telescope
Check the readout occupancy and efficiency under different internal trigger clock (10-40MHz), readout speed (400-1200Mb/s) and threshold (set up by the analog signal or the configuration file?).
Set cosmic ray triggers with scintillator bars or pads to read out single MVTX chip with the external coincidence cosmic ray trigger.
Design of single chip based telescope in progress
μ-
μ-
Efficiency tester
Simple tracker