## Slide 1: MVTX Update: 5/28/2018
Progress on project planning
  BNL Directors Review: 7/10-11
    Speakers TBD soon
  Dry run: 6/19
  Cost, Schedule and Resources
  WBS and org chart being updated
  Physics/Detector simulations w/ HF-Jet TG
    6/11-12 tracking+HF-Jet workfest @BNL
  Weekly meeting for project planning etc
    BNL/MIT/LBNL/LANL
CCNU visit
  Contributions to MVTX project
  Stave production
  Global mechanical integration, MVTX/INTT/TPC
  Simulations and physics analysis
R&D progress at LANL
Ming visited CCNU, May 2017
  Discussed joining sPHENIX/MVTX and CCNU’s possible roles
Maria will visit CERN, June 2017
  discuss using CERN facility for MVTX production etc.

## Slide 2: Feasibility to use CCNU Labs for MVTX HICs/Staves production 5/24/2017
CCNU ALICE/ITS HICs assembly lab
  Chip assembly machine, installed and tested
    2 technicians trained @Italy and also locally
  Wire bonding machine, will arrive soon, a few weeks, arriveds in June
    2 technicians trained @Italy
    1 week local training planned
  One old bonding machine in opeation
Wire bonding
machine location
Dr. Yaping Wang,
Assembly lab director

## Slide 3: Technical Resources
Technical resources
  2 mechanical technicians on MAPS chip mounting on FPCB
    FPC gluing
    Mount chips on FPCB
    Wire bonding
    Trained at CERN/Italy
  1 electronics technician on testing HICs
    Test and fix HICs
    Trained at CERN/Italy
  One Ph.D (An, Mang Mang) trained in all aspects in R&D on HICs assembly and test @CERN
PLAC – Pixel Lab At CCNU
  Electronics readout design engineers,
    a team led by Wang, Dong (from ALICE, readout and trigger)
  Chip design engineers
    A team led by Yang, Ping (participated in ALPIDE design @CERN, 2012-2015)
  Staff and Students from CCNU
      Staff: 15
      Graduate students: 10+ Ph.D and 25+ Master students
  Institute of Particle Physics
    Staff: 30+
    Postdocs and Students: 10+ postdocs, ~80 students

## Slide 4: HICs Assembly Lab: space ~ 70m2 (1K clean room); 20m2 (10K clean room, 2.9m head room)
Chip and FPC gluing
Gluing FPC/MAPS
Chip mounting
Wire Bonding
Electrical circuit testing
Storage
Not Doing:
Stave assembly
No carbon structures
storage
Gluing & assembly
tables
Test bench
Chip mounting
Wire bonding
Machine shop: (Sun, Daming, Tech.)
CNC etc.
Simple mechanical structures

## Slide 5: Test Bench
One MOSAIC
4 single chips
What LANL has now

## Slide 6: CCNU Plan
To produce 500 ALICE/ITS mid-layer HICs
  ~2 HICs per day -> 250 days, 10+ months
  starting from June 27, 20117 –> June 2018
  No immediate use of the lab after June 2018
The lab can be used for MVTX HICs production
  3 months replace jigs, training
  Starting ~Sep. 2018, ~2 HICs per day, -> 35days -> 2 months (2~3 months)
  Many students available for testing
Stave assembly sites: 68 staves
  Stave space frame fabricated at CERN ( by 2017)
  Assemble at US/LBNL? (replace jigs, copy from CERN ITS/IB)
  China/CCNU? -> replace jigs (copy from CERN ITS/IB)
  @CERN 2 staves/week, from MAPS/Spaceframe/stave
CCNU Budget ALICE: $7.5M RMB
Pay MAPS chips
Pay toolings, jigs
Pay assembly machine
Technician salary
Traveling, student labor
CCNU budget sPHENIX: US$100K?
toolings, jigs, training
M&S for operation, gas etc.
Technician’s salary
Traveling, student labor
Shipping MAPS/HICs/staves

## Slide 7: CCNU Plan – Cont.
Experts and Designers of ALICE MAPS/ALPIDE on-chip electronics
  Analogy circuit – Dr. Chaosong Gao
  Digital circuit – Dr. Ping Yang
  They will help us!
PLAC – Pixel Lab At CCNU
  Also interested in mechanical system integration
  Plan to hire a full time engineer to work on sPHENIX integration effort
    Visit LANL 6-12 months, work on preliminary conceptual design for the MVTX/INTT/TPC
Physics simulation and analysis
  Many students
Gao
Yang
PLAC Ass. Director
Dr. Xiangming Sun

## Slide 8: PLAC Members (Pixel Lab At CCNU)
Faculty: ~15
Ph.D students: ~10
Master students: ~25

## Slide 9: Stave production plans
Plan-A
  CERN production:
    Assembly and test
  Time: starting 08/2018, 6-9 months
Plan-B
  HICs production @CCNU, Sep. 2018, 2-3 months
  Stave space frame production @CERN ITS/IB, by 2017
  Stave assembly: US/LBNL? Or China/CCNU, 4-6 months
DOE Budget: FY18
Impact on sPHENIX start date?
CCNU option  plan A?

## Slide 10: R&D @LANL on MAPS Single Chip Readout
MOSAIC test bench in operation
  Single MAPS chip with high-speed readout
  Threshold scan
  Noise scane
  Test data readout speed
    1.2Gb/sec
    0.6Gb/sec
    0.4Gb/sec
Test firefly cables
  5m (ALICE default)
  7m, 10m
  Short extension cables, +20~30cm
MAPS chip
MOSAIC test bench
10m FireFly cable
Sho, Elena, Xuan et al

## Slide 11: Test under internal trigger (40MHz)
Readout speed 1.2 Gb/s and 50 injections.
Scan the threshold per pixel and the average value is 385.12±44.17 (e).
From Xuan

## Slide 12: Test under internal trigger (40MHz)
Readout speed 1.2 Gb/s and 50 injections.
Scan the noise per pixel and the average value is 7.47±1.80 (e).
From Xuan

## Slide 13: Test under internal trigger (40MHz)
Readout speed 600 Mb/s and 50 injections.
Scan the threshold per pixel and the average value is 394.33±41.79 (e).
From Xuan

## Slide 14: Test under internal trigger (40MHz)
Readout speed 600 Mb/s and 50 injections.
Scan the noise per pixel and the average value is 7.53±1.76 (e).

## Slide 15: MVTX single Chip Lab test To-Do List
Check the readout occupancy and efficiency under different internal trigger clock (10-40MHz), readout speed (400-1200Mb/s) and threshold (set up by the analog signal or the configuration file?).
Check the electric trigger logic setup etc, set up the external trigger with a pulse generator.
Set cosmic ray triggers with scintillator bars or pads to read out single MVTX chip with the external coincidence cosmic ray trigger.
Design of single chip based telescope in progress
μ-
μ-
Efficiency tester
Simple tracker