## Slide 1
Meeting rooms:
  Main room: Zuni South
  2nd room: Chaco West for afternoon
Breakfast: 8:00-9:00AM
Group dinner tonight at 6PM (Cesar)
  Pink Adobe
Local contact/help:
  505-412-7396 (Ming)
  631-384-4381 (Cesar)
Welcome to Santa Fe
Photo by
Haiwang Yu

## Slide 2: MVTX Status and Plan
MVTX & HF-Jet Workfest, Santa Fe
12/5-7, 2017
Ming, Maria, Bob, Grazyna, Jin and Xin

## Slide 3: Outline
MVTX update since July Director’s Review
  Physics and Simulations
  Readout and Controls
  Mechanical System
  Budget and Schedule
Plan for the rest of the week

## Slide 4: New sPHENIX baseline and MVTX Plan
New sPHENIX baseline schedule
  CD-1 Review: 5/2018
  sPHENIX installation
    4/2021 – 7/2022
  sPHENIX ready for beam: 9/2022
  First collision: 1/2023
New/reduced sPHENIX baseline detectors
  EMCal: |eta| < 0.85 (1.1)
  OHCal: |eta| < 1? (1.1)
  IHCal: not available (1.1)
MVTX plan – align with the new sPHENIX schedule
  Stave production
    Following ALICE production: ~8/2018
  Readout units production
    Be part of ALICE RU production:
      FPGA & GTB chipset
  Ready for installation: later 2021
    INTT ready for installation 4/2021
  MVTX ready for beam
    sPHENIX day-1
Ed’s talk

## Slide 5: Performance Update
Fully implemented MVTX models used in performance projection
Large jets production in full detectors, including detailed MVTX detector + full calorimetry
  250k MB jets in p+p collisions
  100k MB jet embedded into central Au+Au collisions
Xin’s talk

## Slide 6: Updated p+p and Au+Au b-jet Projections
b-jet tagging projection re-evaluated with full tracking + calorimetry simulation
  Tagging work point has been stable (60% Purity 40% eff for pp)
  Central Au+Au Tagging work point has been stable (40% Purity 40% eff)
Performance has been stable using truth jet finding or calorimetry reconstructed jet finding
sPHENIX b-jet work point

## Slide 7: Theoretical Inputs – in Progress
LANL model
Duke model
TAMU
AMPT
PHSD
Ads/CFT
JetScape
….
New calculations from PHSD

## Slide 8: MVTX Readout and Controls
Power Board/ALICE
Filtering Capacitors
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Front End Electronics
Readout Unit/ALICE
Regulated Power
Back End Electronics
FELIX/ATLAS
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
5-10 m
GBT Optical Links
9-sensor Stave
sPHENIX GL-1 & GTM
DCS
CAN bus
Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
RUv1.0: 10/2017
FELIXv1.5:
6/2017
Stave: 06/2017
PS: 08/2017
CAEN PS: 08/2017
Sho’s talk

## Slide 9: Excellent Progress in Detector R&D
ALPIDE Evaluation and optimization
  MOSAIC + Single Chip/Stave
  Laser system
Power unit tested
  PU + MOSAIC
  PU + RU
Full readout chain demonstrated
  ALPIDE + RUv1.0 + FELIX v1.5 + RCDAQ
  Full stave + RUv1.x + FELIX v2.0 + RCDAQ
Telescope under development
  Mechanical frame
  GEANT simulation
  Alignment & tracking
  Cooling

## Slide 10: LDRD – MVTX/sPHENIX Key Tasks/Milestones
RU/KC705)/FELIX1.5 Integration
40MHz, 7/17-12/17
RUv1.x/FELIX2.0, 10MHz,
11/17 – 6/18
MVTX Design Review 7/2018
System test, cosmic & source
6/18 - 1/19
LDRD
MVTX: 2018 – 2023
Stave Production, procure FPGA, GBT etc.
8/18-4/19
7/17
10/17
10/18
10/19
Electronics Production
1/19-8/19
Test Beam, tracking performance
analysis, NIM paper etc.
1/19 – 9/19
Today
BNL Director Review
7/10-11, 2017

## Slide 11: Mechanical System & Integration
MVTX Design
  Extended CYSS
MVTX+INTT+TPC
END WHEELS
PATCH PANEL
ESTIMATED TOTAL MASS HALF DETECTOR 1,100.0 grams
CONICAL SECTION
Walt’s talk

## Slide 12
MVTX + INTT Integration

## Slide 13: sPHENIX cross-section view, including envelope for services; TPC and INTT
TPC services (one end)
INTT services, (one –end)

## Slide 14: Budget and Schedule – in Progress
Total budget: 6.5M
  Production
  Assembly
  Integration
Dave’s talk
Major Items | Cost ($M) | Schedule
Staves (WBS 1.5.3.1) | 1.4 | 8/2018-5/2019
Readout & Controls (WBS 1.5.2) | 1.3 | 1/2019-6/2019
Mechanics & Detector Assembly (WBS 1.5.3) | 1.8 | 2019-2022, TBD
Integration (WBS 1.5.4) | 1.0 | 2021-2022, TBD
Project Management | 1.0 | 8/2018-1/2023

## Slide 15: Plan for the Workfest
Writing, Writing and Writing …. To update the full proposal document
Chris has assigned 9 powerful interactive machine for this workfest (40 Core/80 GB memory), no time limit.
Valid for use until Dec 12.
These interactive RCF nodes are: rcas2901-2904 and rcas2906-2910

## Slide 16: Agenda
Day-1: (12/5, Tue.)
  Review current draft – by WG TLs
    Identify and discuss areas for improvements
  Working sessions in the afternoon: working groups
Day-2:
  Discuss updates from day-1 – by WG TLs
  Working sessions in the afternoon: working groups
Day-3:
  Discuss updates from day-2
  Finalize a preliminary full proposal
4 working groups with
team leaders:
Physics & simulations
Electronics & sensors
Mechanical system
Cost, Schedule & Risks
Two rooms available
Zuni South
Chaco West
Workfest Indico Page: https://indico.bnl.gov/conferenceModification.py?confId=3557

## Slide 17: 4 Working Groups To complete the draft by the end of this workshop
Physics and Simulations
  HF-Jet TG, Jin, Xin, Tony, Sanghoon, Haiwang, Darren, Xiaolong, SukHyun, Cesar, Ming et al
Staves, electronics & power system
    Readout - Mark, Sho, AlexT, Jo, Kun, Ming, Giacomo, Kai/BNL/ATLAS, Jin/BNL, Martin, JohnH …
    Staves/Sensors- Cesar, Xuan, Maria, Ming …
Mechanical system & Integration
  Integration - Bob, Grazyna, Walt, Jim K., Giacomo, Chris …
  Carbon structures – Grazyna
Project Cost, Schedule, Risks
  Dave, Ming, Maria, Bob, Grazyna, Giacomo, Jo, …
* Working group team leaders

## Slide 18: Backup

## Slide 19: Day 1: 12/5
8:00-9:00 Breakfast
9:00-9:10: Workshop Goals (Ming, Maria) Chair: Cesar
9:10 – 9:30: sPHENIX plan (Ed, Maria)
9:30 – 9:50 MVTX Overview (Maria, Ming)
9:50-10:20 Status Report 30’: Science and Simulations (Jin/Xin)
10:20-10:40 coffee break 20’
10:40 – 11:10: Status Report 30’: Readout (Mark, Sho) Chair: Jin
11:10-11:30: Status Report 30’: Mechanical system (Bob, Walt, Grazyna)
11:30-12:00: Status Report 30’: Cost and Schedule (Dave, Maria)
Lunch break: 12:00-1:30
1:30-2:00 INTT/MVTX integration – Mickey Chiu Chair: Maria
2:00-2:30 sPHENIX Readout integration discussions – (Ed Desmond, Martin, John)
2:30 – 5:30 Working sessions, 4 groups
3:30-4:00 Coffee break
group dinner @6:00PM in Santa Fe

## Slide 20: Day-2
8:00-9:00 Breakfast
9:00- 9:20: Progress report and discussion 20’: Physics and Simulations Chair - Bob
9:20- 9:40: Progress report and discussion 20’: Readout
9:40- 10:00: Progress report and discussion20’: Mechanical system
10:00- 10:20: Progress report and discussion20’: Cost and Schedules
10:20-11:00: coffee break
11:00- 11:30: Physics presentation by Haitao Li/Ivan Vitev Chair - Xin
  title:
  Inverting the mass hierarchy of jet quenching with b-jet substructure
  abstract:
  The two-prong substructure of the leading subjets inside a reconstructed jet opens new windows on precision constraints on the in-medium modification of parton showers. We present the first resumed calculation of the groomed soft dropped subjet momentum sharing distribution in heavy ion collisions, and demonstrate that both the STAR data at RHIC and the CMS results can be understood in the unified framework of soft-collinear effective theory with Glauber gluon interactions. Recent advances in understanding mass effects on the QCD splitting functions enables us to apply this method for the first time to heavy flavor tagged jets. We find that in the kinematic region that will be accessed by sPHENIX in the future there is a unique reversal of the mass hierarchy of jet quenching effects. Namely, the momentum sharing distribution of b-tagged jets is more strongly modified in comparison to the one for light jets.
Lunch break: 12:00-1:30
1:30 – 5:30 Working sessions, 4 groups
3:30-4:00 Coffee break

## Slide 21: Day-3 (half-day?)
8:00-9:00 Breakfast
9:00- 9:20: Progress report and discussion 20’: Physics and Simulations Chair - Grazyna
9:20- 9:40: Progress report and discussion 20’: Readout
9:40- 10:00: Progress report and discussion 20’: Mechanical system
10:00- 10:20: Progress report and discussion 20’: Cost and Schedules
10:20-11:00: coffee break
11:00 – 12:00: sPHENIX MVTX plan general discussions, full proposal submission etc – all Chair - Ming
  full proposal submission to DOE, 1/15/2018(Monday)?
Lunch break: 12:00-1:30
1:30 – 5:00 Working sessions, 4 groups
3:30-4:00 Coffee break

## Slide 22: b-jet v2 projection
From the MVTX Director’s review, we were also recommended to make projection for b-jet v2
In mid-central events, probing path-length dependent energy loss for b-quark
b-jets
Inclusive jet and photon arXiv:1501.06197 [nucl-ex]

## Slide 23: Performance study update since July review
Fully implemented MVTX models used in performance projection
Large jets production in full detectors, including detailed MVTX detector + full calorimetry
  250k MB jets in p+p collisions
    Macros modifications: https://github.com/sPHENIX-Collaboration/macros/compare/master...blackcathj:HF-production-bjet-pp200?expand=1
    Final sample available: /sphenix/data/data02/HF-production-bjet-pp200/pythia8/
  100k MB jet embedded into central Au+Au collisions
    Production file location: /sphenix/data/data02/HF-production-bjet-AuAu200/pythia8
    Example analysis macro is on this branch: https://github.com/blackcathj/macros/tree/HF-production-bjet-AuAu200-readback

## Slide 24: Updated p+p and Au+Au b-jet ProjectionS
b-jet tagging projection reevaluated with full tracking + calorimetry simulation
  Tagging work point has been stable (60% Purity 40% eff)
Performance has been stable using truth jet finding or calorimetry reconstructed jet finding
Secondary vertex method by Sanghoon Lim
Track counting method by Haiwang Yu
sPHENIX b-jet work point

## Slide 25: Updated central Au+Au b-jet tagging
Track counting tagging: Haiwang reevaluated with full tracking + calorimetry simulation of p+p jets embedded in central Au+Au
  Central Au+Au Tagging work point has been stable (40% Purity 40% eff)
Toolsets prepared to update the secondary vertex tagging too
  https://github.com/sPHENIX-Collaboration/coresoftware/pull/386
sPHENIX b-jet work point
Using calorimetry reco jet finding, by Haiwang Yu
Using truth jet finding, by Haiwang Yu

## Slide 26: MVTX Readout Electronics
Power Board
Filtering Capacitors
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Front End Electronics
Regulated Power
Back End Electronics
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
5-10 m
GBT Optical Links
9-sensor Stave
sPHENIX GL-1 & GTM
DCS
CAN bus
Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
RUv1.0: 10/2017
FELIXv1.5:
6/2017
Stave: 06/2017
PS: 08/2017
CAEN PS: 08/2017

## Slide 27: Extended inner tracker with current outer composite shell

## Slide 28: Section view of sPHENIX inner detector assembly the ALICE service barrel has been modified – shortened

## Slide 29
DETECTOR SECTION
SERVICES, SUPPORT SECTION
ALICE HALF-BARREL ASSY

## Slide 30: First INTT Drawing from Don Cacace