## Slide 1: MVTX Update 4/28/2017
UT-Austin Meeting
  Thank you Jo and Christina!
Meetings @BNL
  Maria, Ed, Bob, Grazyna and Ming
  In-depth MVTX project discussions
FELIX discussions with BNL engineer
  Preferred option for TPC
ALICE Stave PRR 4/27/2017
  Good progress
  Updated schedules

## Slide 2: MVTX Readout Workfest @UT-Austin https://indico.bnl.gov/conferenceDisplay.py?confId=3047
Very productive discussions on the technical sides:
  sPHENIX readout – Martin
  TPC readout – Jin and Takao
  ALICE ITS readout system – Jo
  LV/HV and Slow controls - Giacomo
  MVTX readout options – Mark
Lab demo of RUv0 and “CRU” R&D
  RU v0
  “CRU” prototype with an Altera eval board
A brief summary
  Possible MVTX readout path
    RDO Unit, some modification
    CRU or FELIX (TPC), both could work OK, significant R&D needed
  Joint R&D on RU and CRU, maybe also FELIX integration
  UT-Austin’s interest in RU and CRU production & test!

## Slide 3: A nice/low cost Machine Shop @UT-Austin Fast turn around R&D mechanical structures

## Slide 4
Wish you were here too ;-)

## Slide 5: Meetings @BNL
A full day in-depth discussions of project plan, cost and schedule
  Follow up discussions through out the week on project cost and schedule
  BNL, LANL, MIT and LBNL
  CERN recognized experiment and “MOU” etc
BNL Directors Review: July 10-11 (Tentative)
  A dry run in June, date TBD
Action items
  Identified areas for improvement, C&S,
  Org chat being updated, institution tasks etc
  Review dates etc.

## Slide 6: Electronics R&D FELIX and MVTX Power Distribution Boards
Visited BNL Labs and had FELIX system demo
  V1.5 boards, all functionalities available- data, slow control and Timing/Trigger/Busy, w/ GBT
  Multi-channel GBT links and PCIe interface code developed, with examples of user modules
  V2.0, available end of 2017, sPHENIX application
  A 1.5v FELIX board produced and tested, ready for shipment to LANL; Optical cables etc. to be ordered soon for LANL test bench
Power distribution boards
  LBNL PS distribution board availablefor R&D from CERN/LBNL ~ June
  R&D power supply system to be ordered
FELIX: tested

## Slide 7
  Pixel Sensor Chip - EDR (Oct’ 15)
  Stave - EDR (May’ 16)
  Detector Barrel Mechanics - EDR (Jul ’16)
  Cooling – EDR (Jul ’16)
  Pixel Sensor Chip - PRR (Nov ’16)
  Detector Barrel Mechanics - PRR (Dec ’16)
  Service Barrel Mechanics - EDR (Dec ‘16): done
  Cooling – PRR (Dec ’16): done
  Readout Electronics – EDR (Jan ‘17): done
  Stave - PRR (Apr ‘17)
  Service Barrel Mechanics – PRR (May ‘17)
  Readout Electronics – PRR (Dec ’17)
Project Review Milestones
ALICE ITS Upgrade
Stave Production Readiness Review:
4/27/2017
Stave production starts ~May/June;
1st set of IB by Jan 2018;
2nd set of IB by July 2018
LANL people + others/MVTX work on stave production from May 2017 at CERN
Fully working staves for R&D available ~Jan 2018;
Near final readout RU/CRU: ~12/2017
From L. Musa, 4/27/2017
Stave PRR Presentation

## Slide 8
Sensor Series Production
Stave Develop
2016
2017
2018
2019
2020
Commissioning @ Surface
Installation
Commissioning in ALICE
Stave Mechanics
HIC Production
CMOS processing, thinning & dicing, test
HIC and Stave
Stave Production
Mechanical Support Structures
Design & Prototyping
Design & Prototyping
Production & Test
PRR
PRR
Global Assembly
EDR
PRR
Development
Production
2016
2017
2018
2019
2020
EDR
PRR
Readout Electronics
Commissioning
11 months
Dry Assembly Test
ALICE ITS Upgrade
Overall ITS Planning (Simplified Global View)
From L. Musa, 4/27/2017
Stave PRR Presentation

## Slide 9
Project R&D and Construction Milestones
ALICE ITS Upgrade
Nov-16 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
ALPIDE EDR (10/15) |  |  |  |  |  | 
ALPIDE PRR (25/11/16) |  |  |  |  |  | 
ALPIDE product. and test (end 12/17) |  |  |  |  |  | 
IB stave EDR (3-4/5/16) |  |  |  |  |  | 
IB stave PRR (27/4/17) |  |  |  |  |  | 
IB FPC production end (12/17) |  |  |  |  |  | 
IB space frame & cold plate prod. end (9/17) |  |  |  |  |  | 
IB-1 stave production end (1/18) |  |  |  |  |  | 
IB-1 assembly end (3/18) |  |  |  |  |  | 
OB stave EDR (3-4/5/16) |  |  |  |  |  | 
OB stave PRR (27/4/17) |  |  |  |  |  | 
OB FPC production end (6/18) |  |  |  |  |  | 
OB space frame & cold plate prod. end (1/18) |  |  |  |  |  | 
OB HIC production end (6/18) |  |  |  |  |  | 
OB stave production end (8/18) |  |  |  |  |  | 
OB stave assembly end (10/18) |  |  |  |  |  | 
From L. Musa, 4/27/2017
Stave PRR Presentation

## Slide 10
Project R&D and Construction Milestones
ALICE ITS Upgrade
Mar-17 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
RO electronics EDR (27/1/17) |  |  |  |  |  | 
RO electronics PRR (12/17) |  |  |  |  |  | 
RO electronics prod. end (12/18) |  |  |  |  |  | 
Detector barrel EDR (20/7/16) |  |  |  |  |  | 
Detector barrel PRR (14/12/16) |  |  |  |  |  | 
Detector barrel prod. end (7/17) |  |  |  |  |  | 
Service barrel/cage EDR (14/12/16) |  |  |  |  |  | 
Service barrel/cage PRR (5/5/17) |  |  |  |  |  | 
Service barrel/cage prod. end (9/17) |  |  |  |  |  | 
Cooling plant EDR (21/7/16) |  |  |  |  |  | 
Cooling plant PRR (16/12/16) |  |  |  |  |  | 
Cooling plant ready (9/18) |  |  |  |  |  | 
Commissioning surface end (5/19) |  |  |  |  |  | 
Installation during LS2 (4/20) |  |  |  |  |  | 
11 months contingency
From L. Musa, 4/27/2017
Stave PRR Presentation

## Slide 11: To do list
Prepare for BNL Directors reviews
  Update links between Org. Chart and Cost & schedule WBS
  Update cost and schedule, missing items etc.
  Physics and detector simulations, Money plots
Detector R&D
  Readout
  Mechanical integration
  Stave production at CERN
  Test bench at LANL
  Joint LANL/UT-Austin on RU, CRU/FELIX work

## Slide 12: Service Cables
506.2 mm
16 mm
41.9 mm
16.15 mm
The 9 silicon chips are read out in parallel: each chip sends its data stream to the end of Stave by a dedicated differential pair, 100 mm wide. Two additional differential pairs distribute the clock and configuration signals.
CHIP 1
CHIP 9
……
CHIP 2

## Slide 13: FPC Extension for Connection to Electrical Services
FPC
DVDD
AGND
DGND
DVDD
DGND
DVDD
AVDD
AVDD
AVDD
AGND
AGND
DGND
The connection to the service cables is achieved by a double FPC extension which is soldered to the HIC
x-section at interconnection between FPC and extensions
signal lines (FPC)
analogue power
digital power
FPC
AVDD
AGND
AVDD
AGND
AGND
AVDD
Flex power extension
FPC
DVDD
DGND
DVDD
DVDD
DGND
DGND
Flex power extension
Antonello Di Mauro, Stave PRR 4/27/2017