## Slide 1: MVTX: WBS 1.12
A separate MIE as an upgrade project

## Slide 2: MVTX Update
Meetings with Maria Chamizo Llatas of BNL Project Office
  Weekly LANL/LBNL/MIT/BNL phone meetings to discuss path toward reviews, project plan etc
  A full day meeting 4/25 @BNL, LANL/LBNL/MIT
  Bi-weekly MVTX detector group meetings discussed
  MVTX BNL Directors review: Science + C&S
    ~mid July, a dry run in late June
    A draft charge of review, ~next week?
Cost and Schedule project file updated 4/7/2017
  LANL & LBNL, detailed labor profile
  MIT, discussed last week, some thoughts on mechanical integration issues
    MVTX as a standalone, NO modification of the service end etc;
    if other subsystems introduced, they work out integration issues
    Potential increase in cost & schedule if MVTX/INTT/TPC, tracking integration task force report
  Other institutions, in progress
  DOE wants to keep the fund below $5M, possibly from some redirected $$
  Project webpage: BOE, WBS, project file
  https://p25ext.lanl.gov/maps/mvtx/mvtx.html

## Slide 3: MVTX R&D Status
Readout R&D
  Workfest @UT-Austin, 4/19-20
  LANL MOSAIC test bench setup in progress
  RUv1 available in May, will be used for LDRD telescope
  CRU being prototyped with Altera evaluation boards, able to communicate with the board;
  BNL/ATLAS FELIX being evaluated as an alternative
    Computer arrived, fibers/cables ordered
    Obtain one FELIX in a few weeks
Stave production for LDRD telescope
  ALICE Stave Production Readiness Review 4/27, prod. Starts in May
  LANL people do assembly and test at CERN, May – Sept. 2017
Project C&S – work in progress
  Detailed commitment from each institutions etc
  More work after BNL meeting w/ Project Office, 4/25
Tracker integration task force, led by Mickey
  MVTX + INTT + TPC mechanical integration issues
  Identify the major tasks, report due by the end of April
  Resources will be workout later

## Slide 4: Prepare for the BNL Director’s Review Physics/Detector Simulations
Produce preliminary by early June, prepare for a dry run in mid/late June
  B hadron physics
  B-jet physics
  Detector performance plots
To be ready for BNL Directors Review in July
  Money plots for the proposal