## Slide 1: MVTX Update
Ming Liu
12/21/2019

## Slide 2: MVTX Project Update: 12/21/2018
RU and Stave production at CERN
  UTK paperwork is progress, funding (likely) available in January
  A Pledge letter from Ed to ALICE/CERN last week
    Now RU is part of ALICE production!
    Stave production, ~January 2019
Cost & Schedule being updated, 12/17/2018
  Try to keep the total cost below $5M cap, $4.14M ($5.38m w/ 30% Cont.)
  Near term TODOs
    Revisit carbon structure cost: M&S/FTE = $368K/$924K
      End wheel: $72K/$73K
      CYSS: $103K/$333K
      Service barrel: $113K/$266K
    Split mechanical engineering design work: LANL, MIT, LBNL
Mechanical system integration
  Meetings at CERN and LBNL being planned
  Final Technical Design Review (FDR), ~Feb 2020 in P6
Over by ~400K

## Slide 3
Total = $4.14M
$5.38M, w/ 30% contin.

## Slide 4
Carbon: $370+$920 = $1.29M

## Slide 7: Mechanical design review and discussion @CERN
Draft agenda: https://docs.google.com/document/d/1Liu2-oHSLKGhlhd7nCG99XuPl-BLQ2uoyIW5Ex3tw5s/edit
Staff/engineers from LANL, MIT and LBNL will
meet at CERN at the end of January 2019
1/27-2/1, 2019
Final Design Review: ~Jan-Feb. 2020?
Then to proceed with production of carbon
and also non-composite structures
End Wheels
CYSS
Service barrel
Assembly jigs

## Slide 8: HF/MVTX Workshop @LBNL Dates TBD soon (Feb 27 – Mar 1?)
One day physics workshop
One day simulation workshop
One day mechanical design & fab workshop
  LANL, MIT, LBNL
  Reevaluate mechanical design and cost estimate
    To reduce carbon cost
    Mechanical integration, with 2-layer INTT
  Invite INTT group also?

## Slide 9: MVTX Service: Racks & Cables
Mickey, Walt
@FSU meeting

## Slide 10
Ross, Sho, Walt et al
“V0” sPHENIX integration

## Slide 11: MVTX in P6: 12/21/2018
Complete MVTX testing at BNL by 11/12/2021. (page-2)
Auxiliary activity early, to have FDR 2/2020 (page-7)