## Slide 1: MVTX Review Report and Plan 07/27/2018
MVTX Director’s Review @BNL July 19-20, 2018. Based on the close out session, we expect the report recommendations to be:
Perform fast simulation of 3-layer MVTX + 3(4)-layer INTT to evaluate global tracking performance;
  Taskforce led by Christopher Roland et al, ~6 weeks
2) Build a physical 3-D mock-up of the MVTX and INTT to evaluate the current design
  Walt Sondheim, Dan Cacace and Mickey Chiu/OSI et al, ~6 weeks
3) Conduct sensor irradiation tests up to ~1-2 MRad in next a few months to evaluate
TID effects on sensor performances, noise and efficiency etc.
  Leo Greiner/Grazyna Odyniec/Yuan Mei et al, irradiation at LBNL this summer
  Update –Leo has obtained the latest ALICE stave irradiation results tested above 2MRad and confirmed ALPIDE will have no issue for sPHENIX 5-year operation/~1MRad).

## Slide 2: TID Update – from Leo
Update from ALICE: TID > 2MRad
Noise level ~15e @1MRad (sPHENIX 5-year run)
Operation threshold range = 50 – 250e
NO problem for sPHENIX!
sPHENIX
Expected TID

## Slide 3: Other Near Term R&D Activities
Wire bond vibration study @BNL
  Eric + Paul G. and LANL folks, at BNL CAD 0.5T field magnet
  This summer, late August?
  Estimated resonance point ~50kHz, but not observed in ALICE (scanned 40 – 400 kHz)
Stave/Extended FPC Power prototype at CERN, in ~September
  Build a few (partially populated)HIC with extended FPC power cables
  Check the impacts on chip performances, potential noise pickup etc.
  Mechanical integration, patch panels modification etc
Stave production QA and procedures – prepare for sPHENIX stave production
  Training in IB production and test
  QA and QC procedures, Database etc.

## Slide 4: Update 7/30/2018 Following the draft review report recommendations (received last Friday 7/27/2018)

## Slide 5: #7. Is the design of the Staves and Readout Units final?
Yes, with two minor caveats:
- A stave with the longer power cable has not yet been produced.
There is a slight possibility a version 2.1 RU will be needed with very minor fixes to version 2.0.
MVTX Plan:
-Staves: will produce a few IB HIC prototype with extended PFC power cable, in September 2018
-RUs: will follow the ALICE test and production plan

## Slide 6: #8. Are the Staves and Readout Units ready for procurement?
The RU are ready for procurement.
The staves will be ready following the team’s addressing the final general recommendation (presented below) concerning the interferences between the INTT and MVTX envelopes. The committee believes however a solution will be found.
Recommendation for RUs:
- Order RUs together with ALICE to save money. Note, this is a recommendation to BNL management.
Recommendation for staves:
Procure longer power cables, test and confirm any production issues with CERN team as soon as possible.
MVTX Plan:
Staves: will produce a few IB HIC prototype with extended PFC power cable, in September 2018, and evaluate:
- noise level
- issues with HIC and stave assembly procedures with longer FPC power cables etc.

## Slide 7: Recommendations for Simulations
- Create a prioritized list of the tracker layout configurations to consider creating additional space for MVTX integration with INTT, by changing number of layers in INTT.
Provide realistic time scale for selection of the final layout.
MVTX Plan:
The task force is working on these recommendation

## Slide 8: General recommendation ​to be done before the commitment to purchase staves in September
The primary concern emerging from this review is whether there is an unavoidable interference between the MVTX and INTT envelopes in the services region.
  The preferred solution is to move the MVTX power patch panel to a location further out in the Z direction from the signal patch panels. However, it is not certain this will work.
  Other possible strategies to free up space from the INTT envelope might be to decrease the number of INTT layers or move them further out toward the TPC.
We recommend all of these approaches be quickly considered by mid September.
  A quick mockup of both the INTT and MVTX in the interference region only should be made. Fast simulations of the INTT with either 3 or 4 layers, or INTT with larger radii should be made to consider the impact on the physics.
  And finally modeling of what can be gained in the interference region by either decreasing the number of INTT layers to 3 or moving the layers further out in radius should be done.
Results of all of these should be summarized and presented to upper management for consideration before the commitment to purchase the Alice staves.