## Slide 1: MVTX Status & Plan
Ming Liu
Los Alamos National Lab
for the MVTX Group
1st sPHENIX Workshop in China
Peking University, Beijing, China

## Slide 2: Outline
Project Status
MVTX full proposal
  Physics and Simulations
  Readout and Controls
  Mechanical Integration
  Budget and Schedule
R&D Highlights
Latest development
Document: sPH-HF-2018-001
https://indico.bnl.gov/event/4072/

## Slide 3: MVTX Status: Where do we stand?
Full proposal submitted to BNL Associate Laboratory Director Dr. Berndt Mueller in Feb. 2018
March 27, a meeting of ALD, MVTX principals, co-SP and sPHENIX project office. Given improved DOE funding fiscal outlook, ALD recommended to bring MVTX into MIE baseline:
  This would be post-OPC/CD-1 Review(5/23-25, 2018), MIE baseline will be defined in the CD-2 (~summer 2019); MS Project -> P6 in progress
  Exploring advance-funding options to procure Readout Units ($250K, now) and staves from ALICE at CERN ($1.2M, fall 2018)
    Cost saving and reduce technical and schedule risks
  ALD seeks DOE agreement to proceed
MVTX workfest at MIT 4/30-5/1, 2018
  Refine MVTX roadmap – cost & schedule etc
  Prepare for sPHENIX integration mini review (~summer)
    MVTX+INTT+TPC…
    Both electrical and mechanical systems
https://indico.bnl.gov/event/4380/

## Slide 4: MVTX: Monolithic-Active-Pixel-Sensor-based VerTeX Detector
sPHENIX Inner Tracking
“Adopt” ALICE/ITS
Mini. risk,
Max. physics
sPHENIX upgrade @RHIC
ALICE ITS Upgrade @CERN;
Inner Tracker System (2021+)
Key integration tasks:
Readout
Mechanics
MVTX could also be a day-1 EIC detector

## Slide 5: Monolithic-Active-Pixel-Sensors (MAPS) ALPIDE: The next Generation State of the Art Pixel Tracker
Advantages of ALICE MAPS(ALPIDE):
  Very fine pitch (27x29 μm)
  High efficiency (>99%) and low noise (<10-6)
  Excellent time resolution, ~5 μs
  Ultra-thin/low mass, 50μm (~0.3% X0)
  On-pixel digitization, low power dissipation
An ideal detector for sPHENIX and EIC physics!
50 μm
28 μm
ALPIDE design
FPC
9 Chips
Cooling plate
A 9-chip MAPS stave, 9 x (1.5 x 3 cm2)

## Slide 6: sPHENIX Tracking System
TPC
INTT
MVTX
Excellent Tracking system:
  TPC: Time Projection Chamber
  INTT: Intermediate Silicon Strip Tracker
  MVTX
TPC:
R = 20-80cm
INTT:
R =6,8,10,12cm
MVTX:
R=2.3, 3.2, 3.9cm
2m

## Slide 7: MVTX Enables the 3rd Science Pillar
Jets
Upsilons
Open Heavy Flavor
Bottom quarks are heavy (4.2 GeV)
Produced in initial collision, probe QGP evolution
Well controlled in pQCD
Provide access to fundamental transport properties

## Slide 8: MVTX Physics Highlights
Heavy quarks – unique probe of QGP w/ new scales, mc, mb
  Study mass dependence
    Jet quenching & energy loss
    Flow – interaction with medium
  Access QGP properties
    Temperature, density, coupling, transport coefficients, viscosity etc.
MeV
1
10
102
103
104
mu md
LQCD
TQGP
mc
mb
Tc
ms
“B meson and b-jet modification”
“B meson and b-jet flow”

## Slide 9: New Insight into QGP: HF-Jet Substructure
QCD Splitting function in QGP
H. Li & I. Vitev (2018)
f->f+g
g->f+fbar
Gluon splitting
Prompt c/b

## Slide 10: New Insight into QGP: B v2
Very active theoretical investigation:
LANL model
CUJET
Duke model
TAMU
UrQMD
AMPT
PHSD
Ads/CFT
BAMPS
HQ+EPOS2
JetScape
….
Various new model calculations, PHSD, AMPT etc, for B-hadron v2:
Significant non-zero v2 suggested, but may NOT follow the scaling due to large b-mass!
D-meson: v2 scaling
observed at RHIC
sPHENIX sensitivity
sPHENIX sensitivity

## Slide 11: B-Hadron & b-Jet Tagging
Physics Reminder
Detected using the long lifetime of bottom quark hadrons:
  Displaced tracks
  Large 2nd vertex invariant mass
Need high precision tracking and vertex determination – MVTX!
Need excellent jet detection capabilities – sPHENIX!

## Slide 12: Simulation for b-jet and B-meson tagging
Design to Simulation
sPHENIX Geant4 display of pT=30 GeV/c B+-hadron
MVTX and INTT _
_ MVTX Ladders modeled in details
MVTX sensors

## Slide 13: B-hadron Tagging
Impact parameter (DCA) method to tag non-prompt D0 from B-meson decays
Inclusive and exclusive channels possible
Partial reconstruction: B->D+x
Fully reco’d: B->D+pi

## Slide 14: b-jet Tagging in p+p and Au+Au
Fully implemented MVTX models used in performance projection
b-jet tagging projection evaluated with full tracking + calorimetry simulation
  Tagging work point has been stable (60% Purity 40% eff for pp)
  Central Au+Au Tagging work point has been stable (40% Purity 40% eff)
Performance has been stable using truth jet finding or calorimetry reconstructed jet finding
sPHENIX b-jet work point

## Slide 15: MVTX Detector Integration
Electrical system
  Readout, power, controls
Mechanical system
  Support and cooling
MVTX:
3 layers
48 staves

## Slide 16: MVTX Electronics, Power and Controls
Power Board
Filtering Capacitors
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Front End
Regulated Power
FELIX
Back End
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
5-10 m
GBT Optical Links
9-sensor Stave
DCS
CAN bus
Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
MVTX Detector Electronics consists of three parts
Sensor-Stave (9 ALPIDE chips) | Front End-Readout Unit | Back End-FELIX

## Slide 17: MVTX Full Readout Chain Demonstrated
Readout Unit configures Stave using USB interface
FELIX distributes clock to Readout Unit
Readout Unit distributes clock to the Stave
Stave is triggered, sends data at 1.2Gb/s
Configured GBT link to recover clock from FELIX
Readout Unit receives the data and sends the data to FELIX over fiber using GBT link
FELIX packs data, stores it on disk using RCDAQ - the sPHENIX data formate and software
Readout
Unit
Stave
FELIX
Server + FELIX
Readout Unit + Stave

## Slide 18: MVTX Test Beam at Fermilab: 02/20-03/10
Goals:
  Test full readout chain
  Evaluate ALIPDE sensor performance
Experimental setup
  A 4-sensor telescope
  Full readout chain: MAPS+RU+FELIX+RCDAQ
Parasitic with INTT run
Very productive & collaborative
120 GeV
proton
4-sensor
Telescope

## Slide 19
FELIX(“CRU”) in Server
KC705
LHC 40MHz
Mockup
4-ALPIDE Telescope;
5m long SamTec cables
4-ALPIDE Telescope Setup at Fermilab Test Beam
RU
Summary:
Successfully operated the full readout chain
Confirmed all communications links and data path
Confirmed telescope performance
  Primarily 120GeV proton beam; also with low energy pion beams
  Beam trigger rate ~7kHz
  Tested High ALPIDE occupancy runs, with 10cm lead bricks in front of the sensors

## Slide 20: Fermilab Test Beam Results (I)
4-hit track
Cluster size: 2.1 ~ 2.4
Mostly single tracks
4-sensor telescope
# of tracks per event
Cluster size
120 GeV proton beam

## Slide 21: Fermilab Test Beam Results (II)
Hit Efficiency > 99.5%
Pixel size (~28um)
Hit Spatial Resolution: < 5 um

## Slide 22: ALPIDE Readout Optimization and Trigger Latency Study
OUT_A clipping: VCLIP. Decreasing VCLIP decreases clipping point.
OUT_A returns to baseline time: ITHR, VCLIP. Increasing ITHR decreases discharge time, and decreasing VCLIP decreases discharge time after clipping.
OUT_D return to baseline time: IDB. Increasing IDB increasing charging time hence decreasing pulse duration.
clipping point
- Expected sPHENIX trigger latency 4~5 uS
- Two possible readout modes: 1) Triggered and 2)Continuous

## Slide 23
A Test Bench at LANL
Power Board
Filtering Capacitors
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Regulated Power
FELIX
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
5 m
Optical Links
9 Sensor Stave
RCDAQ
One HIC and 5+ individual ALPIDE chips.
MOSAIC miniDAQ
Power Board

## Slide 24: Trigger Latency and Signal Shaping Time Study
Lower the OUT_D threshold (IDB) increases the trigger duration time, but also increases the cluster size which might include more background hits.
In the continuous readout mode, “trigger/strobe” can be as early as ~1uS
Default set
Lower Threshold
(Lower the IDB)
sPHENIX
trigger

## Slide 25: Mechanical Integration Model of MVTX with INTT inside TPC with the addition of two concentric composite cylinders;
Location in Z where the inner-hcal ends (see control drawing) Z=2175.0 mm
Location of conflat flange on beam-pipe

## Slide 26: MVTX and INTT Integration – Work in Progress
It is clear from this detail view the conical region of the MVTX detector barrel with the INTT that the MVTX will need to translate in Z…

## Slide 27: Signal and Power Extension for FPC

## Slide 28: MVTX Carbon Structures
IB CYSS
Layer 0
Layer 1
Layer 2
Detector carbon frames:
End Wheels
CYlindrical Support
Structure (CYSS)
Carbon structures need modifications w.r.t. ALICE for installation in sPHENIX

## Slide 29: MVTX Mechanical Conceptual Design
View of MVTX half detector assembly with extended central barrel
IB CYSS
Layer 0
Layer 1
Layer 2
27cm
MVTX Staves
Stave layout
Beam view
Need extension for sPHENIX INTT integration

## Slide 30
 | FY2018 | FY2019 | FY2020 | FY2021 | FY2022
MVTX Cost | $1,436,825 | $1,911,749 | $2,610,068 | $501,407 | $63,152
Chart: sPHENIX MVTX Cost & Schedule Profile
| FY2018 | FY2019 | FY2020 | FY2021 | FY2022
FY2018 FY2019 FY2020 FY2021 FY2022 | 1436825.0796 | 1911749.0297 | 2610068.0348 | 501406.9081 | 63152.0927
New numbers:
$1.52M
$1.6M
FY18: Stave + RU production
FY19: Stave/RU QA & test; mechanical
design & carbon frame production
FY20: Carbon structure production
& detector assembly
FY21: Test and installation at BNL
RU units moved from FY19 to FY18
* 50% cost reduction due to joint production with ALICE
FY20-22: funding profile smoothing
Proposed new early funding
Work in progress “smoothing”
MVTX installation:
Starts ~6/2022
Budget in full proposal

## Slide 31: Updated Major Cost Items
$250K
$1.2M

## Slide 32: Possible Contributions from China?
Offline detector and physics simulation
  sPHENIX
  EIC
FPC extension R&D at CERN, LANL
  MVTX+INTT+TPC integration
Electronics production test and QA
  Readout Units/CERN, FELIX/BNL
  Power boards and control system
Stave assembly, test and QA
  CERN, China, US
Slow control firmware/software development
  Online monitoring
  Safety controls
Carbon structure design and/or fabrication?
Detector construction and test
  LBNL, half-barrel assembly, test, QA
  Final assembly & installation at BNL
Timeline
(MVTX & Heavy Flavor Topical Groups)
Now
2018
2019
2020
2022

## Slide 33: Summary and Outlook
MVTX full proposal completed
  Expanded science
  sPHENIX baseline
Cost and schedule update in progress
  Major item cost
  Funding profile smoothing
Excellent progress in R&D
  Readout and controls proof-of-principle demonstrated
  Conceptual mechanical system design being developed
MVTX+INTT+TPC integration in progress
  Electrical and mechanical system
  sPHENIX wide coordination through Office of Integration
To be ready for sPHENIX Day-1 Physics in 2023
  sPHENIX and later EIC possibility
Welcome Contributions from Chinese Consortium!
Document: sPH-HF-2018-001
https://indico.bnl.gov/event/4072/

## Slide 34: Backup slides

## Slide 35: Physics & Simulations: from sPHENIX to EIC
MVTX

## Slide 36: RHIC Multi-Year Plan: sPHENIX 2023-2027+
Precision B-tagging w/ MVTX:
  Tracking resolution better than 50um @pT=1GeV
  High multiplicity HI collisions
  Low multiplicity but high rate p+p collisions
  High efficiency and high purity
B hadrons/pT<15GeV: O(1M)
b-jets/pT>15GeV: O(100K)
Evolving

## Slide 37: Summary: Major Remaining R&D
Mechanical/Electrical integration with INTT+TPC
  Carbon structure design
  FPC extension
Full electrical system control
  Power
  Safety
  Online monitoring & controls
Readout system firmware/software with slow controls

## Slide 38: More information

## Slide 39: Mechanical Integration

## Slide 40
sPHENIX Integration: MVTX + INTT + TPC

## Slide 41: MVTX staves
stave
Wire Bonding
Single Stave:
FPC + Wire Bonding + Sensors + Space Frame

## Slide 42: INTT-MVTX Conflict
INTT 4-layers
Currently a clear conflict between the INTT and MVTX
  INTT only includes ladder, no connectors, cooling barbs, etc
R&D items: 1) Extend cables to move the conical structure further out in z-direction; 2) Design/optimize INTT layers to fit current MVTX geometry;
  FPC data cable is the HDI and can’t be easily extended, short “firefly” cables possible?
  Reduce angle of cone – redesign C-structures and connectors
|η|<0.95
|η|<1.09
|η|<1.28
|η|<1.12
INTT Acceptance
@ |z|=10

## Slide 43: INTT-MVTX Conflict
INTT 4-layers
Extend cables to move the conical structure further out in z-direction
  FPC data cable is the HDI and can’t be easily extended
  Possibly add short “firefly” cables to hook up to patch panel, R&D needed
Reduce angle of cone – redesign

## Slide 44: MVTX/INTT Integration Extend MVTX Service Cables?
506.2 mm
16 mm
41.9 mm
16.15 mm
The 9 silicon chips are read out in parallel: each chip sends its data stream to the end of Stave by a dedicated differential pair, 100 mm wide. Two additional differential pairs distribute the clock and configuration signals.
CHIP 1
CHIP 9
……
CHIP 2

## Slide 45: MVTX FPC R&D @CERN and LANL

## Slide 47
END WHEELS
PATCH PANEL
ESTIMATED TOTAL MASS HALF DETECTOR 1,100.0 grams
CONICAL SECTION
MVTX half detector assembly

## Slide 48: MVTX Detectors

## Slide 49
DETECTOR SECTION
SERVICES, SUPPORT SECTION
ALICE HALF-BARREL ASSY
Service Barrel: Design and Fabrication

## Slide 50: ALICE Inner Tracker Rail Support
The MVTX plus INTT half barrel assemblies location position is provided by the engagement of 4 rollers on the half-barrel, which would be previously measured and aligned, into four precise inserts housed in the “cage-rail” assembly.
Eccentric:
Adjustable roller +/- 1.0 mm, by steps of .25 mm
Rail guides for upper half assembly
In sPHENIX we will not use a “service cone, rail system” anywhere near the size of that planned for the ALICE detector, but we will use their concept.

## Slide 51: INTT Readouts from both North and South
h=0
h=1
105 cm
35cm
Bus Extender
The bus extender needs to run to ROC boards (reuse FVTX ROC) outside TPC.
Minimum length is 105cm – ladder length + distance to ROC board.
ROC
Boards
Bus Extender
ROC
Boards
Identical to FVTX Big Wheel
ROC boards mount off inner EMCAL

## Slide 52: BNL control envelope drawing; Z location of the inner hcal is at 2175,0mm
Z=2175mm

## Slide 53: Cross-section view from CAD model of MVTX, INTT, TPC, beam-pipe, plus two composite conical shells

## Slide 54: Gap between conical shell of MVTX and inner layer of INTT is 11.58 mm
Dist= R61.58 – R50
= 11.58mm

## Slide 55: 56.0 mm gap between INTT and inner radius of TPC
Gap= R200-R143.5
= 56mm

## Slide 56: Earlier model for the INTT, chevron configuration, inner layer half ladders in width;
Number of ladders:
Layer 0 – 38 half ladders,
Layer 1 – 26
Layer 2 – 34
Layer 3 - 42

## Slide 57: Offset from OD of beampipe and innermost component of the MVTX
New gap 2.025 mm

## Slide 58: Offset needed to install split MVTX into run location around beampipe, passing over 2.75 in conflat flange
37.6mm

## Slide 59: INTT stave design with HDI

## Slide 60: Latest configuration of ladders in the INTT, 4 layers where each is made from two layers for hermeticity

## Slide 61: New INTT model with HDI extensions;

## Slide 62: Cost & Schedule

## Slide 63: Cost and Schedule I the Full Propsal
Total budget: 6.5M
  Production
  Assembly
  Integration
About 9 months schedule float
Major Items | Cost ($M) | Schedule
Staves (WBS 1.5.3.1) | 1.3 | 8/2018-5/2019
Readout & Controls (WBS 1.5.2) | 1.3 | 1/2019-6/2019
Mechanics & Detector Assembly (WBS 1.5.3) | 1.8 | 2019-2022, TBO
Integration (WBS 1.5.4) | 1.0 | 2021-2022, TBO
Project Management | 1.0 | 8/2018-1/2023

## Slide 64: MVTX labor profile in the full proposal
 | Escalation + Overhead + Contingency
Labor | $2.5M
M&S | $4M ($3.75M if RU produced in FY18)
Only engineers and Technical staff costed to the project

## Slide 65: Early funding motivation for MVTX FY18,FY19
Buy 84 good staves from CERN following ALICE production, end FY18
  Includes: sensors, space frame, FPC, assembly and tests
  Very low technical risk
  CERN will deliver 100% working staves
Buy 58 Readout Units with the ALICE production in FY18 (was FY19)
  FPGA chips and GBT chips as part of the ALICE production
    GBT not commercially available product
  ~50% cost saving w.r.t. to estimated budget (exact number confirmed 04/18)
MVTX telescope Fermilab test beam confirmed the readout chain and sensor performance in early March 2018
  Sensors(ALPIDE) + RU(frontend) + FELIX(backend) + sPHENIX RCDAQ
To attract external funding & support for MVTX
  Foreign consortium, individual institution

## Slide 66: M&S cost options & risks
Staves:
  Oprion1: MVTX production following ALICE production at CERN, ~Aug 2018
    All material included and 100% working staves delivered
  Option2: Partial stave assembly at CCNU (China)
    MVTX project would still need to buy sensors, Flexible Printed Circuit (FPC) and space frames
    Wuhan could assembly sensor and FPC; assembly with space frame may be done elsewhere
    No experience assembly inner barrel  training required and hardware modified
    Potential saving on some labor assembly work
    Yield unknown -> schedule and cost uncertainty
Readout Units (radiation hard electronics):
  Option1: Produce with ALICE batch (FPGA chips & GBT chips) in FY18
    50% cost reduction w.r.t. budgeted cost
  Option2: MVTX produces its own batches cost increase and schedule impact
Carbon structures:
  Exploring cost-saving options, build carbon structures elsewhere (France and Italy) instead of LBNL etc.
Reuse hardware from LDRD
  Electronics, Power System etc.
Green: low risk / MVTX baseline budget
Red: High technical risk, low cost saving or increased cost

## Slide 67: LANL LDRD – MVTX/sPHENIX Key Tasks/Milestones
RU/KC705)/FELIX1.5 Integration
40MHz, 7/17-12/17
RUv1.x/FELIX2.0, 10MHz,
11/17 – 6/18
MVTX Design Review ~7/2018
System test, cosmic & source
6/18 - 1/19
LDRD
MVTX: 2018 – 2023
Stave Production, procure FPGA, GBT etc.
8/18-4/19
7/17
10/17
10/18
10/19
Electronics Production
1/19-8/19
Test Beam, tracking performance
analysis, NIM paper etc.
1/19 – 9/19
Today
BNL Director Review
7/10-11, 2017

## Slide 68: Electronics and Controls

## Slide 69: MVTX Electronics Overview
Power Board
Filtering Capacitors
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Front End
Regulated Power
FELIX
Back End
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
5-10 m
GBT Optical Links
9-sensor Stave
DCS
CAN bus
Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
MVTX Detector Electronics consists of three parts
Sensor-Stave (9 ALPIDE chips) | Front End-Readout Unit | Back End-FELIX

## Slide 70: Sensor and Electronics R&D @LANL
ALPIDE evaluation and optimization
  MOSAIC + Single Chip/Stave
  Cosmic and source
  Laser system
Power unit tested
  PU + MOSAIC
  PU + RU
Full readout chain demonstrated
  ALPIDE + RUv1.0 + FELIX v1.5 + RCDAQ
  Full stave + RUv1.x + FELIX v2.0 + RCDAQ
Mechanical system integration
  Conceptual design developed
  MVTX+INTT integration
Collimator
Sr90 source
MVTX
ALPIDE chip
Scintillator

## Slide 71: First Full Chain Readout: Success!
Successfully configured, triggered and readout single ALPIDE chip
  RU configures ALPIDE using python scripts interfacing the USB chip on RU
  Felix distributes clock to RU, the RU then distributes the clock to the ALPIDE
  ALPIDE is triggered on the control line, sends data at 1.2Ghz over copper
  The RU receives the data and sends the data to FELIX over fiber using GBT link
  FELIX packs the data and stores in on disk which is read out using RCDAQ
  Configured ALPIDE to accept triggers from FELIX using python software that came with the RU
  Configured GBT link to recover clock from FELIX and GT link (FGPA gigabit interface)
  8 RU’s emulated using 1 fiber link per RU on FELIX, 15kHz, 400 hits per RU
Currently working the implementation of the above using a Stave
LANL + Martin, JohnH et al
RUv1.0

## Slide 72
LANL Fermilab Test Beam Setup 03/2018
4-ALPIDE Telescope + 4-SamTec cables + 1 RU + 1 FELIX(“CRU”)
LHC 40MHz
mockup
CLK recovered from
FELIX through GBT link;
Trigger from FELIX
4-ALPIDE Telescope
4 5m SamTec Cables, 1.2Gbps
FELIX (“CRU”)

## Slide 73: Parallel Effort at UT-Austin – Shared R&D

## Slide 74: LANL R&D: Single ALPIDE Chip Scan – Active Channel Fraction
Scanned the available chips and stave at the LANL lab through digital scan to verify the dead channel fraction: the bad channel fraction is <1%.
Similar results with different readout speeds.
Chip 1 test example
No. of 0 hits
777
Cold channel
1
Hot channel
0
Bad fraction
0.15%

## Slide 75: Hit Pixel Cluster Distribution from Source Test (Sr90)

## Slide 76: Achieved all goals and more!
Tested a new readout scheme
  4 sensors (~4 staves) per RU (ALICE 1 stave per RU)
Sensor performance evaluation
  Cluster size
  Threshold, signal shaping, trigger delay
System stress test
  High multiplicity events created via lead bricks “shower”
  With 5, 10, 20cm lead bricks
Analysis software developed
  Online monitor
    hit distribution, relative alignment etc.
  Offline reconstruction, alignment etc.
    Preliminary alignment, ~O(100um)
hits
Hits/sensor
4 sensors
Connected
to one RU
RU

## Slide 77: RC DAQ event Data Screen Shot
Rcdaq receiving events from KC705 using ddump utility
ffff0044ffffc0ff4ea0
a0 - Chip Header
4e - bunch counter
ff - IDLE
c0 - Region Header
40 00 - first Hit
Second screen shot showing end of one event (b0…, f000f000) and the beginning of another

## Slide 78: Data Rate Calculations
  Assume 10us window and cluster size 3
 | Collision Rate
Au Au | 200kHz
P P | 10Mhz
 | Au Au | P P
# of collisions | 2 = 10us * 200kHz | 100 = 10us * 10Mhz
# of hits, hottest chip | 270 = 3 * 90 | 75 = 3 * 25
# of hits in a stave | 1983 = 3 * 661 | 543 = 3 * 181

## Slide 79: Expected Data Rate (from the proposal)

## Slide 80: Physics & Simulations: from sPHENIX to EIC
MVTX

## Slide 81: B-jet tagging
Multi-tracks w/ large DCA
2nd vertex mass reco’d
CMS work-point, Phys. Rev. Lett. 113, 132301 (2014)

## Slide 82: sPHENIX Projected RAA Sensitivity
Open questions to be answered: energy loss mechanisms and QGP medium properties
B-jets
B-Mesons

## Slide 83: sPHENIX Project Elliptical Flow v2
Open questions to be answered: nature of quasi-particles, medium interactions and transportation
B-jets
B-Mesons

## Slide 84: More Theoretical Inputs (II): B-meson R_AA
New calculations from PHSD for B-hadrons:
Potential significant anti-shadowing effects
Open b-bar in AuAu, very important baseline for Upsilon program!
B prod.
x~0.05
@RHIC
Gluon
anti-shadowing
Q2 ~100
EPS09

## Slide 85: Project Organization