## Slide 1: MVTX Status Overview WBS 3.2
Ming Liu
LANL
For the MVTX Group

## Slide 2: Outline
MVTX project scope update
Design and R&D progress
Near term plan
Document: sPH-HF-2018-001
https://indico.bnl.gov/event/4072/
Submitted to BNL ALD 2/2018

## Slide 3: MVTX Enables the 3rd Science Pillar
Jets
Upsilons
Open Heavy Flavor
Bottom quarks are heavy (4.2 GeV)
Produced in initial collision, probe QGP evolution
Well controlled in pQCD
Provide access to fundamental transport properties
Jin/Xin’s talk

## Slide 4: A Short Summary of the Project Status
RU and Stave production – a separate direct procurement from ALICE/CERN
  Technical doc and paperwork were prepared and sent to UTK from BNL in November
  Paperwork in progress through OSP at UTK, aim for sign-off by December.
    60 RUs and 84 staves, production starts ~ January 2019.
MVTX upgrade project in sPHENIX P6
  RU and stave production moved out from this scope
  Work in progress on funding details
    Split engineering/tech T&E among LANL, MIT, LBNL, BNL etc.
  Adjustment in WBS scope (some moved to WBS 2.x) to keep the total cost under $5M
  To be discussed and updated at this sPHENIX collaboration meeting
Recent reviews since last collaboration meeting in June 2018
  MVTX Production Review 07/19-20, 2018
    Stave and RU procurement readiness
    https://indico.bnl.gov/event/4729/
    Draft responses presented and discussed at PMG meeting
      Review committee members, BNL and sPHENIX management
  MVTX Interim Design Review, 11/19/2018
    Mechanical system integration
    Led by John Haggerty, draft recommendations being discussed
      no evident showstoppers
    https://indico.bnl.gov/event/5351/
All recommendations
on stave/sensor R&D addressed

## Slide 5: MVTX Detector
MVTX RUs, PUs & other services
3-layer sensor barrel
- 48 staves, 432 chips
Service cone: signal, power, cooling
and mechanical support
MVTX
parameters
End-Wheel
CYSS: Cylindrical Shell Structure
Extended power FPC

## Slide 6: MVTX Readout, Power and Controls (11/2018)
Power Board
Flex PCB Filtering Capacitors
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Front End
Regulated Power
FELIX
Back End
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
GBT Optical Links
9-sensor Stave
DCS
CAN bus
CAEN Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
MVTX Detector Electronics consists of three parts
Sensor-Stave (9 ALPIDE chips) | Front End-Readout Unit | Back End-FELIX/DAM
one pixel
ALPIDE pixel:
Shaping
Digitization
Zero-suppression
3x buffer
ATLAS Front-End Link eXchange (FELIX):
sPHENIX Data Aggregation Module(DAM)

## Slide 7: MVTX Full Readout Chain Demonstrated
4-hit track
4-MAPS telescope
120 GeV proton
beam
Tracking spatial resolution
achieved: <5 um
4-MAPS
telescope
Fermilab Test Beam: Feb-Mar, 2018

## Slide 8: Progress in MVTX Global Mechanical System Integration
L = 350.0 cm
MVTX service barrel design proposed, with two parts:
  Part-1: from MVTX to PP-1b, all power PCB, 40cm
  Part-2: length TBD later, from PP-1b to PP-2
TPC
TPC
R= 209.6cm
INTT
MVTX
PP-1a:
short signal cables
PP-2:
Signal and power cables
PP-1b:
power cables
Service Barrel
Walt & Ross’ talks

## Slide 9: MVTX Mechanical Integration in Progress
This MVTX model shown with 40cm flat power extension cables
Walt’s talk
PP-1a: signal cables
PP-1b: power cables

## Slide 10: Confirmed HIC with Extended 40(60)cm Power FPC
Built and tested two HICs at CERN in the week of 9/17/2018
  No change in sensor performance (noise, threshold) observed, as expected;
Details presented by Dr. Sho Uemura at the sPHENIX general meeting on 9/23/2018
60cm PWR FPC
40cm PWR FPC
ALICE: 15cm PWR FPC
Followed identical
ALICE IB QA test procedure,
with a 8m SamTec cable!
Nice work by Alex and Sho!

## Slide 11: MVTX + 4-layer INTT 3-D Mockup Demonstrated
MVTX and INTT
Space conflict resolved!
Office of System Integration
– led by Mickey & Bob,
a team of engineers and physicists

## Slide 12: Sensor Irradiation Test – OK at 2.7MRad
Continuous effort by ALICE (@NPI, Czech)
BNL review recommendation: test sensor up to 1MRad
https://indico.cern.ch/event/758048/

## Slide 13: Response to the July MVTX Review Recommendations
Completed sensor/HIC/stave evaluations at CERN
  Built and tested two HICs with 40cm and 60cm long power FPC
    Confirmed sensor performance same as the ALICE default configuration
  Sensors irradiated up to 2.7MRad, no problem (updated 9/18/2018).
Addressed all recommendations on stave/sensor R&D
Cost are set for staves/RU, UTK has started procurement paperwork
  Technical specs document completed for production
  RU, Staves, sPHENIX production starts ~ January 2019, expect to last ~12 months
MVTX/INTT mechanical integration
  Mechanical design being updated and mockup done
  Inner tracking task force completed evaluation, preferred INTT-layer < 4
  SamTec readout cables
    ALICE confirmed signal performance with 8m long readout cables. For MVTX, 10m very likely works (30AWG vs 32AWG), to be confirmed by on-going R&D
Cables
  BNL approved the use of SamTec blue cables
    Electrically better & mechanically compact
  Signal and power cable samples ordered/obtained for mechanical global system integration mockup
https://docs.google.com/document/d/1vsm_G7ZLgqv-kBZqK0jF69T_Nx2Uwk0Zxv86jRVxybw/edit?usp=sharing

## Slide 14: Scope of the MVTX Project
MAPS Staves & Electronics
  Readout Integration R&D (LANL LDRD)
    Frontend: ALICE/ITS, RU
    Backend: ATLAS FELIX
    Reprogram RU & FELIX into RCDAQ/sPHENIX
  Production-I:
    84 ALICE/ITS-IB staves from CERN
      Acceptance test @LBNL, 48+spares(36)
    60 ALICE/ITS-RU from CERN
      Acceptance test @UT-Austin, 48+spares(10)
  Production-II:
    sPHENIX production
      Acceptance test @LANL, 8 FELIX
    Final detector assembly in US
      LBNL half detectors
      BNL full detector
    Ancillary systems
      “adopt” ALICE ITS system
      Power, slow control & monitoring etc.
Mechanics & Cooling
  Changes to ALICE/ITS inner tracker mechanical structures
    End Wheels
    Cylindrical structure shells
    Detector half barrels
    Detector and Service half barrels
  Mechanical Integration,
    Conceptual design (LANL LDRD)
    Prototyping sPHENIX R&D
    Design integration frames, MIT/LANL/LBNL
    Composite structures, LBNL
    Non-composite structure, MIT
    Installation tooling etc., BNL/LANL/MIT/LBNL
  Adopt ALICE cooling plant design
    Modifications to fit sPHENIX, MIT/BNL
    Much smaller heat load than ALICE ITS
Dave’s talk

## Slide 15: MVTX Schedules and Milestones (11/2018)
CY-2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU
production
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel
design & production
End Wheels
CYSS
Half barrel #1
Half barrel #2
Half barrels
arrive @BNL
MVTX installation & commissioning @BNL
RU, FELIX, PS, cables etc.
Install half barrels
@sPHENIX IR
Ready for beam;
sPHENIX day-1 run
FELIX
production
Barrel Assembly & Testing @LBNL
ALICE IB stave done;
Facilities available for
sPHENIX production;
A window of opportunity:
Low technical risk
Cost saving
sPHENIX: CD1/3a CD2
MVTX
1st collisions
Installation
Global integration
/interface design?
design & procure
interface to
sPHENIX rails
Design & procure
sPHENIX rails
To be updated @FSU 12/2018
Work in progress:
LANL/MIT/LBNL
Design and fabrication
Dave’s talk

## Slide 16: Stave and RU Production QA Plan Documents
Staves
Purchase 84 staves from ALICE/CERN
  48 + 28(spares for 2 inner layers) + 8 spares
  Production following the completion of ALICE ITS/IB
  Starting ~Oct. 2018, will last 6-12 months
  Fully tested at CERN before shipping to US
    All Gold/Silver staves (same as ALICE IB)
    A LANL postdoc (Dr. Yasser Morales) oversees production QA at CERN
Acceptance QA at LBNL
  Full test and QA
    Electrical
    Mechanical
  Detector assembly at LBNL
Readout Units
Purchase 60 RUs from ALICE/CERN
  48 + 12 spares(20%)
  To be part of ALICE production
    Cost saving
    Minimize technical risks
  Initial test at CERN
Acceptance QA at UT-Austin
  Full test
  LANL as the 2nd test site
https://indico.bnl.gov/event/4729/

## Slide 17: MVTX Services - Work in Progress
Service racks located close to MVTX detector
  RU
  PU
  “Minimal cable length”, ~8m
    R&D on 10m at LANL
48 RU and 24 PU
  1PU ->2RU
  6-U VME crates
CAEN bulk power supply
  located nearby
Cooling plant
  Location TBD
MVTX
RU/PU& PS

## Slide 18: Near Term Project Tasks & Schedule
RU production through ALICE: 60 RUs
  Being started at CERN, first batch of ALICE production ~ Dec., 2018
    sPHENIX RUs available: ~Summer 2019
  Acceptance test and QA at UT-Austin: starting ~summer 2019
    Good opportunity for training and contribution
Stave production through ALICE: 84 staves (ALICE Gold/Silver QA)
  sPHENIX sensor production ~Jan. 2019
    3 months (wafer production) + 1 month (dicing & testing)
    Stave assembly starts @CERN, ~ April 2019, will take ~12 months to finish
    Training & contribution at CERN, Stave test and QA
  Acceptance test and QA at LBNL, ~Summer 2019
    Hand-carrying staves to LBNL, ~4 trips, ~20 staves each trip
Mechanical system integration design
  In good progress, under OSI
Carbon and non-composite structure design and fabrication
  Design & review – LANL/MIT/LBNL
  Carbon structures fabrication @LBNL
  Non-composite structure fabrication @MIT
Half-detector assembly at LBNL
  To setup assembly & test lab as soon as fund available
Safety, slow-control and monitoring
MVTX detector commissioning at BNL
  Setup lab, pre-installation commissioning
  IR installation
(Physics & detector simulations, tracking etc.)
More discussions in this week

## Slide 19: Stave Production and Shipping etc
Hand carry staves from CERN to LBNL, 4 trips
Preliminary design from CERN for stave transportation plates
  To be produced at CERN, paid by LBNL/sPHENIX
Extended design from CERN
for MVTX
ALICE ITS IB

## Slide 20: Detector Assembly & QA at LBNL
Precision positioning and installation of staves on end-wheels
IB CYSS
Layer 0
Layer 1
Layer 2
Follow ALICE IB assembly procedures to build half-detectors for MVTX
QA records in DB, travelers
Modified jigs for MVTX
Build two full half-barrel detector with the service structures
ALICE 1st half inner layer being assembled
6/2018@CERN
staves
Install SamTec & power cables during half-barrel assembly with the service barrel at LBNL (under discussion)
dummies
Walt & Yuan’s Talks

## Slide 21: sPHENIX MVTX Group: Institution Roles
Major institutions lead key tasks
for discussions

## Slide 22: Other Activities and Plan
CERN/ALICE visit planned ~end of January 2019
  Walt, Ming, and MIT/Bolek, Jim, Ross et al
  Mechanical design and integration
  Produce 5 staves for MVTX telescope
Preparation for MVTX stave production at CERN
  One LANL PD hired at CERN
  MIT student/postdoc/tech help at CERN, under discussion
  LBNL will start preparing the MVTX detector lab as soon as funds will transferred
Fermilab beam test with INTT, ~May 2019
  Waiting for HDI cables for INTT
  MVTX telescope will be ready ~March 2019
  A joint test beam proposal being developed
  Test global tracking, timing etc.
Possible MVTX beam test at LBNL
  MVXT sensor and readout electronics characterization etc.
  Details under discussion

## Slide 23: Summary: MVTX - WBS 3.2
MS Project being updated, now in the sPHENIX P6
  Stave and RU production through ALICE, moved out of the scope
  The rest of tasks, being optimize for cash flow and production schedule
Early procurements of staves and readout units (RU) through US-Alice
  DOE and BNL agreed, DOE directly pays UTK/US-ALICE
  Received signed letter from CERN on the cost of 60 RUs and 84 Stave, ~$1.36M
  Purchase paperwork in progress at UTK, aiming to complete by ~ December 2018
About $5M to be added to the sPHENIX Management Portfolio
  Open MVTX accounts in progress
  As a separated project from the MIE, for the rest of MVTX tasks
    Mechanical system design and fabrication
    Monthly report to sPHENIX and BNL upper management
    Update baseline cost and schedule by January 2019
  Will NOT be part of CD-2/3 DOE review
    Prepared for a separate DOE review in FY19

## Slide 24: backup

## Slide 25: MVTX Physics Highlights
Heavy quarks – unique probe of QGP w/ new scales, mc, mb
  Study mass dependence
    Jet quenching & energy loss
    Flow – interaction with medium
  Access QGP properties
    Temperature, density, coupling, transport coefficients, viscosity etc.
MeV
1
10
102
103
104
mu md
LQCD
TQGP
mc
mb
Tc
ms
“B meson and b-jet modification”
“B meson and b-jet flow”

## Slide 28: MVTX Sensors and Electronics Production
Major hardware:
  48 ALICE ALPIDE Staves + Interface Cables
  48 Front End Electronics (ALICE RUv2)
  6 Back End Electronics (ATLAS FELIX v2)
  6 EBDC Linux servers
  24 Power Boards + CAEN Supplies + Cables
  48 Stave to RU cables
  144 data fiber optic cables (3 fibers x 48 FEE)
Stave production: total 84, 75% spares
  Two inner layers: 12+16=28
  10% spares: 8 staves
RU production: 60 in total, 25% spares
ALICE ITS/IB stave
ALICE ITS RU

## Slide 29: sPHENIX vs ALICE
 | ALICE (Run3) | sPHENIX (Max) | Ratio of data rates sPHENX/ALICE
Pb+Pb / Au+Au | 50kHz | 200 kHz | 0.3
p+p | 200kHz | 13 MHz | (1.6)
Trigger/Readout | 50 kHz/(C.R.) | 15 kHz | -
MB Event track multiplicity dN/dη
  sPHENIX = 1/3 ALICE (pp)
  sPHENIX = 1/5 ALICE (AA)
sPHENIX triggered data rate fits well within ALICE readout hardware specs

## Slide 30: Projected Radiation Level after 5-year Runs
sPH-TRG-2018-001
Projected sPHENIX integrated luminosities after 5-year operation
  AuAu: Lum. = 214 nb-1
  pp+pAu: Lum. = 1340 pb-1
Projected sPHENIX MVTX L0 fluence:
Outer layers:
L1 = 0.6 x L0; L2 = 0.4 x L0
TID = 1060krad
NIEL = 6x1012 Neq/cm2
PHENIX study
arXiv: 0710.2676 [nucl-ex]
Sensors tested to full MVTX NIEL and ~3x TID @ALICE

## Slide 31
Type-A
Type-B
Type-A

## Slide 32: Two HICs Produced and Tested at CERN w/ Extended Power Cables NO noticeable difference in sensor performance, as expected
MVTX: 40cm flex power PCB
MVTX: 60cm flex power PCB
ALICE IB: 15cm

## Slide 33: HICs Test Results from CERN
Before: 2 ALICE IB HICs
After: same ALICE HICs, replaced power FPCs
Noise level: ~4 e’s; Threshold: ~180e’s; MIP: ~1000 e’s
Chip-0
Chip-8
HIC1
HIC2
Noise
Noise
Thr.
Thr.

## Slide 34: FPC Extension for Connection to Electrical Services
FPC
DVDD
AGND
DGND
DVDD
DGND
DVDD
AVDD
AVDD
AVDD
AGND
AGND
DGND
The connection to the service cables is achieved by a double FPC extension which is soldered to the HIC
x-section at interconnection between FPC and extensions
signal lines (FPC)
analogue power
digital power
FPC
AVDD
AGND
AVDD
AGND
AGND
AVDD
Flex power extension
FPC
DVDD
DGND
DVDD
DVDD
DGND
DGND
Flex power extension
From Antonello Di Mauro
Modified for sPHENIX:
15cm -> 40cm

## Slide 35
2-layer flex, PI: 50 µm, Cu: 35 µm, solder mask: 20 µm
The two flexes are connected together, AVDD is transferred from top to bottom
The PWR extension is connected to the FPC by iron soldering and wings are cut.
FPC Extension for Connection to Electrical Services
digital
analogue
analogue
digital
digital
AVDD
DVDD
DGND
AGND
From Antonello Di Mauro
Longer copper traces ~30cm
for sPHENIX, no other components
Unchanged

## Slide 36: LANL LDRD Activity Highlights
Sensor source test
MAPS evaluation
Readout integration
4-sensor telescope
Test beam at Fermilab
Mechanical & cooling
Signal integrity & cables
Cooling system
prototype
Service cone R&D
FPC power extension R&D
4-ALPIDE Telescope;
5m-long SamTec cables
Readout R&D
stave
RU

## Slide 37: sPHENIX/MVTX IB Stave Assembly Procedure at CERN by ALICE ITS Group
Prepare sensors and FPC
Glue 9 sensors to FPC
Wire bonding 9 sensors to FPC
Solder power flex PCB to FPC
Glue HIC to coldplate/carbon space frame
A stave is ready for QA
CMM

## Slide 38: MVTX: MAPS-based VerTeX Detector
sPHENIX Inner Tracking: MVTX
“Adopt” ALICE ITS/IB:
- Minimum risk
- Maximum physics
ALICE ITS Upgrade @CERN;
Inner Tracker System (2021+)
Key integration tasks:
Readout
Mechanics
Leveraging on extensive R&D and design work by ALICE
sPHENIX@RHIC
(2023+)

## Slide 39: Monolithic Active Pixel Sensors (MAPS) The Next-Generation, State-of-the-Art Pixel Tracker
Advantages of ALICE PIxel DEtector (ALPIDE) sensor:
Very fine pitch (27μm x 29μm), for superb spatial resolution
High efficiency (>99%) and low noise (<10-6), for excellent tracking
Time resolution, as low as ~5 μs, for less pileup
Ultra-thin/low mass, 50μm (~0.3% X0), for less multiple scatterings
0.5M channels with on-pixel digitization, for zero-suppression and fast readout
Low power dissipation, 40mW/cm2, for minimal service materials
An ideal detector for QGP physics!
50 μm
~28 μm
ALPIDE design
Flexible Printed Circuit(FPC)
9 Chips
Cold plate
A 9-chip MAPS stave, 1.5cm x 27cm
ALPIDE sensor:
1.5cm x 3.0cm, 0.5M channels

## Slide 40: B-Hadron & b-Jet Tagging
Detected using the long lifetime of bottom quark hadrons:
  Displaced tracks
  Large 2nd vertex invariant mass
Need high precision tracking and vertex determination – MVTX!
Need excellent jet detection capabilities – sPHENIX!

## Slide 41: Simulation for b-jet and B-meson tagging
Design to Simulation
sPHENIX Geant4 display of pT=30 GeV/c B+-hadron
MVTX and INTT _
_ MVTX Ladders modeled in details
MVTX sensors

## Slide 42: Expected Performance
Tony’s talk