## Slide 1: MVTX Task List and Institution Roles 12/5-9,2018 @FSU
Tasks
  Do we have all tasks covered by institutions with names?
  Do we miss anything important?
Resources
  Do we have enough engineering/technician T&E to cover all the technical work in the project?
  Physicists’ work
Schedule
  Can we accomplish all the tasks in time?
  Are the schedule consistent with your institution’s plan?

## Slide 2: MVTX Schedules and Milestones (12/9/2018)
CY-2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU
production
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel final design & production
End Wheels
CYSS
Half barrel assembly & test #1
Half barrel #2
Half barrels
arrive @BNL
MVTX installation & commissioning @IR
Install half barrels
@sPHENIX IR
Ready for beam;
sPHENIX day-1 run
FELIX
production
Layer Assembly & Test @LBNL
ALICE IB stave done;
Facilities available for
sPHENIX production;
A window of opportunity:
Low technical risk
Cost saving
sPHENIX: CD1/3a CD2
MVTX
1st collisions
Installation
Global integration
/interface design
procure sPHENIX
rail support
procure MVTX
Interface to rails
To be updated after discussion @FSU
Work in progress: split cost,
LANL/MIT/LBNL, design and fabrication;
Some global support move to WBS2.x
FDR
Pre-installation
commissioning @BNL

## Slide 3: FETS from MVTX Project (11/26/2018) To be updated by January 2019
need to update MIT, LANL, UTA, GSU FTEs et al,
both “on/off-proj” effort, staff/pd/students
MIT:
test and QA of staves at CERN,
simulations & tracking, detector work,
2~3 students,
0.5 Research Scientist, (Ivan)
~1 (Ross)
Mechanical design simulations, FEA etc., (0.5FTE)
;structure designed by LANL (50/50)
- Designer (~0.5FTE)
LANL:
Detector simulation & tracking
0.5 PD, MVTX geometry, Digi, alignment
0.5PD, tracking and DCA analysis
0.5 FTE, detector work, readout and control
0.5 FTE, software & analysis work
UT-Austin:
PD/student
Student/postdoc
Technician (~0.3)
GSU:
0.5PD/student
Online monitoring, power system
Safety DB and display

## Slide 4: sPHENIX MVTX Group: Institution Roles
Major institutions lead key tasks

## Slide 9: Project Cost & Schedule To Do List – MVTX Revision
https://docs.google.com/document/d/1iJeXKRCEmV4wGoGIUpKtPzvUtKE-yGvLaBJD6XGPKR0/edit?usp=sharing
Procurement plan – Excel file

## Slide 10: MVTX Task List & Institution Roles (I)
Sensors and Electronics
RU production and QA
  QA at UT-Austin
Stave production and QA at CERN
Detector assembly at LBNL
  Stave acceptance test
  Assembly
  QA
Readout and control integration
  FELIX production
  sPHENIX readout integration
  Electronics system control and monitoring
Slow control and monitoring, safety system interlock etc.
  Cooling system
  Power system
  Sensors and electronics
Mechanical system
Detector mechanical frame design and fabrication
  Carbon
  non-composite structure
Service barrel frame design and fabrication
  Global mechanical integration
Cable test & QA
  Signal and control
  Power
Power system
  Power unit
  CAEN PS
  Control & monitor

## Slide 11: MVTX Task List & Institution Roles (2)
Detector & Physics simulations
Detector geometry & response simulations
Vertexing & DCA
B-hadron Physics simulation and analysis
B-jet Physics simulations and analysis
Other physics topics
  Correlation
Explore open HF trigger/stream readout for pp and pA
And more ...
Detector commissioning at BNL
Setup MVTX lab at BNL
  Readout & cooling
  Half detector lab commissioning
Installation
  Services – power, cables
  Detector

## Slide 12: Tracking Topics
Tracking simulation overview -
MVTX detector geometry and response
Primary and 2nd vertex finding, 2-layer INTT + MVTX, DCA, - Sookhyun, Sanghoon
Event pileup in pp/pA collisions -Sanghoon
HF tagging, b-jet, B-hadron in pp, AA
New ideas, physics update - Jin, Xin et al
Explore open HF trigger for pp and pA - Jin, Ming et al
Discussion of to-do list for detector simulation and b-tagging - all
  Update physics plots with 2(or 3)-layer INTT + MVTX