## Slide 1: Build MVTX at CERN – in kind contribution? 02/12/2018
ALD is planning to visit CERN in next a couple of weeks
  one of the topics to discuss is a possibility that CERN builds the MVTX as in-kind contribution
What would be the minimal cost to have the hardware build at CERN?
  Sensors and staves
    Stave assembly and QA
  Readout electronics and controls
    RU production and QA
    FELIX production and QA
  Power supply
    PU production and QA
    CAEN module and mainframe
  Detector carbon structure
    Design
    Production
  Assembly
    Jig design
    Assembly and QA
  Carbon structure for sPHENIX integration
    Design
    Production
Possible US or joint US/CERN efforts:
FELIX
PU
Integration

## Slide 2: MVTX Major Cost Items: $2.54M/3.48M (total, 37%)
Major Items | Cost w/ 35%Cont. ($M) | Schedule
Staves (WBS 1.5.3.1) | 1.3 | 8/2018-5/2019
Readout & Controls (WBS 1.5.2) | 1.3 | 1/2019-6/2019
Mechanics & Detector Assembly (WBS 1.5.3) | 1.8 | 2019-2022, TBO
Integration (WBS 1.5.4) | 1.0 | 2021-2022, TBO
Project Management | 1.0 | 8/2018-1/2023

## Slide 3: Time Sensitive Items: ~1.5M
Stave production @CERN: 1.3M (w/ 35% contin.)
  0.97M(quote from ALICE, $11.5K/stave x84)
  Cost & technical risk reduction
  Two-step in procurement?
    48+20%, in FY18/19 (700K)
    Rest comes later (300K)
Readout Unit: 0.66M
  0.48M (best estimate, paid for RUv1.0, 58RUs)
  Cost reduction (~50%) through ALICE mass production
Saving from sPHENIX contingency? Non-DOE contribution?
MVTX has a large schedule contingency: > 1 year
  New funds could come in later … Foreign, non-DOE/US and DOE
Major Items | Cost ($M) | Schedule
Staves (WBS 1.5.3.1) | 1.3 | 8/2018-5/2019
Readout & Controls (WBS 1.5.2) | 1.3 | 1/2019-6/2019
Mechanics & Detector Assembly (WBS 1.5.3) | 1.8 | 2019-2022, TBO
Integration (WBS 1.5.4) | 1.0 | 2021-2022, TBO
Project Management | 1.0 | 8/2018-1/2023
CCNU?
sPHENIX
Run
2023

## Slide 4: Project file: 11/29/2017
11/29/2017
M&S
Labor

## Slide 5
M&S
Labor

## Slide 6
M&S
Labor

## Slide 7
M&S
Labor

## Slide 8: Labor Cost Profile in the Current Proposal
Physicists and students/postdocs are not costed
Engineers & Technicians are costed in the project
  Could some covered by institution’s base program?
  More “in kind” contribution to reduce project management cost (Engineers & Physicists)