## Slide 1: MVTX Proposal Status & Plan
Ming Liu
For MVTX Group
1/12/2018

## Slide 3: MVTX Full Proposal under Collaboration Review 1/3-15, 2018
Thanks many people’s countless effort!
Please send in your feedback by next Monday 1/15!
Full proposal page:
  https://www.overleaf.com/10919417bwssgrhhgryc#/41088600/
Major updates:
  Executive summary
  More theory inputs
  Detector performance simulations
  Readout integration
  Mechanical system integration
  Cost & Schedule
  Matches sPHENIX baseline schedule, day-1

## Slide 5: MVTX Proposal Submission Timeline
sPHENIX collaboration feedback – by 1/15, next Monday!
  MVTX group updates proposal: 1/16-19
Send to ALD for feedback: 1/19 (Fri)- 1/26 (Fri)
  MVTX group updates proposal: 1/27-31
Send the proposal to ALD for DOE submission: ~1/31(Wed)
DOE budget meetings: ~2/20 (BNL?), 2/22(LANL)
Our goal: early funding in FY18 for stave production at CERN
  MVTX stave production starts ~9/2018, following ALICE ITS/IB production ~8/2018

## Slide 6: MVTX+INTT Integration Model of MVTX with INTT inside TPC with the addition of two concentric composite cylinders;
Location in Z where the inner-hcal ends (see control drawing) Z=2175.0 mm
Location of conflat flange on beam-pipe

## Slide 7: MVTX-INTT-TPC updated model, Dan Cacace & Walter Sondheim 1/5/2018
TPC
INTT
INTT ROC cards
INTT ROC cards
MVTX
MVTX interface,
patch panel
MVTX service/installation barrel

## Slide 8: MVTX-INTT-TPC model continue;
Added extension cables to end of MVTX detector staves to conical patch panel, added length 20.0 cm

## Slide 9: LDRD Telescope and Test Beam at Fermilab
Participate in sPHENIX test beam at Fermilab
  A 3~4 sensor-layers telescope with full readout chain
  3~4 sensor + one RUv1.0 + one FELIX v1.5 + RC DAQ
  Test full readout chain
  Study sensor and electronics performance
  Preliminary tracking study
Schedule
  Setup at Fermilab: 2/20-23, 2018
  Parasitic run with INTT: 3/5-9, 2018

## Slide 10: MVTX Readout and Control R&D
Power Board/ALICE
Filtering Capacitors
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Front End Electronics
Readout Unit/ALICE
Regulated Power
Back End Electronics
FELIX/ATLAS
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
5-10 m
GBT Optical Links
9-sensor Stave
sPHENIX GL-1 & GTM
DCS
CAN bus
Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House