## Slide 1: Report from MVTX Workfest at MIT
Ming Liu
Los Alamos

## Slide 2: MVTX-HF Workfest @MIT 4/30-5/1
Primary goals: discuss and refine a roadmap for MVTX realization
  ~20 people attended, MVTX, INTT experts and sPHENIX management and project offices;
  defined near term action items for MVTX/INTT integration in sPHENIX
  A mini-sPHENIX integration review proposed, ~last week of June
Monday April 30:
  a series of presentations & discussions of current considerations on budget & schedule and possible cost reduction measures, and MVTX+INTT integration
Tuesday May 1:
  mostly follow up on day-1 discussions, near term R&D, MVTX + INTT
Workfest indico page: https://indico.bnl.gov/event/4380/

## Slide 3: Topics discussed
News from sPHENIX workshop in China;
Involvement in MVTX project from Chinese Consortium;
1) stave production, test and simulations;
2) possible joint R&D and/or production of carbon structures
MVTX project status and plan:
Working on early procurement of Readout Units and Staves from ALICE/CERN, EIC R&D proposal to DOE
Highlight from Fermilab test beam
MVTX integration in sPHENIX
Project schedule and funding profile smoothing to fit projected sPHENIX cash flow
Near term R&D for MVTX and INTT
New development in physics and simulations
ALD asked to have a mini-review of sPHENIX tracking integration ASAP (MVTX+INTT+TPC + …)
the week of June 25th or early July, TBD
Carry out critical integration R&D MVTX, INTT..
A joint MVTX+INTT test beam at Fermilab, Jan-Feb 2019
Full subsystem test
INTT ~1.2m extension bus
MVTX, full staves with possibly extended FPC

## Slide 4: A Broad Physics Program
Xin & Jin

## Slide 5: Simulations
Haiwang & Jin

## Slide 6: RU Production Plan
Plan-A
To be part of ALICE ITS production
Timeline:
  Production starts ~May 2018, available by ~end of 2018, fully tested
Need to make commitment “NOW”
  BNL management actively working on funding RU through RHIC $
Plan-B
Produce RU later, ~2019 as funding allows?
  Procure GBT chips from CERN
  Production & test in US, UT-Austin, LANL et al.
Higher cost, 2x
Higher technical and schedule risks

## Slide 7: Stave Production Plan
Plan-A
Produce staves following the completion of ALICE IB at CERN, using ALICE facility
Timeline:
  Starting as early as Aug/Sep 2018 +, last about 6 months for production and test
All 84 staves produced and tested at CERN
BNL management actively working with DOE to build staves at CERN
Plan –B
Produce full staves at CCNU later as funding allows, ~2019?
Earliest starting date - May 2019 + , ~12 months (could be shorter)
Higher technical and schedule risks
Impact on cost, TBD

## Slide 8: Carbon Structure Design and Fabrication
Mechanical system design
  MIT + LANL + LBNL + BNL
Production
  LBNL
Alternative path for fabrication being explored
  Europe (France & Italy, used for ITS Upgrade)
  Asia (Korea, China)

## Slide 9
Chart: 
| FY2018 | FY2019 | FY20 | FY21 | FY22
 | 1449 | 1645 | 1223 | 364 | 46
FY2018 | FY2019 | FY20 | FY21 | FY22
1449 | 1645 | 1223 | 364 | 46
k$
Current Profile (Cost): Funding Profile Smoothing, FY20-22
No Contingency and Passthru
Staves and RU in FY2018
Installation June 2022
Dave Lee

## Slide 10: MVTX Test Beam at Fermilab 02/20-03/10, 2018
Goals:
  Test full readout chain
  Evaluate ALPIDE sensor performance
Experimental setup
  A 4-sensor telescope
  Full readout chain: MAPS+RU+FELIX+RCDAQ
Parasitic with INTT run
Very productive & collaborative
120 GeV
proton
4-sensor
Telescope

## Slide 11
Fermilab Test Beam Setup 03/2018
4-ALPIDE Telescope + 4-SamTec cables + 1 RU + 1 FELIX(“CRU”)
LHC 40MHz
mockup
CLK recovered from
FELIX through GBT link;
Trigger from FELIX
4-ALPIDE Telescope
4 5-m SamTec Cables, 1.2Gbps
FELIX (“CRU”)
Online Display
Amazing work by Sho, Alex et al

## Slide 12: Fermilab Test Beam Results (I)
4-hit track
Cluster size: 2.1 ~ 2.4
Mostly single tracks
4-sensor telescope
# of tracks per event
Cluster size
120 GeV proton beam
Beautiful analysis done by Sanghoon and Darren et al

## Slide 13: Fermilab Test Beam Results (II)
Hit Efficiency > 99.5%
Pixel size (~28um)
Hit Spatial Resolution: < 5 um

## Slide 14
Rachid
Latest design of INTT support from Dan Cacace

## Slide 15: MVTX/INTT Integration Review: ~last week of June (TBD)
w/ ~50cm FPC power extension
  @LANL, voltage drop, noise pickup
  MVTX conical structure modification, reduced radius
w/ 10cm extension FPC – Plan A
  INTT layout, “cables” and supporting structures
  Final extension bus ~1.2m, INTT, summer 18
  MVTX conical structure modification
  10cm HS signal simulation now ..
  Early R&D possible? right now, ~Sept 2018 @CERN
  Mechanical mockup: MVTX+INTT + .. , @BNL, LANL
w/o FPC extension – Plan B
  Revisit INTT layout, cables and supporting structures
  Final 1.2m bus, summer 18
  MVTX conical structure modification
INTT/MVTX simulations
  New INTT postdoc, INTT optimization, including supporting structure
Resources
  MIT engineers Jim/Jason ?
  Walt, Dan, Mike L, Hubert, Chris …,
  new $$ from non-MIE BNL project? New engineers? Under discussion

## Slide 17: MVTX Flexible Printed Circuit (FPC) Extend MVTX Service Cables? Maximum +10cm for HS signal, TBD through R&D
506.2 mm
16 mm
41.9 mm
16.15 mm
Extend FPC/signal path by ~10cm
Power connection
Signal connection
Extend by ~10cm
signal
Power cable
Extension ~50cm
Also Impacting
SamTec
Cable length:
5~7m

## Slide 18
LADDER (rigid)
HDI (flexible)
INTT Support Structure
MVTX Outer Cone
TPC inner
Edge (r=20cm)
Space reserved for support rail
HDI connector (rigid)
Major conflict of INTT HDI connectors w/ MVTX
Work in Progress
Mickey, Dan, Walt, Rachid et al