## Slide 1: MVTX Status
Ming Liu
For the MVTX Group
7/13/2019

## Slide 2: MVTX Director’s Review: 7/19-20, 2018 @BNL
sPHENIX overview – Dave/Gunther
  Compelling science
MVTX overview –Ming
  Status and highlights
Readout integration – Alex/Sho
  #1, 2, 3
Staves – Leo/Grazyna
  #1, 3, 4, 5, 6, 7, 8
Readout Units – Jo
  #1, 3, 4, 5, 6, 7, 8
INTT overview – Rachid
  Important for tracking
Mechanical integration – Walt/Dan
  #10
Tracking simulation – Tony
  #9
Summary – Ming
  YES, we are ready, #1, 8

## Slide 3: Scope of the MVTX Project
MAPS Staves & Electronics
  Readout Integration R&D (LANL LDRD)
    Frontend: ALICE/ITS, RU
    Backend: ATLAS FELIX
    Reprogram RU & FELIX for sPHENIX
  Production:
    84 ALICE/ITS-IB staves from CERN
      Acceptance test @LBNL
      48+spares(36)
    58 ALICE/ITS-RU from CERN
      Acceptance test @UT-Austin, 48+spares(10)
    Reproduce 8 ATLAS/FELIX
      Acceptance @LANL
    Final assembly and test in US
      LBNL and BNL
  Ancillary systems, “adopt” ALICE system
Mechanics & Cooling
  Some changes to ALICE/ITS inner tracker mechanical structures,
    End Wheels
    Cylindrical structure shells
    Detector half barrels
    Detector and Service half barrels
  Mechanical Integration,
    Conceptual design by LANL LDRD
    Prototype by sPHENIX R&D, MIT/LANL
    Design integration frames
    Carbon frames etc., LBNL
    Installation tooling etc.
  Adopt ALICE cooling plant design
    Minor modification to fit sPHENIX
    Smaller heat load than ALICE ITS
Leo
Jo
Alex & Sho
Walt & Dan
Walt
- Early R&D by LANL LDRD, $5M, FY17-19, readout, mechanical design and physics
- Established LANL-ALICE MoU in 12/2016 for joint R&D for MVTX

## Slide 4: Schedules and Milestones
2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU
production
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel
design & production
MVTX final
design review
End Wheels
CYSS
Half barrel #1
Half barrel #2
Test half barrels
#1, 2@BNL
MVTX installation & commissioning @BNL
RU, FELIX, PS, cables etc.
Install half barrel
#1, 2@sPHENIX IR;
Ready for beam;
sPHENIX day-1 run
FELIX
production
Barrel Assembly & Testing
ALICE IB stave done;
Facilities available for
sPHENIX production;
Window of opportunity
sPHENIX: CD1 CD2
MVTX
1st collisions
Installation

## Slide 5: sPHENIX DAQ Architecture
DCM
DCM
DCM
DCM2
SEB
SEB
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Rack Room
DCM
DCM
DCM
DCM2
DCM
DCM
DCM
DCM2
DCM
DCM
DCM
FEM
DCM
DCM
DCM
FEM
DCM
DCM
DCM
FEM
Event Builder
SEB
EBDC
FELIX
EBDC
FELIX
EBDC
FELIX
Network
Switch
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
Buffer Box
Buffer Box
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
To the
RACF/HPSS
Calorimeters,
INTT, MBD
TPC
MVTX
SEB Sub-Event Buffer
EBDC Event Buffer and Data Compressor
ATP Assembles events and compresses data
Buffer Box data interim storage before sending data to the computing center

## Slide 6: MVTX Readout, Power and Controls
Power Board
Filtering Capacitors
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Front End
Regulated Power
FELIX
Back End
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
GBT Optical Links
9-sensor Stave
DCS
CAN bus
Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
MVTX Detector Electronics consists of three parts
Sensor-Stave (9 ALPIDE chips) | Front End-Readout Unit | Back End-FELIX/DAM
Alex,Sho, Jo, Leo
#1,2,3
one pixel
ALPIDE pixel:
Shaping
Digitization
Zero-suppression
3x buffer
ATLAS Front-End Link eXchange (FELIX):
sPHENIX Data Aggregation Module (DAM)

## Slide 7: MVTX Full Readout Chain Demonstrated
Alex & Sho
#1,2,3
4-hit track
4-MAPS telescope
120 GeV proton
beam
Fermilab Test Beam: Feb-Mar, 2018
Tracking spatial resolution
achieved: <5 um
4-MAPS
telescope

## Slide 8: Projected Radiation Level after 5-year Runs
sPH-TRG-2018-001
Projected sPHENIX integrated luminosities after 5-year operation
  AuAu: Lum. = 214 nb-1
  pp+pAu: Lum. = 1340 pb-1
Projected sPHENIX MVTX L0 fluence:
Outer layers:
L1 = 0.6 x L0; L2 = 0.4 x L0
Leo
#1
TID = 1060 krad
NIEL = 6x1012 Neq/cm2
PHENIX study
arXiv: 0710.2676 [nucl-ex]
Sensors tested to full MVTX NIEL and ~1/2 TID @ALICE

## Slide 9: Stave and RU Production QA Plan
Staves
Purchase 84 staves from ALICE production
  48 + 28(spares for 2 inner layers) + 8 spares
  Production following the completion of ALICE ITS/IB
  Starting ~Oct. 2018, last 6-12 months
  Fully tested at CERN before shipping to US
    All Gold/Silver staves (same ~ALICE IB standard)
    A LANL postdoc (Dr. Yasser Morales) oversees production QA at CERN
Acceptance QA at LBNL
  Full test and QA
    Electrical
    Mechanical
  Detector assembly at LBNL
Readout Units
Purchase 58 RUs from ALICE
  48 + 10 spares(20%)
  To be part of ALICE production
    Cost saving
    Minimize technical risks
  Initial test at CERN
QA at UT-Austin
  Full test
  LANL as the 2nd test site
Leo & Jo
#4,5,6,7,8

## Slide 10: #5, Has a QA plan and acceptance tests for the Staves and Readout Units been defined?
Yes!
  Both stave and RU QAP documents are available.
Leo & Jo

## Slide 11: Mechanical Integration
MVTX, INTT and TPC
  MVTX detector design modified
  Global interface being developed
L = 350.0 cm
TPC
TPC
R= 209.6cm
Walt & Dan
#10
INTT
MVTX

## Slide 12: Simulations for Optimization
Task force formed
  Goals and deadline defined
  Evaluate tracking with different INTT layers & geometry
Complementary roles in global tracking:
  MVTX:
    Precision DCA and vertexing
  INTT:
    Matching in-time hits of MVTX and TPC
    Important for p+p and p+A, pileups
Tony & Rachid
#9, 10

## Slide 13
MVTX Review Agenda Page:
https://indico.bnl.gov/event/4729/
- Presentation slides
- RU QA plan document
Stave QA plan document
All practice review slides & QA documents
https://indico.bnl.gov/event/4806/
Send your comments/suggestions