## Slide 1: MVTX Cost & Schedule (WBS 3.2)
Dave Lee/Ming Liu
April 9-11, 2019
BNL

## Slide 2: MVTX C & S - Assumptions
LANL 04/10/19
2
Integrated into the sPHENIX schedule (P6)
Self contained project, funding from BNL
Technically driven schedule
Built in resource hourly rates fully burdened with escalation
Electronics ready for production on day one due to LDRD effort, cost based on as built experience, FELIX and RU support boards
Schedule not smoothed, ~5 month contingency in P6 prior to sPHENIX installation
Will implement Risk Based Contingency
Staves and Readout Units (RU) not in P6, separate cost

## Slide 3: MVTX Schedules and Milestones
CY-2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU production @CERN
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel &
global system design
End Wheels
CYSS
Half barrel #1
Half barrel #2
6/15 Half barrels
arrive @BNL
Pre-installation commissioning @BNL
RU, FELIX, PS, cables etc.
8/25 Installed
Ready for commissioning
Ready for beam;
sPHENIX day-1 run
FELIX production
Stave testing, half-barrel assembly @LBNL
sPHENIX: CD1/3a PD2/3
MVTX
1st collisions
Installation
Detector & interface design
sPHENIX interface & global support design
SB & global mech
sys production
Today
Full detector
system test @BNL Lab
cooling & safety
System @BNL
Construction
MVTX final
review
Generic R&D
Sensors for RHIC
IR installation
Feb. 2019, in P6

## Slide 4: Milestones
Milestone | Date
Start Construction | 3rd Qtr FY 2019
MVTX Final Design Review | 1st Qtr FY 2021
Half Barrels Assembled | 3rd Qtr FY 2021
Installation Finished | 4th Qtr FY 2022
Ready for Beam | 1st Qtr FY 2023

## Slide 5: Cost Drivers
Mechanical design and fabrication
CYSS
End wheels
Service barrel
Global interface

## Slide 6: Basis of Estimate
Electronics: production & LDRD experience
  FELIX: ATLAS/sPHENIX production, LANL/LDRD
  RU services, cables: ALICE/ITS production, LANL/LDRD
  Power boards: ALICE/ITS production , LANL/LDRD
  CAEN bulk PS: Quote from CAEN, ALICE/ITS production, LANL/LDRD
Mechanics & Integration: design and production
  CYSS, End wheels, Service barrel: ALICE/ITS
  Integrations: Recent experience at RHIC upgrades, HFT/STAR, FVTX/PHENIX

## Slide 7: Resource Distribution
Chart: Hours
FY19 FY20 FY21 FY22

## Slide 8: Major Cost Items
WBS | Task Name | Cost (K)
3.2.3.2.2 | End Wheels (EW) | $165
3.2.3.2.3.2 | Cylindrical Structure(CYSS) | $465
3.2.3.2.3.3 | Service Barrel (SB) | $428
3.2.2.4 | Power System (PS) | $357

## Slide 9: Electronics Examples of low contingency
 | WBS | Cost (K) | Contingency | Basis
RU Services | 3.2.2.2 | $186 | 25% | As Built*
FELIX | 3.2.2.3 | $122 | 25% | As Built*
Power Board | 3.2.2.4.1 | $219 | 25% | As Built*
Power Supply | 3.2.2.4.2 | $138 | 25% | CAEN
Total Cost = $665 K
As Built means item is a production unit

## Slide 10: Carbon Structures Examples of high contingency
 | WBS | Cost (K) | Contingency | Basis
End Wheels | 3.2.3.2.2 | $165 | 45% | Previous experience
Cylindrical Structure | 3.2.3.2.3.2 | $465 | 45% | Previous experience
Service Barrel | 3.2.3.2.3.3 | $428 | 45% | Previous experience
Total Cost = $ 1,058 K

## Slide 11: Status and Highlights
Updated Cost & Schedule following MVTX workshop at LBNL, 3/2019
  Carbon structures
    Design
    Production
    Schedule
  Power system
  Contingency
    Electronics
    Mechanics
  Rebalance work load
    LANL, MIT, UT-A
TPC updated
  $4.3M (P6)
  Identified potential $600K cost saving
  OPC, TEC assigned
MVTX Workshop @LBNL, 2/28-3/2,2019
updated major carbon structures’
design & production cost, line by line

## Slide 12: Issues and Concerns
Budget availability
  Final mechanical system design work, at MIT, LANL and LBNL
  Early R&D required to reduce the high production contingency
Carbon structure production cost & schedule
  LBNL, other production plan/ATLAS
  Investiagin Other companies
  Expect high contingency for this ~50%
Global mechanical integration
  Inner volume design is good progress, in ceonuputal
  High contingency, ~ 50%

## Slide 13: Summary
TPC, $4.3M, w/ burden and escalation
Recent scrubbing exercise, possible cost saving ~$600K
Plan to update P6 after the review
Design engineering in progress
Collaboration institutions ready to receive the project fund

## Slide 14: backup

## Slide 15: Resource Distribution
Chart: Resource by Hours
| FY2019 | FY2020 | FY2021 | FY2022 | FY2023
PHYS | 1787 | 5076 | 825 | 656 | 120
ENG | 1997 | 4178 | 460 | 440 | 160
Tech | 999 | 1698 | 277 | 472 | 160
GRDSTD | 96 | 1036 | 864 | 0
Chart: Hours
| PHYS | ENG | Tech | GRDSTD
hours | 10726 | 7039 | 3116 | 2460
To be updated with Jan. version
Skip --- not tied to P6
Get on e from P6

## Slide 16: Funding Profile
2/2019, pre-LBNL C&S

## Slide 17
Cost and Schedule

## Slide 18: MVTX Schedules and Milestones
CY-2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU
production
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel
design & production
End Wheels
CYSS
Half barrel #1
Half barrel #2
Half barrels
arrive @BNL
MVTX pre- installation @BNL
RU, FELIX, PS, cables etc.
Installed 2 half-barrels
@sPHENIX IR;
Ready for beam;
sPHENIX day-1 run
FELIX
production
Stave testing, half-barrel assembly @LBNL
sPHENIX: CD1/3a PD2/3
MVTX
1st collisions
Installation
Detector & interface design
Design & procure
support structure
Procure insertion
sys to sPHENIX rails
Today
Complete detector
system test @BNL Lab
Procure & assemble
cooling system
Construction
MVTX Review
Post-LBNL workshop version, 4/2019; NOT in P6 yet
MVTX pre- installation @BNL
RU, FELIX, PS, cables etc.

## Slide 23: Guidance

## Slide 24: L3 Technical Overview
Emphasize any technical issues that still need to be resolved. If all has been decided put it on the slide.

## Slide 25: L3 Scope
What are you building?
Where you fit in the L2

## Slide 26: L3 Collaborators

## Slide 27: Schedule Drivers

## Slide 28: Cost Drivers

## Slide 29: Status and Highlights
Recent technical accomplishments

## Slide 30: Issues and Concerns

## Slide 31: Back Up