## Slide 1: Goals
BNL Director’s Review: 4/9-11, 2019
  Update budget
MVTX TPC: $5.49M  <$5M
  Revisit major high cost items - carbon structures etc
  Contingency: 30% now for all, some could be lower?
  Move some tasks to WBS 2.x

## Slide 2: MVTX detector in sPHENIX
TPC volume, length 2,160.0 mm
INTT detector, 2 layers
MVTX detector with service cylinder
Support brackets for TPC and INTT

## Slide 3: INTT Consideration

## Slide 4: Friday Mechanical System Discussions

## Slide 6: Notes from Friday Discussions
Power system
  Update the cost - Yuan
  Cost in US $ for CAEN, from LANL LDRD – Ming
  sPHENIX LV PS?
Carbon structures
  Service barrel – new $$, less by ~$100K
    Existing mold, R = 126mm, could be used for MVTX
  CYSS – new cost, less
    INTT feedback – cones become disk OK, if far away from IP
  End wheels – new cost, more, ~40% contingency for some
  Total cost for CYSS + End wheels, ~$1.6M
  Avoid conical structures if possible, they are expensive!
  Carbon structure production schedule - best by 2020 (Eric)
    One sPHENIX order, MVTX+INTT – cost saving
  PHENIX FVTX carbon strucutre cost ~$950K
Integration – reasonable cost, ~$700K

## Slide 7: New Schedule
Stave production @CERN
  May 2019- May 2020, 84 staves
  4-stave/week
Stave acceptance test @LBNL
  MOSAIC system, 9/2019 – 5/2020
Final mechanical design work
  May 2019 – $$ available ?
  CYSS, End wheels
  Service barrel and interface
MVTX detector assembly at LBNL
  LBNL ALICE ML stave production ends ~12/2019, a total of 60 ML staves
  Start MVTX detector assembly ~ end of 2019, after the completion of ALICE ML?
MVTX half-barrel full test @LBNL
  Starts ~mid of 2021
  Using full readout system if ready: 24RU + 12PU + 3FELIX/2 servers ()

## Slide 8: MVTX Schedules and Milestones, in progress (3/2019)
CY-2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU
production
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel
design & production
End Wheels
CYSS
Half barrel #1
Half barrel #2
Half barrels
arrive @BNL
MVTX installation & commissioning @BNL
RU, FELIX, PS, cables etc.
Install half barrels
@sPHENIX IR
Ready for beam;
sPHENIX day-1 run
FELIX
production
Barrel Assembly & Testing @LBNL
sPHENIX: CD1/3a PD2/3
MVTX
1st collisions
Installation
Global integration
/interface design?
design & procure
interface to
sPHENIX rails
Design & procure
sPHENIX rails

## Slide 9: Possible New Test Beam @Fermilab with INTT + TPC: 6/10-20
INTT DAQ needs more support
  After PD-2 review, 5/29-31, 2019
TPC TB, 6/12 – 7/7. (7/8/2019, beam turned off)

## Slide 11: MVTX Global Mechanical System Integration
L = 350.0 cm
MVTX service barrel preliminary design, with two parts:
  Part-1: from MVTX to PP-1b, all power PCB, 40cm
  Part-2: length TBD later, from PP-1b to PP-2
TPC
TPC
R= 209.6cm
INTT
MVTX
PP-1a:
short signal cables
PP-2:
Signal and power cables
PP-1b:
power cables
Service Barrel
iHCal/Support

## Slide 12: Detector Mechanical System Design
a new MVTX stave design with 40cm extended power FPC

## Slide 13: Detector Assembly
Precision positioning and installation of staves on end-wheels
IB CYSS
Layer 0
Layer 1
Layer 2
Follow ALICE IB assembly procedures to build half-detectors for MVTX
QA records in DB, travelers
Modified jigs for MVTX
Build two full half-barrel detector with the service structures
ALICE 1st half inner layer being assembled
6/2018@CERN
staves
Install SamTec & power cables during half-barrel assembly with the service barrel at LBNL
dummies

## Slide 14
West
East
2E1
2E3
1.4 m
6.5 m
4.7 m
MVTX Cable Route

## Slide 15: Signal cable design
The Samtec twinax cables carry clock (40 MHz), control (40 Mbps bidirectional), data (9x1.2 Gbps)
ALICE is using halogen-free cables (32 AWG, LDPE dielectric) due to CERN LSZH requirement; 2.65 + 5.3 m cables have been tested and are now in production
Stave
Stave
RU
RU

## Slide 16: The sPHENIX Detector Design
Φ ~ 5m
Outer HCal
SC Magnet
EMCal
TPC
INTT
15 kHz trigger
>10 GB/s data
MVTX
Inner HCal
Notes: 15kHz matched to collision rate.