## Slide 1: MVTX Overview
Ming Liu
Pre-QM sPHENIX Collaboration Meeting
November 1-2, 2019
Fudan Univ., China
Document: sPH-HF-2018-001
https://indico.bnl.gov/event/4072/

## Slide 2: MVTX Detector
Service cone: signal, power, cooling
and mechanical support
MVTX
parameters
End-Wheel
Extended power FPC
CYSS: Cylindrical Shell Structure
3-layer sensor barrel
- 48 staves, 27.1cm long
- 432 chips

## Slide 3: Scope of the MVTX Project – WBS 3.02
Electronics (3.02.02)
  Readout Integration
    RU QA & assembly @UT-A
    Backend: ATLAS FELIX production
    FELIX boards test @LANL/BNL
    Frontend RU services: daughter cards, transition boards, cables etc.
  Ancillary systems - “adopt” ALICE ITS system
    Power, slow control & monitoring etc.
Mechanical system (3.02.03, 3.02.04)
  MVTX detector mechanical structures
    Design & simulations
    End Wheels
    Cylindrical support structure
    Service barrels
  Mechanical system integration
    Service barrel support & interface to sPHENIX
    Installation tooling etc.
    Adopt ALICE cooling parameters
    Detector safety
  Detector assembly
    Stave QA & detector assembly @LBNL
A separate BNL R&D project, provides Staves & RUs
- no cost to MVTX project
- 84 ALICE/ITS-IB (modified) staves from CERN;
48+spares(2-inner layers+10%), in production
- 60 ALICE/ITS-RU from CERN
48+spares(12, 25%) , all produced

## Slide 4: Project Status Update: 11/01/2019
Confirmed long SamTec readout cables recently – last key electrical integration hardware R&D
  11.4m long cables, > 10m desired length
MVTX mechanical design: excellent progress
  Obtained quotes from outside companies based on preliminary designs for CYSS and End-Wheels
  MVTX/sPHENIX integration/insertion workfest , 11/14 @BNL, MVTX/INTT/TPC…
Early R&D fund released from BNL
  MVTX mechanical engineering design, MIT/LANL
  Preparation for Stave and RU acceptance test, LBNL, UT-Austin
July 2019 MVTX Cost & Schedule Review Response submitted
  WBS, PMP, Risk Registry, P6 updated
  Updated PMP and review response submitted to DOE
  We are ready for full production
Plan to start the MVTX production activities as soon as funds available
  Preparation for Stave and RU acceptance test & QA in US, LBNL and UT-A
  Carbon structure prototype production, site selection etc
Stave and RU production
  Stave production in progress at CERN
  60 MVTX RUs delivered to CERN
  Power mezzanine and transition boards produced at UT-A

## Slide 5: Funding Profile (FY19+20, 21,22)
sPHENIX MVTX Budget Profile |  |  |  | 
 | FY20 | FY21 | FY22 | Total
3.02.01 Management | $233,668 | $209,596 | $101,338 | $544,602
3.02.02 Electronics | $569,582 |  |  | $569,582
3.02.03 Mechanics and Assembly | $1,370,727 | $307,183 | $113,468 | $1,791,378
3.02.04 Integration and Infrastructure | $368,185 | $399,262 | $15,491 | $782,938
Performance Measure Baseline | $2,542,162 | $916,041 | $230,297 | $3,688,500
Contingency | $762,649 | $274,812 | $69,089 | $1,106,550
Total Project Cost | $3,304,811 | $1,190,853 | $299,386 | $4,795,050
From July MVTX Review:
MVTX funding profile: FY20 -22
Can we move some FY20 ($3.3M) activities to FY21 ($1.2M),
with minimal impact to the project?

## Slide 6: Schedules – Smooth Funding Profile?
Candidates for possible delays, from FY20 to FY21:
Carbon Structure production
PU and CAEN PS
Cooling system
Delay stave test and detector assembly work at LBNL
Recent new quotes for carbon structures: CYSS & EndWheels
Possible cost saving through commercial companies
Carbon structure full production possible in FY20, w/ big saving
Fully aligned with sPHENIX via external milestones
Possible Plan-B for FY20?

## Slide 7: MVTX Readout, Power and Controls Hardware Tested
Power Board
Flex PCB Filtering Capacitors
Samtec Twinax “FireFly”, ~10m
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Front End
Regulated Power
FELIX
Back End
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
GBT Optical Links
9-sensor Stave
DCS
CAN bus
CAEN Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
MVTX Detector Electronics consists of three parts
Sensor-Stave (9 ALPIDE chips) | Front End-Readout Unit | Back End-FELIX/DAM
one pixel
ALPIDE pixel:
Shaping
Digitization
Zero-suppression
3x buffer
ATLAS Front-End Link eXchange (FELIX):
sPHENIX Data Aggregation Module(DAM)
Slow control
Mike’s talk
Hardware status: Staves in production; RU produced, SamTec, PU & FELIX ready for production

## Slide 8: MVTX Global Mechanical System Integration
L = 350.0 cm
MVTX mechanical system preliminary design:
  Part-1: from MVTX staves to PP-1, all power PCB, 40cm
  Part-2: length TBD later, from PP-1 to PP-3
TPC
TPC
R= 209.6cm
INTT
MVTX
PP-1:
signal cables
PP-3:
Signal and power cables
PP-2:
power cables
Service Barrel

## Slide 9: Detector Supporting Structures: Part-1
Near final design completed for CYSS, End-Wheels
Obtained quotes from outside companies based on the latest designs for CYSS and End-Wheels
LBNL cost estimate in progress
Next:
Vendor selection
Pre-production

## Slide 10: MVTX Service Barrel – Part-2
PP-1:
signal cables
PP-2:
power cables
PP-3:
Signal and power cables

## Slide 11: ITS/IB Commissioning Setup @CERN, 9/2019
ITS/IB : top half barrel
ITS/IB : bottom half barrel
9/2019@CERN

## Slide 12: MVTX Global Mechanical System Integration

## Slide 13: MVTX Installation & Insertion System
Active discussions on mechanical design and fabrications
  MIT, LANL, LBNL
  CYSS, End-Wheels, Service Barrel
One-day MVTX/sPHENIX insertion system workshop
11/14/2019@BNL, Russ/OSI, Camelia et al
MVTX, INTT, TPC …
MVTX Installation Mockup
(WBS 2.x)

## Slide 14: Beam Pipe Extension by CAD
sPHENIX engineers meeting regularly with the CAD vacuum group;
CAD will do some test welds to beam pipe
material of the same OD to confirm;
Beam pipe modification in the MoU with CAD.
(WBS 2.x)

## Slide 15: 2019 Fermilab Test Beam Highlights

## Slide 16: Very Successful Test Beam @Fermilab 5/20-25, 6/17-22, 2019
4 staves
2 RUv1.1
1 PU
1 FELIX Server + RCDAQ
sPHENIX GTM
11.4m Custom SamTec Cable
Negative pressured cooling for staves
120GeV p-beam
10kHz (30kHz)
Beam intensity:
30k ~ 120k ppp
RU-2: 1 stave
RU-1: 3 staves
FELIX
GTM
SamTec: 11.4m
(2.6m+8.8m)
5m SamTec
Data & Control
Beam Trigger
4-stave telescope
Timing & Trigger
RCDAQ
Online Monitoring
- 1 fully functioning
9-chip stave;
- 3 staves with a few
broken sensors
A full system with final sensor/readout* hardware:
Multi-Stave + Multi-RU -> FELIX readout demonstrated
sPHENIX GTM integrated
Long readout SamTec cable certified
Cooling system demonstrated
* RUv1.1 identical to the final RUv2 electrically

## Slide 17: 2019 MVTX Test Setup
From view
Stave housing (four staves)
beam
Stave housing sits on a motion table which can be moved in (x, y) plane perpendicular to the nominal beam direction. It can also be rotated (+40, -40) degrees (see photo on right). Operation was done at counting house.

## Slide 18: Online Analysis: Detector Misalignment & Hit Spatial Resolution
Typical stave offset,
Horizontally: 20 x 30um = 600 um
Vertically: 5 x 30 um = 150 um
Hit spatial resolution:
peak_sigma_core = 0.55 (pixel size ) =15 um
Chip spatial resolution = 15/sqrt(2) = 11 um
Ref plane
Delta_X/Y
Row #: dY
Col #: dX

## Slide 19
Beam angle: 0
(eta ~0)
Beam angle: 40
(eta ~1)
MVTX 4-Stave Telescope
Offline analysis in progress: all TB data in RCF
https://wiki.bnl.gov/sPHENIX/index.php/MAPS-based_Vertex_Detector_(MVTX)

## Slide 20: Offline Analysis: Cluster size vs Angle
@ 0-degree
Cluster Size ~ 2.4
@ 40-deg
Cluster Size ~ 3.0
To calibrate MC simulations and tracking
Stave geometry, alignment
Clustering

## Slide 21: ALPIDE Sensor Operation Optimization
“ALICE Default Settings”
- “Pile up” integration time ~ 5uS
“Stretched Settings” for sPHENIX trigger study
- Pile up integration time ~ 8uS
64 cells x 106nS = 6.8uS
sPHENIX Trigger Latency ~ 4.7uS
sPHENIX Trigger Latency ~ 6.8uS

## Slide 22: Preliminary Offline Analysis: A simple straight line fit Track hit efficiency vs Trigger Delay
Hit_Eff_Stave3 > 99.5%;
Eff = stave3_hits/(tracks, at least 3hits 1/2/4)
June TB Data analysis in progress
For various ALPIDE operation points, shaping time, threshold, trigger delay etc.
4
3
2
1
From Yasser

## Slide 23: Offline Analysis: A simple straight line fit Stave-3 Track hit resolution vs Trigger Delay
dX, dZ < 5um
4
3
2
1
From Yasser

## Slide 24: Confirmed New MVTX Long SamTec Readout Cables 8.8m + 2.6m = 11.4m (10m desired for sPHENIX; ALICE 8m cables)

## Slide 25: 11.4m SamTec Readout Cable Tested @CERN
Double looped readout cables:
  Effective length = 2 x 11.4 m = 22.8m
  Data rate: 1.2Gbps
  One overnight run, ~10hrs
  Error rate < 1.4 x10-14
Production cable: 11m (>10m)

## Slide 26
Jo is testing the sPHENIX readout cables
Nice job!

## Slide 27: sPHENIX Stave Production Started @CERN
sPHENIX Production started in 9/2019
  Bi-weekly meeting on Thursday 5PM/CERN (9AM/LANL)
~10 staves/month
  Limited by Wire bonding , 2~3 staves/week
Production period: ~10 months
  Complete by the end of 2020
Produce 12 HICs in 2019
First ~21 staves available, 3/2020
First stave production kick-off meeting 10/24
- “The FPC production is well advanced, we have already the first batch of 24 pieces available.”
- ~100 golden chips available
- 1st sPHENIX HIC produced, “GOLD”, IBHIC-A201

## Slide 28: 1st sPHENIX HIC Produced at CERN - IBHIC-A201 & PWR extension clamp
First sPHENIX HIC
Power extension clamp

## Slide 29: IBHIC-A201
Accepted ALPIDE Chips from T847786 19T: A1*, A2, A4, A5, B1, B3, B7, C2, C3
*Dust removed from the back side.
Activities | Ins. after glue | Bonding | Ins. after bonding | Power test | Qualification test | HIC+SF+CP glue | = Stave Ready?
Done? | YES | YES | YES | YES | YES |  | 
Activities | Ins. after glue | Bonding | Ins. after bonding | Power test | Qualification test | HIC+SF+CP glue | = Stave Ready?
Done? | YES | YES | YES |  |  |  | 
With a new set up. PWR extension connection is made using a clamp. Pictures in the next slide.
IB HIC Qualification Test on 22.10.2019:
All gold.
Eyes are okay for all the drivers settings.
Qualification flag: Gold (Matrix: OK (Gold)/DTU: OK)

## Slide 30: Final Production RU Boards Tested at UT-A
60 sPHENIX RUs produced at CERN
10 RUs produced for LANL R&D
Tested 10 RU @UT-A, 10/14-18, 2019
  All tested good, found one bad optical transceiver (1/30)
  Jo, Yasser, Gerd
  Alex T. joined for one day, readout firmware/software plan
Plan to test the 60 sPHENIX RUs later

## Slide 31: R&D at LANL
Full ITS/IB QA testbench in operation
Python GUI developed for telescope readout and control operation
CAEN PS being tested
Stave testbench
Run Control
GUI

## Slide 32: A Full Readout Chain System Test
MVTX – readout in 6-subgroup
  48 staves + 48 RUs + 6 FELIXs
  A complete readout chain:
  8 staves + 8 RUs + 1 Felix + 1 RCDAQ Server
Hardware in hand at LANL
  6 staves + 4 HICs(w/o carbon frame)
  10 RUv2.1
  2 FELIX v2.0
  2 PU
  1 sPHENIX GTM
Build a telescope of:
6 staves + 2 HICs
8 RUv2.1
1 FELIX
1 PU
1 GTM
A test beam later this year or 2020 (TBD)
LBNL, 50MeV p-beam
LANL, 800MeV p-beam
Fermilab?

## Slide 33: Summary
Completed key R&D for readout integration
  Full 9-chip stave readout per RU
  Multi-RU readout per FELIX
  Long readout cables
  sPHENIX GTM
Completed preliminary mechanical design
  Vendor selection
  Carbon structure (pre)production
  Insertion mockup
Improve MC detector response, clustering – in progress
  Calibration data with incident angles, 0, 10,20,30,40,45
Stave and RU production at CERN - in good progress
  Acceptance test & QA in US
July MVTX review response submitted to DOE
  Expect project $$ distributed soon
We are ready for the full production and the physics!

## Slide 34: backup

## Slide 35: Near Term To-Do List
Continue mechanical system design
  CYSS, EW, SB
  Global insertion system design and full mockup
Carbon structure production
  LBNL CF update
  Follow up with US vendors for quotes
  Select vendor(s) for pre-production
RU acceptance QA at UTA
Prepare for stave acceptance QA at LBNL
FELIX production and test
  Jointly with sPHENIX TPC, at BNL? Or LANL?
2019 test beam data analysis
sPHENIX Stave production at CERN
We will follow up the progress closely, production, Test & QA
- bi-weekly meetings with CERN
ITS system surface commissioning at CERN
Now --- May 2020
A good opportunity to learn about the
system operation and controls;
Working on a coordinated effort within MVTX/sPHENIX,
Signup page,
https://docs.google.com/spreadsheets/d/1YBAyouW8geJHUPpzRyLlzN4ePW4YzI8glI5xI66N3ww/edit#gid=0
A full “8-stave + 8-RU + 1-FELIX + 1-PU + 1 GTM” chain test
  10 RU available
  1 PU arrived at LANL from LBNL
  8-stave/HICs telescope frame being designed
  RU & FELIX Firmware update in progress
  Slow control software & GUI
  A possible test beam run later this year

## Slide 36: sPHENIX Timeline

## Slide 37: MVTX Readout and Power Cable Route
sPHENIX MVTX: 7.9+m
  Cable-A: 1.4 m
  Cable-B: 6.5+ m
  Power cable:4.7+ m
Desired ~10m
PWR
RU
PU
Cable-A: 2.65m
ALICE ITS/IB final readout cables: ~8m
Cable-B: 5.3m
BNL has approved “non-halogen free” cables for sPHENIX

## Slide 38: Carbon Structure Production
Visited WorkShape 9/19/2019
  Walt and Ming, Simon
WorkShape well prepared
  Updated the design files
MIT design work good progress, well ahead of time
  Early Carbon structure review for pre-production, Nov/Dec 2019?
Other companies, CA..
  Received quotes for CYSS, End-Wheels
LBNL in progress

## Slide 39
ITS/IB RU and PU, w/ cables

## Slide 40
PU & CAEN PS
CAEN PS

## Slide 41: MVTX Goals – the 2nd TB, 6/17-22, 2019
Test and confirm optimal MVTX operation parameters for sPHENIX
  Threshold scan, analogy shaping time etc.
  Study chip hit efficiency vs trigger(strobe) latency
    dT = 1 ~ 10 uS
    Impact on occupancy & pileup
Parameters predetermined from laser scan at LANL, in good progress
    Single chip readout with MOSAIC with pulsed laser (~MIP)
    Threshold and noise
    Analogy shaping time
    Strobe delay and length

## Slide 42: Study MAPS Performance with Pulsed Laser @LANL
Inject “MIP” signal, focused laser beam
  850 nm laser, 4ns wide pulse, ~1 MIP
  50kHz trigger
  Find optimal MAPS operating parameters
Pixel hits
Laser system
MOSAIC Testbench

## Slide 43: Laser Scan Data – Pixel Hit Efficiency vs Trigger Delay
One of “Stretched Settings” for sPHENIX trigger
MAX: 64 cells x 106nS = 6.8uS
~ 4.7 us
sPHENIX Trigger
Pixel (Row-Col)
~ 4.7 us
sPHENIX Trigger latency
Pixel (Row-Col)

## Slide 44
MVTX
MVTX Test Beam, May 2019

## Slide 45
120GeV p-beam
4-stave Telescope
Negative Pressure Cooling System
2 RUs,
PU,
PS
Motion Table
(X,Y,Phi)

## Slide 46: First Collision Signals
sPHENIX GTM

## Slide 47: Staves, RUs, PU etc.
2 RUs
PU

## Slide 48
Telescope
RUs & PU
Cooling System;
negative pressure
@-30%ATMP (-5PSI)
120GeV p-beam
Telescope
120GeV p-beam

## Slide 49
When MAPS parameters off the optimal point, less hits collected

## Slide 50
No hits seen when MAPS parameters far-off the optimal point

## Slide 51: Installation

## Slide 52: 3-D event Display: p+Pb collision
Stave-1
Stave-2
Stave-3
Stave-4
Cameron

## Slide 53: Offline Analysis: Cluster size vs Angle Run 877, angle – 30 dgr
Cluster Size = 2.7

## Slide 54: Offline Analysis: Cluster size vs Angle Run , angle = 40
Cluster Size ~ 3.0
More work follows by Yasser, Sanghoon et al
Everyone is welcome to join the effort!
Stave geometry
Stave alignment
Clustering
Tracking
Update MVTX MC response in GEANT

## Slide 55: Run Types – Details being documented in MVTX wiki
Horizontal stave scans (many good runs)
Vertical stave scans
Angular stave scans and tilted runs
Electron beam at 5 GeV (one long run)
Extruded aluminum & Lead-block runs
Run1040
Run0877
Run0978
From Xiaochun

## Slide 56
Data run-log in sPHENIX Wiki,
Nice work by Xiaochun et al. @GSU
Jin’s test beam analysis framework
Offline analysis in progress