## Slide 1: MVTX Overview (WBS 3.2)
Ming X. Liu
Los Alamos National Laboratory
sPHENIX Collaboration Meeting @NCU
03/25-27,2019

## Slide 2: Outline
MVTX science & technology
Recent reviews and R&D progress
  LBNL MVTX/HF workshop highlights
MVTX project status
  Near term plan and to-do list
Document: sPH-HF-2018-001
https://indico.bnl.gov/event/4072/

## Slide 3: The sPHENIX Detectors
Φ ~ 5m
Outer HCal
SC Magnet
EMCal
TPC
INTT
15 kHz trigger
>10 GB/s data
MVTX
Inner HCal
Tracking system upgrade:
- MVTX (WBS3.2)
- INTT (WBS3.1)
Notes: 15kHz matched to collision rate.

## Slide 4: MVTX Enables the 3rd Science Pillar
Jets
Upsilons
Open Heavy Flavor
Bottom quarks are heavy (4.2 GeV)
Produced in initial collision, probe QGP evolution
Well controlled in pQCD
Access fundamental transport properties of QGP
Jin/Xin’s talk

## Slide 5
Dave’s talk from this morning

## Slide 6: MVTX Physics Highlights
“B meson and b-jet modification”
“B meson and b-jet flow”
Jin/Xin’s talk
MVTX: |eta|<1
precision vertexing
p+p, p+A, A+A

## Slide 7: Monolithic Active Pixel Sensors (MAPS) The Next-Generation, State-of-the-Art Pixel Tracker
Advantages of ALICE PIxel DEtector (ALPIDE) sensor:
Very fine pitch (27μm x 29μm), for superb spatial resolution
High efficiency (>99%) and low noise (<10-6), for excellent tracking
Time resolution, as low as ~5 μs, for less pileup
Ultra-thin/low mass, 50μm (~0.3% X0), for less multiple scatterings
0.5M channels with on-pixel digitization, for zero-suppression and fast readout
Low power dissipation, 40mW/cm2, for minimal service materials
An ideal detector for QGP physics!
50 μm
~28 μm
ALPIDE design
Flexible Printed Circuit(FPC)
9 Chips
Cold plate
A 9-chip MAPS stave, 1.5cm x 27cm
ALPIDE sensor:
1.5cm x 3.0cm, 0.5M pixels

## Slide 8: MVTX Detector – Modified from ALICE/ITS Design
3-layer sensor barrel
- 48 staves, 432 chips
Service cone: signal, power, cooling
and mechanical support
MVTX
parameters
End-Wheel
CYSS: Cylindrical Shell Structure
Extended power FPC
Ross’ talk

## Slide 9: Scope of the MVTX Project
MAPS Staves & Electronics
  Readout Integration R&D (LANL LDRD)
    Frontend: ALICE/ITS, RU
    Backend: ATLAS FELIX
    Reprogram RU & FELIX into RCDAQ/sPHENIX
  Production @CERN: $1.36M
    84 ALICE/ITS-IB staves from CERN
      Acceptance test @LBNL, 48+spares(2-inner layers+)
    60 ALICE/ITS-RU from CERN
      Acceptance test @UT-Austin, 48+spares(12)
  Production & Assembly @US: ~$5M
    Production QA & assembly
      Half detector assembly & test @LBNL
      FELIX test & integration @LANL/BNL, 6+spares(2)
    Ancillary systems
      “adopt” ALICE ITS system
      Power, slow control & monitoring etc.
Mechanics & Cooling
  Modify ALICE/ITS inner tracker mechanical structures
    End Wheels
    Cylindrical structure shells
    Detector half barrels
    Detector and Service half barrels
  Mechanical system integration,
    Conceptual design (LANL LDRD)
    Design & simulations, MIT/LANL
    Composite structure production, LBNL
    Non-composite structure, MIT
    Installation tooling etc., BNL/LANL/MIT/LBNL
  Adopt ALICE cooling plant design
    Modifications to fit sPHENIX, MIT/BNL
Final test @BNL, Installation & commissioning (BNL + MVTX group)

## Slide 10: MVTX Readout, Power and Controls
Power Board
Flex PCB Filtering Capacitors
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Front End
Regulated Power
FELIX
Back End
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
GBT Optical Links
9-sensor Stave
DCS
CAN bus
CAEN Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
MVTX Detector Electronics consists of three parts
Sensor-Stave (9 ALPIDE chips) | Front End-Readout Unit | Back End-FELIX/DAM
one pixel
ALPIDE pixel:
Shaping
Digitization
Zero-suppression
3x buffer
ATLAS Front-End Link eXchange (FELIX):
sPHENIX Data Aggregation Module(DAM)
Slow control
Mike’s talk

## Slide 11: MVTX Full Readout Chain Demonstrated (3/2018)
4-hit track
4-MAPS telescope
120 GeV proton
beam
Tracking spatial resolution
achieved: <5 um
4-MAPS
telescope
Fermilab Test Beam: Feb-Mar, 2018

## Slide 12: Highlights from Recent Reviews and R&D
July 2018 Stave and RU Production Readiness Review
November 2018 mechanical system integration review
April 2019 Review : “CD-1 equivalent”

## Slide 13: Stave and RU Procurement Readiness BNL Director’s Review, 7/19-20, 2018
To produce RU and staves as part of ALICE production
  Reduce technical risks
  Cost saving
To meet sPHENIX installation & run schedule.
DAY-1 PHYSICS
Recommendations:
RU, proceed with production
Resolve MVTX/INTT space conflict
  modify stave design, longer power cables
  build a 3-D model
  Simulation TF to optimize INTT layers
Stave radiation hardness
https://indico.bnl.gov/event/4729/

## Slide 14: MVTX/INTT Mechanical Integration – Stave Modification
This MVTX model shown with 40cm flat power extension cables
Ross’ talk
PP-1a: signal cables
PP-1b: power cables

## Slide 15: Confirmed HIC with Extended 40(60)cm Power FPC
Built and tested two HICs at CERN in the week of 9/17/2018
  No change in sensor performance (noise, threshold) observed, as expected;
Details presented by Dr. Sho Uemura at the sPHENIX general meeting on 9/23/2018
60cm PWR FPC
40cm PWR FPC
ALICE: 15cm PWR FPC
Followed identical
ALICE IB QA test procedure,
with a 8m SamTec cable!
Nice work by Alex and Sho et al!

## Slide 16: MVTX + 4-layer INTT 3-D Mockup Demonstrated
MVTX and INTT
Space conflict resolved!
Office of System Integration
– led by Mickey & Bob,
a team of engineers and physicists

## Slide 17: Sensor Irradiation Test – OK at 2.7MRad
Continuous effort by ALICE (@NPI, Czech)
BNL review recommendation: test sensor up to 1MRad
https://indico.cern.ch/event/758048/

## Slide 18: Address July 2018 Review Recommendations
Stave and RU procurement readiness
Completed sensor/HIC/stave evaluations at CERN
  Built, tested and confirmed two HICs with 40cm and 60cm long power FPC
  Sensors irradiated up to 2.7MRad, no issues (updated 9/18/2018).
Addressed all recommendations on stave/sensor R&D
Cost are set for staves & RUs, procurement through US-ALICE/UTK!
  Technical specs document completed for production, BNL/DOE agreed
  sPHENIX RU and stave production starts ~April 2019, practically already in progress
MVTX/INTT mechanical integration
  Mechanical design being updated and 3-D mockup demonstrated
  Inner tracking task force completed evaluation, preferred INTT-layers =2
Readout cables
  BNL approved the use of SamTec blue cables
    Electrically better & mechanically compact
    ALICE confirmed signal performance with 8m long readout cables. For MVTX, 10m very likely works (30AWG/sPHENIX vs 32AWG/ALICE), to be confirmed by on-going R&D at LANL
  Samples ordered for system integration mockup and test
https://docs.google.com/document/d/1vsm_G7ZLgqv-kBZqK0jF69T_Nx2Uwk0Zxv86jRVxybw/edit?usp=sharing
Christof, Rachid, Itaru’s talks

## Slide 19: MVTX Design Interim Review 11/19/2019, led by John Haggerty
Detector assembly & installation in sPHENIX
No evident showstoppers
https://indico.bnl.gov/event/5351/
Interim design review report, draft
Ross’ talk

## Slide 20: Detector Assembly & QA Plan at LBNL
Precision positioning and installation of staves on end-wheels
IB CYSS
Layer 0
Layer 1
Layer 2
Follow ALICE IB assembly procedures to build half-detectors for MVTX
QA records in DB, travelers
Modified jigs for MVTX
Build two full half-barrel detector with the service structures
ALICE 1st half inner layer being assembled
6/2018@CERN
staves
Install SamTec & power cables during half-barrel assembly with the service barrel at LBNL (under discussion)
dummies

## Slide 21: ALICE jig assembly steps;

## Slide 22: MVTX Global Mechanical System Integration
L = 350.0 cm
MVTX service barrel preliminary design, with two parts:
  Part-1: from MVTX to PP-1b, all power PCB, 40cm
  Part-2: length TBD later, from PP-1b to PP-2
TPC
TPC
R= 209.6cm
INTT
MVTX
PP-1a:
short signal cables
PP-2:
Signal and power cables
PP-1b:
power cables
Service Barrel
Ross’ talk

## Slide 23: MVTX Services - Work in Progress
Service racks located close to MVTX detector
  Electronics, power etc
  “Minimal cable length”, 8m tested at CERN;
    L~7.9m
    R&D on 10m cables at LANL
48 RU and 24 PU
  1PU ->2RU
  6-U VME crates
CAEN bulk power supply
  located nearby
Cooling plant
  Location TBD
MVTX
RU/PU& PS

## Slide 24: MVTX Readout and Power Cable Rout
sPHENIX MVTX: 7.9+m
  Cable-A: 1.4 m
  Cable-B: 6.5+ m
  Power cable:4.7+ m
On-going R&D for ~10m
PWR
RU
PU
Cable-A: 2.65m
ALICE ITS/IB final readout cables: ~8m
Cable-B: 5.3m
BNL has approved “non-halogen free” cables for sPHENIX
Sho talk

## Slide 25: Major Topics for LBNL HF/MVTX Workshop 2/28-3/2, 2019
New HF physics program development
Total project Cost, $5M cap
Cost of the mechanical system

## Slide 26: Mechanical System Discussions @LBNL
Discussed major carbon structures’
design & production cost
line by line,
also production schedule @LBNL

## Slide 27: Carbon Structures – Work in Progress
Conical sectors are expensive!
A new design under development to avoid the conical structures
From Walt: BNL workfest 3/12-13
Ross’ talk

## Slide 28
2 pt
2 pt

## Slide 29: Latest Budget Update
The cost is $3,699K, and if we add BNL’s global contingency of 30%, the project total cost would be $3.7M x 1.3 = $4.81M
If we go with the detailed contingencies discussed at LBNL (some less but some are higher than 30%), the total project cost is $4.91M
Moved the Electrical Integration Project management (~$100K) and Commissioning effort (~$155K) from MVTX to sPHENIX
Double checking all the numbers and update the budget in the P6 SOON

## Slide 30: MVTX Production Schedule Update
Stave production @CERN
  May 2019- May 2020, 84 staves
  4-stave/week
Stave acceptance test @LBNL
  MOSAIC system, 9/2019 – 5/2020
Final mechanical design work
  May 2019 – $$ available soon(?)
  CYSS, End wheels
  Service barrel and interface
MVTX detector assembly at LBNL
  LBNL ALICE ML stave production ends ~12/2019, a total of 60 ML staves
  Start MVTX detector assembly ~ late summer of 2019 (or after the completion of ALICE ML?)
MVTX full half-barrel detector test @LBNL
  Starts ~mid of 2021
  Using full readout system if ready: 24RU + 12PU + 3FELIX/2 servers

## Slide 31: MVTX Schedules and Milestones, in progress (3/2019)
CY-2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU
production
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel
design & production
End Wheels
CYSS
Half barrel #1
Half barrel #2
Half barrels
arrive @BNL
MVTX installation & commissioning @BNL
RU, FELIX, PS, cables etc.
Install half barrels
@sPHENIX IR
Ready for beam;
sPHENIX day-1 run
FELIX
production
Barrel Assembly & Testing @LBNL
sPHENIX: CD1/3a PD2/3
MVTX
1st collisions
Installation
Global integration
/interface design?
design & procure
interface to
sPHENIX rails
Design & procure
sPHENIX rails

## Slide 32: Upcoming BNL Director’s Review “Breakout Session 4” – Silicon Upgrade
April 9-11 Reviews@BNL
Wednesday, April 10, 2019 – Breakout Session 4 – Silicon Detectors*
8:30 am MVTX Overview/Management(20+10)
9:00 am MVTX Sensors/Staves/Det Assembly(20+10)
9:30 am MVTX Electronics(20+10)
10:00 am MVTX Mechanics, Integration & Infrastructure(20+10)
10:30 am Break(15)
10:45 am MVTX Cost and Schedule(20+10)
11:15 am INTT Overview/Management(20+10)
11:45 am INTT Sensors/Staves/Det Assembly(20+10
12:15 am Lunch(60)
1:15 pm INTT Electronics(20+10)
1:45 pm INTT Mechanics, Integration & Infrastructure(20+10)
2:15 pm INTT Cost and Schedule(20+10)
2:45 pm Committee Executive Session
We will present the latest updates at the review
- ready for the final design and full production

## Slide 33: Detector R&D in Progress
MVTX prototype telescope beam test at Fermilab
  Staves with “final” electronics and cables
  Test beam planned for May, with sPHENIX INTT
SamTec cables
  AWG30(MVTX) vs AWG32(ITS),
  ~10m cables
ALPIDE sensor characterization and optimization
  Readout and trigger optimization for sPHENIX
  Laser system setup in preparation
4-stave Telescope

## Slide 34: 2019 Test Beam: 4-stave Telescope
Scheduled for May 22-28, @Fermilab
Additions compared to the 2018 test beam:
  Staves (from single chips)
  Full-length MVTX signal cables (from 5 m off-the-shelf cables)
  FELIX v2.0 (from v1.5)
  Cooling system
  Power board
  sPHENIX GTM
34
4 ITS production stave @LANL
From Sho
PU

## Slide 35: Readout Electronics
RU v2.1, Power Board in production by ALICE
FELIX v2.0 in production by ATLAS
MVTX firmware and software in sync with current ALICE and ATLAS work, with MVTX-specific logic developed under this LDRD
Key readout boards qualified and in production
RU v1.0
RU v2.1
FELIX v1.5
FELIX v2.0
same functionality
production-qualified
Prototype PB
Production PB
in hand @LANL
@LANL ~May
in discussion
with LBNL
35
From Sho

## Slide 36: sPHENIX DAQ integration
sPHENIX detectors implement “plugins” to tie in to the central DAQ; the MVTX plugin was demonstrated at the 2018 test beam
sPHENIX clock and trigger is distributed by Granule Timing Module (GTM): one BNL prototype at LANL
  We have implemented the “receiver” in FELIX that allows MVTX to receive a trigger from sPHENIX;
MVTX is participating in discussions for the sPHENIX DAQ design
MVTX is fully integrated with sPHENIX
36
From Sho

## Slide 37: Readout Cable Testing
BNL has approved non-halogen-free cables (30 AWG, FEP dielectric); improved signal integrity
sPHENIX cable run estimates are converging: 1.4 + 6.5 m
Ordered SamTec cables for 1.2/2.65 + 5.3/8.8 m (total length 6.5 - 11.45 m)
We will qualify these cables using stave and RU (bit error rates, statistical eye), and scope/network analyzer
We will test full-length MVTX cables in the next months
37
From Sho

## Slide 38: Summary of Near Term Tasks & Schedule
RU production through ALICE: 60 RUs
  Started at CERN, first batch of ALICE production ~ Dec., 2018
    sPHENIX RUs available: ~Summer 2019
  Acceptance test and QA at UT-Austin: starting ~summer 2019
Stave production through ALICE: 84 staves (ALICE Gold/Silver QA)
  sPHENIX sensor production ~April 2019
    Stave assembly starts @CERN, ~ April 2019, ~12 months to finish
  Acceptance test and QA at LBNL, ~late summer 2019
    Hand-carrying staves to LBNL, ~4 trips, ~20 staves each trip
Mechanical system integration design
  In good progress, under OSI
Carbon and non-composite structure design and fabrication
  Design & review – LANL/MIT/LBNL
  Carbon structures fabrication @LBNL
  Non-composite structure fabrication @MIT
Half-detector assembly at LBNL: starting ~ late summer 2019
  To setup assembly & test lab as soon as fund available
Safety, slow-control and monitoring in progress - Mike’s talk
MVTX detector commissioning at BNL: ~summer 2021
  Setup lab, pre-installation commissioning
  IR installation
(Physics & detector simulations, tracking improvement etc., work in progress) – Jin’s talk
Great opportunity for university
groups to join the effort & contribute!
QA & Test
Detector assembly
Control & monitoring
Simulations and analysis

## Slide 39: Summary: MVTX - WBS 3.2
MS Project being updated, now in the sPHENIX P6
  Latest Cost & Schedule under review, under $5M cap
Stave and RU production through US-ALICE
  Early procurements of staves and readout units (RU) through US-Alice
    DOE and BNL agreed, DOE directly pays UTK/US-ALICE
    Received signed letter from CERN on the cost of 60 RUs and 84 Stave, ~$1.36M
    Purchase paperwork in progress at UTK, aiming to complete by ~ April 2019
MVTX detector design & construction
  About $5M to be added to the sPHENIX Management Portfolio
    As a separated project from the MIE
      Mechanical system design and fabrication
      Update baseline cost and schedule soon
      Monthly report to sPHENIX and BNL upper management
    Will NOT be part of CD-2/3 DOE review
    Engineering design work in progress, MIT/LANL et al
    Construction and assembly work in late summer 2019
  Open MVTX accounts in progress, for full production

## Slide 40: sPHENIX Status and Plan
MVTX approved
by BNL/DOE

## Slide 41: Thank You!

## Slide 42: backup

## Slide 43: sPHENIX MVTX Group: Institution Roles
Major institutions lead key tasks

## Slide 44: Open Charm & Beauty Production
Hadron | Abundance | ct (mm)
D0 | 61% | 123
D+ | 24% | 312
Ds | 8% | 150
Lc | 6% | 60
B+ | 40% | 491
B0 | 40% | 455
Bs | 10% | 453
Lb | 10% | 435
b-tagged jet and cor.
60%
0.5%
pT<15 GeV
pT>15 GeV
Exploring and more

## Slide 45: B-Hadron & b-Jet Tagging
Detected using the long lifetime of bottom quark hadrons:
  Displaced tracks
  Large 2nd vertex invariant mass
Need high precision tracking and vertex determination – MVTX!
Need excellent jet detection capabilities – sPHENIX!
Jin, Tony, Sanghoon

## Slide 46: Expected Performance
Tony’s talk

## Slide 47: Projected Radiation Level after 5-year Runs
sPH-TRG-2018-001
Projected sPHENIX integrated luminosities after 5-year operation
  AuAu: Lum. = 214 nb-1
  pp+pAu: Lum. = 1340 pb-1
Projected sPHENIX MVTX L0 fluence:
Outer layers:
L1 = 0.6 x L0; L2 = 0.4 x L0
TID = 1060krad
NIEL = 6x1012 Neq/cm2
PHENIX study
arXiv: 0710.2676 [nucl-ex]
Sensors tested to full MVTX NIEL and ~3x TID @ALICE (as of 9/18/2018)

## Slide 48: MVTX Sensors and Electronics Production
Major hardware:
  48 ALICE ALPIDE Staves + Interface Cables
  48 Front End Electronics (ALICE RUv2)
  6 Back End Electronics (ATLAS FELIX v2)
  6 EBDC Linux servers
  24 Power Boards + CAEN Supplies + Cables
  48 Stave to RU cables
  144 data fiber optic cables (3 fibers x 48 FEE)
Stave production: total 84, 75% spares
  Two inner layers: 12+16=28
  10% spares: 8 staves
RU production: 60 in total, 25% spares
ALICE ITS/IB stave
ALICE ITS RU

## Slide 49: Design & Production Plan Detector Assembly and Integration
Detailed sharing of engineering design, FEA/simulations, review and fabrication discussed
Engineering resources at LANL/MIT/LBNL

## Slide 50: Stave and RU Production QA Plan Documents Available
Staves
Purchase 84 staves from ALICE/CERN
  48 + 28(spares for 2 inner layers) + 8 spares
  Production following the completion of ALICE ITS/IB
  Starting ~Oct. 2018, will last 6-12 months
  Fully tested at CERN before shipping to US
    All Gold/Silver staves (same as ALICE IB)
    A LANL postdoc (Dr. Yasser Morales) oversees production QA at CERN
Acceptance QA at LBNL
  Full test and QA
    Electrical
    Mechanical
  Detector assembly at LBNL
Readout Units
Purchase 60 RUs from ALICE/CERN
  48 + 12 spares(20%)
  To be part of ALICE production
    Cost saving
    Minimize technical risks
  Initial test at CERN
Acceptance QA at UT-Austin
  Full test
  LANL as the 2nd test site
https://indico.bnl.gov/event/4729/

## Slide 51: Stave Production and Shipping etc.
Hand carry staves from CERN to LBNL, 4 trips
Preliminary design from CERN for stave transportation plates
  To be produced at CERN, paid by LBNL/sPHENIX
Extended design from CERN
for MVTX
ALICE ITS IB

## Slide 52: MXTX Model with Correct Length Power Cables:
New shorter 40 cm overall length for power extension cables from stave, more than 220. mm shorter than was shown in previous model, same length service-barrel – 1200.0mm, location for a new patch panel 1B.
Updated inner layer power extension cable – overall length 40.0 cm, as agreed to by ALICE at CERN
Ross’s talk

## Slide 53: MVTX detector in sPHENIX
TPC volume, length 2,160.0 mm
INTT detector, 2 layers
MVTX detector with service cylinder
Support brackets for TPC and INTT

## Slide 54: Signal Cable Design
The Samtec twinax cables carry clock (40 MHz), control (40 Mbps bidirectional), data (9x1.2 Gbps)
ALICE is using halogen-free cables (32 AWG, LDPE dielectric) due to CERN LSZH requirement; 2.65 + 5.3 m cables have been tested and are now in production
Stave
Stave
RU
RU
From Sho

## Slide 55
Type-A
Type-B
Type-A

## Slide 56: Two HICs Produced and Tested at CERN w/ Extended Power Cables NO noticeable difference in sensor performance, as expected, 9/2018
MVTX: 40cm flex power PCB
MVTX: 60cm flex power PCB
ALICE IB: 15cm

## Slide 57: HICs Test Results from CERN (9/2018)
Before: 2 ALICE IB HICs
After: same ALICE HICs, replaced power FPCs
Noise level: ~4 e’s; Threshold: ~180e’s; MIP: ~1000 e’s
Chip-0
Chip-8
HIC1
HIC2
Noise
Noise
Thr.
Thr.

## Slide 58: FPC Extension for Connection to Electrical Services
FPC
DVDD
AGND
DGND
DVDD
DGND
DVDD
AVDD
AVDD
AVDD
AGND
AGND
DGND
The connection to the service cables is achieved by a double FPC extension which is soldered to the HIC
x-section at interconnection between FPC and extensions
signal lines (FPC)
analogue power
digital power
FPC
AVDD
AGND
AVDD
AGND
AGND
AVDD
Flex power extension
FPC
DVDD
DGND
DVDD
DVDD
DGND
DGND
Flex power extension
From Antonello Di Mauro
Modified for sPHENIX:
15cm -> 40cm

## Slide 59
2-layer flex, PI: 50 µm, Cu: 35 µm, solder mask: 20 µm
The two flexes are connected together, AVDD is transferred from top to bottom
The PWR extension is connected to the FPC by iron soldering and wings are cut.
FPC Extension for Connection to Electrical Services
digital
analogue
analogue
digital
digital
AVDD
DVDD
DGND
AGND
From Antonello Di Mauro
Longer copper traces ~30cm
for sPHENIX, no other components
Unchanged

## Slide 60: Stave
Production stave consists of three flex circuits: one signal FPC that carries the ALPIDE sensors, two power FPCs that carry AVDD and DVDD
For MVTX mechanical integration, the power FPCs must be lengthened to 40 cm (from 15 cm)
  We qualified 40 and 60 cm FPCs at CERN: identical performance
4 staves at LANL
MVTX stave modifications have been qualified, and we have our first 4 staves
60

## Slide 61: sPHENIX/MVTX IB Stave Assembly Procedure at CERN by ALICE ITS Group
Prepare sensors and FPC
Glue 9 sensors to FPC
Wire bonding 9 sensors to FPC
Solder power flex PCB to FPC
Glue HIC to coldplate/carbon space frame
A stave is ready for QA
CMM

## Slide 62: 2018 Fermilab Test Beam Highlights
INTT
MVTX EMCal HCal
Track spatial
resolution: ~5 um
High hit efficiency: > 99.5%
4-hit track
4-MAPS telescope
120 GeV protons
Sho’s talk
Demonstrated full high-speed readout chain at Fermilab test beam in Feb - Mar 2018
Sensors + RU + FELIX + RCDAQ/sPHENIX

## Slide 63: LANL LDRD Activity Highlights
Sensor source test
MAPS evaluation
Readout integration
4-sensor telescope
Test beam at Fermilab
Mechanical & cooling
Signal integrity & cables
Cooling system
prototype
Service cone R&D
FPC power extension R&D
4-ALPIDE Telescope;
5m-long SamTec cables
Readout R&D
stave
RU