## Slide 1: MVTX Status: WBS 3.02
Ming Liu
12/05/2019
sPHENIX L2 Meeting

## Slide 2: Budget Distribution – in Progress
Submitted updated MVTX PMP in November, 2019
  Incorporated some feedbacks from BNL Project Office (Maria)
BNL opens MVTX budget account this week
Paperwork preparation in progress @LANL, LBNL, MIT, UTA
  SOW, detailed budget sheet and cover letter from each institute
  Received updated P6 dump from Irina/Glenn this Monday, 12/2
  Produced detailed budget sheets for each institution, 12/3
    Follow the budget plan presented in July 2019 MVTX review
  To get paperwork ready by week

## Slide 3: System Integration: Carbon Structure & Readout
MVTX mechanical design review ~1/22/2020
  Excellent progress in mechanical system design
    CYSS, EW, SB
    Insertion system
Preparation for carbon structure pre-production
  Vendor selection for pre-production, early 2020
  PRR and final production, ~Spring 2020
A full load MVTX readout chain test: a 8-stave telescope
  8-stave + 8-RU + 1-FELIX + 1GTM/Fanout + 1PU + RCDAQ
  Update/sync MVTX firmware with the latest ALICE/FELIX development
  Test beam run being planned for ~late spring 2020, Fermilab (or LANL/LBNL)

## Slide 4: Stave Production at CERN
Good progress, on schedule
  10 HICs produced in November, ~10 more in December
  4 staves produced, all GOLD
Bi-weekly meeting with CERN
A sPHENIX Stave mounted on the Transport Plate

## Slide 5: HICs/Stave Production Status and Plan
Assembled HICs | HICs to be bonded | HICs NOK | HICs to be glued | STAVES OK | STAVES NOK
10 A201, A202, A203, A204, A205, A206, B201, B202, B203, B204 | 4 B201, B202, B203, B204 | 1 A202: broken chip due to glue seepage | 1 A206 | 4 A201(GOLD/OK), A203(GOLD/OK), A204(GOLD/CAN), A205(GOLD/CAN) | 0
Continue HIC production to create a stock of 10-12 modules in December, to be bonded later in 1/2020
First batch of ~ 20 STAVES could be ready by the end of March
LBNL obtained approval from ALICE/ITS to continue to use the same stave test stand for sPHENIX work

## Slide 6: Backup - Details

## Slide 7: Silicon sensors availability
Only “gold” chips are used for HIC assembly (i.e. < 50 dead pixels; ~<10^-4)
Remainder of ITS/IB production: all used
New partial delivery of 3 wafers (i.e. ~ 60 gold chips), end of November
Other two deliveries are expected in January and February, which will cover the entire sPHENIX production

## Slide 8: IB FPC production
Production plans: 132 FPC in total, in batches of 24 (IB yield ~ 80% -> 106 good FPCs)
Delivered series: A2, B2, C2, D2, F2, G2, H2
C2 used for IB, D2 NOK due to Al coating issues
Presently 10 have been used and 23 are available for assembly
Yield ~ 79%
Main production steps | place | duration
1. Upilex-S75 heat treatment in vacuum @ 400 oC for 2 h | CERN | 1 week
2. Holes drilling by laser, final FPC cutting | KIRANA (IT) | 1 week
3. Preparation for Al coating: cleaning, polishing | CERN | 1 week
4. Al PVD coating | HEF (F) | 2 weeks
5. LDI, etching, Ni/Au, coverlay, | CERN | 3 weeks
6. Cutting by Laser | KIRANA (IT) | 1 week
7. Inspection, test, SMD mounting (manual), metrology, cleaning, inspection | CERN | 3 weeks

## Slide 9: IB FPC production
FPC batch # | FPC ID | Delivery date | Status
10 | A201, .…, A206 | 02/09/2019 | A201, A202, A203, A204, A205, A206: used for assembly ;
 | B201, …., B206 | 09/07/2019 | B201, B202, B203, B204: used for assembly ; B205, B206: available
 | C201, …., C206 | 14/06/2019 | Used for IB
 | D201, …., D206 |  | NOK due to Al coating issues
11 | E201, …., E206 |  | E201 damaged during SMD; E202, …, E206: available
 | F201, …., F206 | 02/09/2019 | F203 damaged during SMD; F201, F202, F204, F205, F206: available
 | G201, …., G206 | 21/10/2019 | G201, …., G206: available
 | H201, …., H206 |  | H201 NOK due to scratch in Al layer; H202, …, H206: available
12 | I201, …, I206 |  | On hold for Ni/Au validation at Bondlab, expected to be available at the end of Jan, 2020
 | J201, …., J206 |  | On hold for Ni/Au validation at Bondlab, expected to be available at the end of Jan, 2020
 | K201, …., K206 |  | On hold for Ni/Au validation at Bondlab, expected to be available at the end of Jan, 2020
 | L201, …., L206 |  | On hold for Ni/Au validation at Bondlab, expected to be available at the end of Jan, 2020
13 | M201, …., M206 |  | Al PVD done, delivered next week
 | N201, …., N206 |  | Al PVD done, delivered next week
 | O201, …., O206 |  | Al PVD done, delivered next week
 | P201, …., P206 |  | Al PVD done, delivered next week

## Slide 10: IB FPC production
FPC batch # | FPC ID | Delivery date | Status
14 | Q201, .…, Q206 |  | Laser drilling done, in preparation for Al PVD, expected to be available in March 2020
 | R201, …., R206 |  | Laser drilling done, in preparation for Al PVD, expected to be available in March 2020
 | S201, …., S206 |  | Laser drilling done, in preparation for Al PVD, expected to be available in March 2020
 | T201, …., T206 |  | Laser drilling done, in preparation for Al PVD, expected to be available in March 2020
15 | U201, …., U206 |  | Laser drilling done, in preparation for Al PVD, expected to be available in April 2020
 | V201, …., V206 |  | Laser drilling done, in preparation for Al PVD, expected to be available in April 2020
 | W201, …., W206 |  | Laser drilling done, in preparation for Al PVD, expected to be available in April 2020
 | X201, …., X206 |  | Laser drilling done, in preparation for Al PVD, expected to be available in April 2020