## Slide 1: MVTX Status & Plan
Ming Liu
MVTX Bi-Weekly Meeting
03/13/2020

## Slide 2: Finalizing MVTX Mechanical Design
Address recommendations from 1/29/2020 FDR
  Added rollers to maintain the correct gap between the detector and the beam-pipe,
  modified one of the patch panels (for an easier access to cooling lines),
  FEA analysis confirmed sagging is small
    attaching the two North end flanges together to further reduce the overall sag of the detector (by ~x2)
  Talking with others (LBL) to decide on a simplified (shorter) vendor selection procedure
  Weekly mechanical design meeting, MIT/LANL, LBNL
Investigating a simplification compared to the ITS design
  Analysis seemed promising, and price with vendors was checked (looks ok so far)
  Internal ‘review’ with CERN (ITS lead engineer) and LBNL engineers, last Friday 3/6
  Plan to finalize the design and produce a prototype to certify the design and vendor

## Slide 3: MVTX 8-Stave Telescope Setup
Successfully readout the system
  2-stave + 2-HIC + 4-SingleChip, (4 staves will arrive next week with Alex)
  8-RUs + 1-PU + 1-FELIX + 1-GTM + CAEN PS
  11m long “final” readout cable
  Telescope box designed
Weekly readout meeting
  Firmware & software update
Test Beam @Fermilab, 4/22-5/4
  Coronavirus outbreak?
8-SingleChips
2 Staves
8 RUs + PU
4 “final” cables
CAEN PS
MVTX Telescope Box
6-stave + 2-HIC
2 HICs
Trigger scope
New cooling
panel for 8-stave

## Slide 4: Stave Production at CERN
Replacement of carbon frame cooling tubes starts this week, 3/9
HIC production in progress, 24 assembled as of 3/13
  Issues with software upgrade two weeks ago
  Rolled back to older version, system is working now
Production meeting with CERN next Thursday,
  Cooling tube work
  HICs & Stave testing
  ~10 staves available for shipping late March or early April
Cooling tubes:
55cm -> 70cm