## Slide 1: MVTX Status
Camelia, Grazyna, Ming
05/08/2020
MVTX Bi-Weekly Meeting
https://indico.bnl.gov/event/8464/

## Slide 2: Progress under COVID-19
MVTX funding distribution
  LANL, LBNL, MIT done
  UT-A in progress
CERN is opening slowly…
  first limited to essential CERN staff only May 18, possible full access for users ~mid September?
  Stave production – a planning meeting scheduled with CERN next Thursday 5/14
  RU test - on hold
MVTX mechanical structure design – in progress
  Prototypes are made
sPHENIX system integration – in progress
  Beam pipe
  Supporting racks, power, cooling etc.
Readout and slow control – in progress
  Firmware and software - RU done, working on FELIX
Detector simulations and Test Beam analysis – in progress
  Hit cluster distribution

## Slide 3: Where do we stand - PMP(12/2019)
Delays in FY-20:
Mechanical design & prototyping
  Final design review
Carbon structure fabrication
  Most facilities are closed due to COVID-19
Insertion system design, beam pipe
  Active discussions with BNL CAD and sPHENIX OSI
Power system
  Power boards fabrication – ready to order
  CAEN power – ready to order
  Cables – waiting for final layout for length
Stave production &RU test
  CERN schedule ?
  International shipping?
Today
5/8/20
Final design review -> late Fall 2020?