## Slide 1: MVXT Status and Plan
Camelia Mironov, Grazyna Odyniec, Ming Liu
MVTX Bi-Weekly Meeting
11/06/2020

## Slide 2: Project Status & Plan
Mechanical system
  Carbon fiber production at WorkShape (Fr.)
    1st test article by 11/2020, Layer-0 EW
    Complete full production in ~4/2021
    1st half detector available early, ~3/2021
  MVTX insertion and mockup designed, MIT/LANL
  Detector assembly fixture designed and reviewed
  1-piece EW: PEEK  Al
Readout and control
  Readout Unit Test in progress at ORNL
  FELIX AMD server setup in progress at LANL
  Slow control, LLA (Low-Level Arbitration) interface in progress
  mGTM development – draft doc circulated
Stave production and transportation
  37 Gold staves ready for shipping
  Still have problems with HIC assembly machine
  Transportation case tested, ready for 1st shipping 4 staves
FY21 funding expected ~Jan 2021
  Early funding request for ORNL and LANL, in progress
  Okey for MIT and LBNL for next a few months
MDC and MVTX detector & physics simulation
  Coming months
ITS commissioning remote shift participation
  Good opportunity to help us for MVTX commissioning later
Detector assemble fixture designed and reviewed - MIT, LANL, LBNL
1st prototype L0 EW fabricated,
next version in progress
Detector occupancy increase: ~<1%

## Slide 3: Challenges
Schedule delay due to COVID-19
  Carbon structure production and test/QA
    1st test article, Layer-0 EW, by end of Nov. 2020
    CF FDR ~Dec. 15, 2020
  Start full production ~ Jan. 2021
    1st half CF(EW+CYSS+SB) available in ~March 2021
    2nd half CF available in April
Stave production and transportation
  First test shipping, ~11/2020, 4 staves
  Stave QA @LBNL, follows
Half-detector assembly at LBNL
  CF and stave test fitting ~March 2021
  Half-detector assembly review, ~7/2021
  Complete the 2nd Half-detector by 12/2021
  Lab access at LBNL, schedule etc.
Tight schedule to meet the installation dates
Pre-COVID19 Schedule
Today
Assembly review

## Slide 4: Upcoming Reviews …
CF structure production readiness review ~ 12/15/2020
  CF structures - CYSS, EW and SB
  Detector assembly fixtures
  X-wing design
Insertion and mock up review ~ Jan 2021 ?
  Insertion design
  Insertion mockup
  w/ other subsystems, INTT, MBD, BP etc.

## Slide 5: backup

## Slide 6: Milestones in PMP, 12/2019 (targeted schedule + 2 months/contingency)
Now ~ 12/15/2020
CF structures:
- 1st half: 3/2021
- 2nd half: 4/2021
Assembly testing starts ~3/2021
Half-Detector assembly review, ~July 2021
On track … to meet the final completion milestones,
very tight schedule

## Slide 7
1-piece EW: to be replaced with Al,
to minimize “springb ack”
sPHENIX simulations:
PEEK, Al, AL7075