## Slide 1: MVTX Status
Camelia, Grazyna, Dave, Ming
04/24/2020
MVTX Bi-Weekly Meeting

## Slide 2: Impacts of COVID-19
MVTX Fund transfer – in progress
  LANL, LBNL, MIT (almost) done
  UT-A in progress
Stave production at CERN – on hold
  CERN is closed
60 RU boards test plan at CERN in May-July
  Need to revisit the testing plan
MVTX mechanical design – slow progress, limited access to computers & shops
  Finalizing designs
  Prototyping 2 new EndWheel pieces in progress
MVTX Fermilab Test Beam in May – canceled
  May consider TB later this year, @Fermilab or @LANL/LBNL
8-stave telescope development – slowed down, limited access to hardware
  Readout firmware/software updated
    Tested with 4-stave setup
  Mechanical support frame designed

## Slide 3: Schedules in PMP (12/2019)
Delays in FY-20:
Mechanical design, ~2 months?
Carbon structure fabrication, ?
  Most facilities are close due to COVID-19
Insertion system design, beam pipe
  Active discussions with BNL CAD and sPHENIX OSI
Power system
  Power boards fabrication
  CAEN power
  Cables
Stave production & test
  CERN schedule?
  International transportation?
4/1/20
Today

## Slide 4: Milestones in PMP (12/2019)
Milestone | Date
Project Start | December 2019
Power Board Prod. Contract Awards | January 2020
Preliminary Design of the sPHENIX Interface | February 2020
End Wheel & CYSS Design Complete | March 2020
Start Test and Rework Staves – Batch 1 | April 2020
Service Barrel Design Complete | May 2020
MVTX Final Design Review | July 2020
Complete End-Wheels Fabrication | October 2020
Complete CYSS Fabrication | November 2020
Complete SB Fabrication | December 2020
Support Structures Contract Awards | January 2021
Test Installation of Staves onto End-Wheels | March 2021
Half-Detector Assembly Review | May 2021
Perform Half-Detector Metrology on Layers | July 2021
Assemble Layers and CYSS into Half-Barrel #1 | August 2021
Assemble Layers and CYSS into Half-Barrel #2 | September 2021
Test and Rework Half-Barrel #1 | October 2021
1st Half Barrels Assembled | December 2021
2nd Half Barrels Assembled | January 2022
Test Half Barrels at BNL | March 2022
MVTX ready for Installation | May 2022
Approve Project Complete | May 2023
Major responsible institutions:
LBNL;
MIT/LANL;
Final Design Review  Fall 2020?