## Slide 1: MVTX Status and Plan
Camelia, Grazyna and Ming
11/20/2020
MVTX bi-Weekly Meeting

## Slide 2: Project Status
Mechanical system
  1st test article produced at WorkShape!
  Insertion system design and mockup in progress, MIT/LANL
Electrical system integration
  RU testing in progress at ORNL
  AMD server made progress at LANL
  Power system and cable layout, LBNL
  Slow control, MIT
Stave production and transportation
  37+ gold staves at CERN, meeting next week(?)
  4 staves arrived at LBNL safely
MDC and physics study
  Next ~3+ months
FY21 budget
  ORNL’s budget being process at BNL
  Didn’t receive detailed FY21 budget, under discussion
ITS commissioning remote shifts
  A few openings available
A lots of cables ….
ITS/IB readout and power
End Wheel: L0
@WorkShape
4 staves from CERN

## Slide 3: Upcoming Challenges
Mechanical support structures
  CF production and QA
    1st test article, Layer-0 EW CMM etc.
    CF FDR: Dec. 15, 2020
  CF full production starts ~ Jan. 2021
    1st half CF(EW+CYSS+SB) available in ~March 2021
    2nd half CF available in April
  Insertion system design & mockup
    System integration review: ~Jan 2021
Stave production and transportation
  Shipping and QA, to be ready for assembly in time
Half-detector assembly at LBNL
  CF and stave test fitting ~March 2021
  Half-detector assembly review, ~May 2021
  Complete the 2nd Half-detector by 12/2021
Power, readout and controls
  Half-detector readout and control at LBNL, ~summer 2021
Tight schedule to meet the installation dates
Pre-COVID19 Schedule
Today
Assembly review