## Slide 1: MVTX Status
Camelia, Grazyna, and Ming
08/16/2021

## Slide 2: MVTX Assembly Review: Sept. 9-10th @LBNL
Planned originally for Aug 18-19th
  rescheduled because of COVID travel policy (many approvals, including DOE)
Half-detector assembly will start only after the review
  Still aim to finish assembly and be ready for shipping to BNL in the first months of 2022
Draft review agenda page:https://indico.bnl.gov/event/12699/
Time zone: MDT

## Slide 3: MVTX detector construction
All Carbon Fiber parts: delivered to LBNL
Fixtures for Layer-0 assembly: at LBNL
  test fitting in progress with mock-up components
  Assessing in parallel if any change to fixture is needed
Stave shipping & QA: in progress
  10 staves received last week, under testing
  Next shipment: 20 staves
Signal and power cable production:
  long lead time (8~12 weeks?)
  Fix the length ASAP, using final detector pieces
L2
L1
L0
CYSS
ServiceBarrel
Fixture

## Slide 4: Electrical system
VTRx baking: in progress at ORNL
  85C, 500hrs, 2 batches
mGTM integration and trigger framing: in progress, ~40MHz (160MHz)
  FDAQ output looks okey
  RCDAQ integration in progress, working on busy/interrupt integration
DCS and Detector Safety system: finished design
  WinCC and PLCs, procurement in progress
  DCS Software ported from ITS and successfully tested in hardware
CAEN power system: test in progress at LBNL
Cable and fiber routing plans: completed, under review
  Full fiber fanout test planned later this summer

## Slide 5: Near Term Tasks Critical (potential delays)
MVTX half-detector assembly review
  Half-detector assembly
  Stave QA
MVTX insertion system mockup
  To clear interference, MVXT support/INTT
Cooling system test
  Stave cooling @ MIT
  Electrics cooling @LANL
New GTM integration
DCS integration, online monitoring
MVTX alignment & MDC-2
  Prepare for commissioning
Signal+power cable fabrication
Re-designing anything (following review, or mock-ups results)
Insertion
@MIT/Bates
INTT + MVTX/X-Wing
mockup @BNL

## Slide 6: Backup slides

## Slide 7: MVTX: other activities
Cooling circuits (PID): working on mock-up
  Design finished for both racks (LANL) and detector (Bates)
  Need to buy components for mock-up/cooling test
    Some parts bought: Chilldyne units
    Some delayed: waiting for fab account to be brought up in MIT (BNL money arrived)
Support and insertion: working on mock-up
  Rails, ‘hands’, base plate w/ load cells, sliding mechanism, special table: all in Bates
  Missing components:
    X-wing (support structure) -- huge delays at the shop
    INTT ROC + cables: Dan is preparing the shipment