## Slide 1: MVTX Status
Camelia, Grazyna, Ming
02/26/2021

## Slide 2: Mechanical Structures
CFC production on schedule
  1st full-half detector to LBNL ~end of March
Finalizing assembly jig design, w/ LBNL last week
  Build 3 set assembly jigs first + 3 cradles …
MVTX insertion system design in progress
  => finalize cable lengths, readout and power
PP1/2 design updated
  Reducing data and power cable shift/twist

## Slide 3: Readout and Electrical System
All 60 production RU tested
  3 arrived at factory for repair
  Spare components
mGTM development in progress
  Preliminary design developed, good discussion this week, 80MHz or 160MHz options
  1st prototype mGTM available in ~3 weeks
AMD server integration
  Testing new RU firmware in progress
  New data format
Power system, racks, cables etc
  ESR dry run with BNL engineers last week, received good suggestions
Detector Safety System kickoff meeting between BNL and Michael next week
Budget update for FY21:
Spare electronics components
  VTTx/VTRx ~ $12k.
Miscellaneous items:
  VME crates (~$6K), 4 fanout boards($10k?), patch panels, CANBUS cables, fibers etc.
  Safety system -> MVTX + WBS2.x
mGTM simulation from Joe Mead
sPHENIX PB Test – unstable I2C signal?
IB/Switch

## Slide 4: Stave Production, Transportation and QA
50 gold staves ready for shipping
  16 new HICs produced
    11 staves under test
  7 staves done metrology
  Production rate: ~5 HICs/week
4 (3 Gold + 1 Silver) under test at LBNL
  Mostly consistent with CERN data
  Some details under investigation
1 partially working HIC for ORNL
  Arrived with new loggers at LBNL
  Tested at LBNL
  To be tested at LANL before shipping to ORNL
New Logger MSR 175: Feb. 5 – 16, 2021. CERN LBNL
Shock

## Slide 5: Near Term Plan
Mechanical structures
  Continue CFC production at WorkShape
    Produce low-cost “evil-twin” at the end of production
  Finished X-wing design, fabrication
    Build full mockup, w/ beam pipe @MIT
  Finish assembly fixtures
Stave shipping & QA
  Prepare for detector assembly
Readout and control integration
  AMD server
  mGTM
  Slow control
  Update FW and SW
MVTX detector safety system
  Interface to sPHENIX safety system
Experimental Safety Review
  power cables etc.
Power system & Cooling system
  system tests and procurements
Budget update -> more engineering support in FY21
LBNL, add “setup clean room”, ~$20k, (need to double check)
MIT, TBD, in progress -> finish X-wing +insertion system, assembly fixtures, cooling sytem, extra evil MVTX (for insertion dry testing in BNL), etc. (might need extra 200-250K from P6, + ~50K WBS2x
Test fit: Mar-April, 2021
Detector assembly Review: ~May 2021
Readout & Test @LBNL:
full or partial detector?
1, 6/L0, 8/L1, 10/L2

## Slide 6: backup

## Slide 7
* Partial/Not functioning
7 new STAVEs with metrology tests.
50 STAVES are ready to deliver.
4 STAVEs are delivered.
 | STAVE-production summary table |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IBSTAVE ID | HIC assembly | HIC assembly date | Ins. after glue | Bonding | Pull test (>=2 lifts + F <7g) | Ins. after bonding | HIC PWR test | Qualification test | Threshold cluster | HIC Matrix | HIC DTU | HIC DTU (new) | HIC+SF+C -> Stave | Stave PWR test | Stave test | STAVE test date | STAVE metrology | Stave PWR test (long PWR extn.) | STAVE final test (PT100) | Final STAVE Matrix | Final STAVE DTU | STAVE Deliverd
TOTAL | 94 |  | 94 | 92 |  | 91 | 88 | 74 |  |  |  |  | 66 | 65 | 65 |  | 61 | 54 | 54 |  |  | 4
A201 (326) | 1 | 03/10/2019 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 01/11/2019 | 1 | 1 | 1 | GOLD | OK | 1
A202* | 1 | 07/10/2019 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
A203 (144) | 1 | 08/10/2019 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 04/11/2019 | 1 | 1 | 1 | GOLD | OK | 1
A204 (158) | 1 | 22/10/2019 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 07/11/2019 | 1 | 1 | 1 | GOLD | OK | 1
A205 (167) | 1 | 23/10/2019 | 1 | 1 | 4 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 08/11/2019 | 1 | 1 | 1 | GOLD | OK | 
A206 (204) | 1 | 30/10/2019 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | GOLD | CAN | CAN | 1 | 1 | 1 | 24/01/2020 | 1 | 1 | 1 | GOLD | CAN | 
B201 (352) | 1 | 30/10/2019 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 28/05/2020 | 1 | 1 | 1 | GOLD | OK | 
B202* | 1 | 31/10/2019 | 1 | 1 | 0 | 1 | 1 | 0 |  | Broken |  |  |  |  |  |  |  |  |  |  |  | 
B203 (114) | 1 | 07/11/2019 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 29/05/2020 | 1 | 1 | 1 | GOLD | CAN | 
B204 (116) | 1 | 13/11/2019 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | SILVER | CAN | CAN | 1 | 1 | 1 | 28/05/2020 | 1 | 1 | 1 | SILVER | CAN | 1
B205 (115) | 1 | 14/01/2020 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 02/06/2020 | 1 | 1 | 1 | GOLD | OK | 
B206 (295) | 1 | 15/01/2020 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 02/06/2020 | 1 | 1 | 1 | GOLD | OK | 
F201* | 1 | 27/02/2020 | 1 | 1 | 1 | 1 | 1 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
F202 (230) | 1 | 28/02/2020 | 1 | 1 | 3 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 04/06/2020 | 1 | 1 | 1 | GOLD | CAN | 
F204 | 1 | 29/02/2020 | 1 | 1 | 5 | 1 | 1 | 1 | 2 | GOLD | CAN | OK |  |  |  |  |  |  |  |  |  | 
G202 (234) | 1 | 10/02/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 04/06/2020 | 1 | 1 | 1 | GOLD | OK | 
G203 | 1 | 12/02/2020 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN |  |  |  |  |  |  |  |  |  | 
F203* | dummy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H202 (294) | 1 | 24/02/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 05/06/2020 | 1 | 1 | 1 | GOLD | OK | 
H203 (302) | 1 | 26/02/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 05/06/2020 | 1 | 1 | 1 | GOLD | OK | 
H204 (354) | 1 | 27/02/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 11/06/2020 | 1 | 1 | 1 | GOLD | OK | 
H206* | 1 | 04/03/2020 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
E204 (110) | 1 | 05/03/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 22/06/2020 | 1 | 1 | 1 | GOLD | CAN | 
E201* | 1 | 12/02/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 3 | PARTIAL | CAN | OK |  |  |  |  |  |  |  |  |  | 
E202 | 1 | 10/03/2020 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | CAN (bad driver) | CAN (bad driver) |  |  |  |  |  |  |  |  |  | 
E206 (101) | 1 | 12/03/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 16/06/2020 | 1 | 1 | 1 | GOLD | OK | 
H205 | 1 | 11/06/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | SILVER | OK | OK |  |  |  |  |  |  |  |  |  | 
I202 (175) | 1 | 15/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 22/06/2020 | 1 | 1 | 1 | GOLD | OK | 
I203 (187) | 1 | 16/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 26/06/2020 | 1 | 1 | 1 | GOLD | OK | 
I204* | 1 | 17/06/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
I205 (266) | 1 | 22/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 26/06/2020 | 1 | 1 | 1 | GOLD | OK | 
J201* | 1 | 23/06/2020 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
J202 (207) | 1 | 24/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 16/07/2020 | 1 | 1 | 1 | GOLD | CAN | 
J203 (245) 345 right | 1 | 29/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 17/07/2020 | 1 | 1 | 1 | GOLD | CAN | 
J204 (252) | 1 | 30/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 03/07/2020 | 1 | 1 | 1 | GOLD | OK | 
J206 (260) | 1 | 01/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 03/07/2020 | 1 | 1 | 1 | GOLD | OK | 
K202 (122) | 1 | 07/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 18/08/2020 | 1 | 1 | 1 | GOLD | OK | 
K203 (125) | 1 | 08/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 18/08/2020 | 1 | 1 | 1 | GOLD | OK | 
K204 (129) | 1 | 09/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 04/09/2020 | 1 | 1 | 1 | GOLD | OK | 
K205 (128) | 1 | 13/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 04/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
K206 (347) | 1 | 14/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 28/09/2020 | 1 | 1 | 1 | GOLD | OK | 
L202 (130) | 1 | 23/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 08/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
L203 (139) | 1 | 24/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 08/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
L204 (127) | 1 | 27/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 14/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
L205 (136) | 1 | 28/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 14/09/2020 | 1 | 1 | 1 | GOLD | OK | 
J205* | 1 | 05/08/2020 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | CAN | CAN |  |  |  |  |  |  |  |  |  | 
I201* | 1 | 06/08/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
L206* | 1 | 13/08/2020 | 1 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
L201 (169) | 1 | 14/08/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 30/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
Stave production meeting
2/18/2021, from Rajendra

## Slide 8
IBSTAVE ID | HIC assembly | HIC assembly date | Ins. after glue | Bonding | Pull test (>=2 lifts + F <7g) | Ins. after bonding | HIC PWR test | Qualification test | Threshold cluster | HIC Matrix | HIC DTU | HIC DTU (new) | HIC+SF+C -> Stave | Stave PWR test | Stave test | STAVE test date | STAVE metrology | Stave PWR test (long PWR extn.) | STAVE final test (PT100) | Final STAVE Matrix | Final STAVE DTU | STAVE Deliverd
S201 (359) | 1 | 03/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 30/09/2020 | 1 | 1 | 1 | GOLD | OK | 
S202 | 1 | 04/09/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | SILVER | CAN | CAN |  |  |  |  |  |  |  |  |  | 
S203 (235) | 1 | 08/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 16/11/2020 | 1 | 1 | 1 | GOLD | OK | 
S204 (237) | 1 | 15/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 30/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
S205 (142) | 1 | 16/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 01/10/2020 | 1 | 1 | 1 | GOLD | CAN | 
S206 (98) | 1 | 17/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 02/10/2020 | 1 | 1 | 1 | GOLD | OK | 
T201 (277) | 1 | 04/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 17/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
T202 (279) | 1 | 06/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | GOLD | CAN | CAN | 1 | 1 | 1 | 19/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
T203 | 1 | 09/11/2020 | 1 | 1 | 0 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
U201 (291) | 1 | 10/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | SILVER | CAN | CAN | 1 | 1 | 1 | 24/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
U202 (238) | 1 | 11/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 26/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
U203 (126) | 1 | 12/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 20/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
U204* | 1 | 13/11/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
U205 (89) | 1 | 16/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 27/11/2020 | 1 | 1 | 1 | GOLD | OK | 
U206 (111) | 1 | 17/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 25/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
Q201 (155) | 1 | 18/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | SILVER | CAN | CAN | 1 | 1 | 1 | 27/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
Q202 (140) | 1 | 19/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 03/12/2020 | 1 | 1 | 1 | GOLD | CAN | 
T204 (107) | 1 | 23/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 03/12/2020 | 1 | 1 | 1 | GOLD | CAN | 
T205 (168) | 1 | 24/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 03/12/2020 | 1 | 1 | 1 | GOLD | OK | 
T206 (232) | 1 | 25/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 14/01/2021 | 1 |  |  |  |  | 
R201 (119) | 1 | 27/11/2020 | 1 | 1 | 8 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 08/12/2020 | 1 | 1 | 1 | GOLD | CAN | 
R202 (109) | 1 | 30/11/2020 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 17/12/2020 | 1 | 1 | 1 | GOLD | CAN | 
W201 (52) | 1 | 01/12/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | data line broken |  |  |  |  |  |  |  |  | 
W202* | 1 | 02/12/2020 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | CAN | CAN |  |  |  |  |  |  |  |  |  | 
W203 (212) | 1 | 03/12/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | SILVER | CAN | CAN | 1 | 1 | 1 | 05/01/2021 | 1 | 1 | 1 | SILVER | OK | 
W204 (271) | 1 | 07/12/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 3 | GOLD | OK | OK | 1 | 1 | 1 | 05/01/2021 | 1 | 1 | 1 | GOLD | OK | 
W205 (275) | 1 | 08/12/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 18/01/2021 | 1 |  |  |  |  | 
W206 | 1 | 09/12/2020 | 1 | 1 | 0 | 1 | ?? Digi short |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R203 (322) | 1 | 06/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 20/01/2021 |  |  |  |  |  | 
R204* | 1 | 11/01/2021 | 1 | 1 | 0 | 1 | 0 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
Q203* | 1 | 12/01/2021 | 1 | 1 | 0 | 1 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
X201 (102) | 1 | 13/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 21/01/2021 | 1 |  |  |  |  | 
X202 (209) | 1 | 14/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 27/01/2021 | 1 |  |  |  |  | 
X204 (239) | 1 | 18/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 27/01/2021 | 1 |  |  |  |  | 
X205 (269) | 1 | 19/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 28/01/2021 | 1 |  |  |  |  | 
X206 (296) | 1 | 21/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 28/01/2021 | 1 |  |  |  |  | 
P202 | 1 | 22/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN |  |  |  |  |  |  |  |  |  | 
P203 | 1 | 25/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN |  |  |  |  |  |  |  |  |  | 
O201 (357) | 1 | 26/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 11/02/2021 |  |  |  |  |  | 
O203 (292) | 1 | 27/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 11/02/2021 |  |  |  |  |  | 
O204 (100) | 1 | 28/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 16/02/2021 |  |  |  |  |  | 
O205 (351) | 1 | 29/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 |  |  |  |  |  |  |  |  | 
P204 | 1 | 10/02/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK |  |  |  |  |  |  |  |  |  | 
B301 | 1 | 11/02/2021 | 1 | 1 | 0 | 1 | 1 | 1 |  | SILVER | OK | OK |  |  |  |  |  |  |  |  |  | 
B303 | 1 | 12/02/2021 | 1 | 1 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B304 | 1 | 15/02/2021 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B305 | 1 | 16/02/2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 9: Status & Plan
Pre-COVID19 Schedule
Today
Assembly review
Some delay in CFC production,
but still on track for completing
the assembly work in 2021
Readout, Control and Electrical System Integration
3 RUs sent to factory@UK for repair
FW/SW synced to latest ALICE/ATLAS code
Low-level slow control under testing
mGTM progress at BNL (40MHz/LHC)
Readout and service cables and power system
production started
@LBNL
MVTX
installation
~9/2022