## Slide 1: MVTX Status
Camelia, Grazyna, Ming
02/12/2021
sPHENIX L2 Project Meeting

## Slide 2: Mechanical Structures & Integration
CFC production on schedule
  A new all carbon Lay-0 EW, to replace the test article
    In kind contribution from WorkShape
  Complete in 3rd week of March
X-Wing design near completion
  PP3 optimization (3D print)
  => finalize cable lengths, for readout and power
Finalizing assembly jig design
  meeting with LBNL next week
PP1/2 designs updated, confirmed w/ 3-D mockups
  Improve cable passthrough, locking
Budget update -> more engineering support
LANL, add 0.3FTE on MVTX + WBS2.x, ~$150k
LBNL, add “setup clean room”, ~$20k
MIT, in progress
-> finish X-wing+insertion system, assembly fixtures, cooling system, extra lower cost
“Evil MVTX CYSS/SB” (for insertion dry run in BNL, WBS2.x scope), etc.
-> might need extra 200-250K from P6, and +~50K WBS2x
Detector Assembly Jig
X-Wing

## Slide 3: Readout and Electrical System
All 60 production RU tested
  3 sent to factory for repair
  spare components procurements
    mezzanine cards ordered
    VTRx/VTTx under discussion, repurpose UT-A RU-test travel fund?
Detector safety system proposed – (T, V, I )
  Modify from ALICE “ITS2S”
mGTM development in progress
  Preliminary design available for testing ~next week?
Readout in progress
  New data format and latest firmware
  mGTM and FELIX interface
AMD server integration in progress
  Slow control communication ok
  DMA data transfer ok
Power system, racks, cables etc
Budget update for FY21:
Spare components
  RU mezzanine cards ordered (<$10K)
  VTTx/VTRx ~ $12k, try to repurpose RU test travel $ (UT-A) to small item purchase?
Miscellaneous items:
  VME crates (~$6K), 4 fanout boards($10k?), patch panels, CANBUS cables, optical fibers etc.
  Safety system -> MVTX + WBS2.x

## Slide 4: Stave Production, Transportation and QA
48 + spares Gold staves produced
  6 new staves finished metrology (as of 1/20/2021)
  Production rate: 4~5 HICs/week
4 (3 Gold + 1 Silver) under test at LBNL
  Mostly consistent with CERN data
  Some details under investigation
One more test shipping this week
  1 HIC, several monitoring loggers
Next Meeting with CERN @2/18
one HIC on the way to LBNL,
Double check transportation loggers
Budget: no change
Power board calibration and stave QA @LBNL
DVDD, AVDD
FPC power cable resistance values

## Slide 5: Near Term Plan
Mechanical structures
  Continue CFC production at WorkShape
    Produce low-cost “evil-twin” at the end of production
  Finished X-wing design, fabrication
    Mockup
  Finish assembly fixtures
Stave shipping & QA
  Prepare for detector assembly
Readout and control
  AMD full integration
  mGTM integration
  Slow Control
MVTX detector safety system
  Interface to sPHENIX safety system
Experimental Safety Review
  power cables etc.
Power system & Cooling system
  system tests and procurements
- Test fit in Mar-April
- Assembly review, ~May 2021
Complete assembly 12/2021

## Slide 6: Status & Plan
Pre-COVID19 Schedule
Today
Assembly review
Some delay in CFC production,
but still on track for completing
the assembly work in 2021
Readout, Control and Electrical System Integration
3 RUs sent to factory@UK for repair
FW/SW synced to latest ALICE/ATLAS code
Low-level slow control under testing
mGTM progress at BNL (40MHz/LHC)
Readout and service cables and power system
Production in progress
@LBNL
MVTX
installation
~9/2022

## Slide 7
* Partial/Not functioning
 | STAVE-production summary table |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IBSTAVE ID | HIC assembly | HIC assembly date | Ins. after glue | Bonding | Pull test (>=2 lifts + F <7g) | Ins. after bonding | HIC PWR test | Qualification test | Threshold cluster | HIC Matrix | HIC DTU | HIC DTU (new) | HIC+SF+C -> Stave | Stave PWR test | Stave test | STAVE test date | STAVE metrology | Stave PWR test (long PWR extn.) | STAVE final test (PT100) | Final STAVE Matrix | Final STAVE DTU | STAVE Deliverd
TOTAL | 83 |  | 83 | 80 |  | 80 | 76 | 62 |  |  |  |  | 58 | 57 | 57 |  | 49 | 49 | 49 |  |  | 4
A201 (326) | 1 | 03/10/2019 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 01/11/2019 | 1 | 1 | 1 | GOLD | OK | 1
A202* | 1 | 07/10/2019 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
A203 (144) | 1 | 08/10/2019 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 04/11/2019 | 1 | 1 | 1 | GOLD | OK | 1
A204 (158) | 1 | 22/10/2019 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 07/11/2019 | 1 | 1 | 1 | GOLD | OK | 1
A205 (167) | 1 | 23/10/2019 | 1 | 1 | 4 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 08/11/2019 | 1 | 1 | 1 | GOLD | OK | 
A206 (204) | 1 | 30/10/2019 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | GOLD | CAN | CAN | 1 | 1 | 1 | 24/01/2020 | 1 | 1 | 1 | GOLD | CAN | 
B201 (352) | 1 | 30/10/2019 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 28/05/2020 | 1 | 1 | 1 | GOLD | OK | 
B202* | 1 | 31/10/2019 | 1 | 1 | 0 | 1 | 1 | 0 |  | Broken |  |  |  |  |  |  |  |  |  |  |  | 
B203 (114) | 1 | 07/11/2019 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 29/05/2020 | 1 | 1 | 1 | GOLD | CAN | 
B204 (116) | 1 | 13/11/2019 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | SILVER | CAN | CAN | 1 | 1 | 1 | 28/05/2020 | 1 | 1 | 1 | SILVER | CAN | 1
B205 (115) | 1 | 14/01/2020 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 02/06/2020 | 1 | 1 | 1 | GOLD | OK | 
B206 (295) | 1 | 15/01/2020 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 02/06/2020 | 1 | 1 | 1 | GOLD | OK | 
F201* | 1 | 27/02/2020 | 1 | 1 | 1 | 1 | 1 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
F202 (230) | 1 | 28/02/2020 | 1 | 1 | 3 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 04/06/2020 | 1 | 1 | 1 | GOLD | CAN | 
F204 | 1 | 29/02/2020 | 1 | 1 | 5 | 1 | 1 | 1 | 2 | GOLD | CAN | OK |  |  |  |  |  |  |  |  |  | 
G202 (234) | 1 | 10/02/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 04/06/2020 | 1 | 1 | 1 | GOLD | OK | 
G203 | 1 | 12/02/2020 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN |  |  |  |  |  |  |  |  |  | 
F203* | dummy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H202 (294) | 1 | 24/02/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 05/06/2020 | 1 | 1 | 1 | GOLD | OK | 
H203 (302) | 1 | 26/02/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 05/06/2020 | 1 | 1 | 1 | GOLD | OK | 
H204 (354) | 1 | 27/02/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 11/06/2020 | 1 | 1 | 1 | GOLD | OK | 
H206* | 1 | 04/03/2020 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
E204 (110) | 1 | 05/03/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 22/06/2020 | 1 | 1 | 1 | GOLD | CAN | 
E201* | 1 | 12/02/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 3 | PARTIAL | CAN | OK |  |  |  |  |  |  |  |  |  | 
E202 | 1 | 10/03/2020 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | CAN (bad driver) | CAN (bad driver) |  |  |  |  |  |  |  |  |  | 
E206 (101) | 1 | 12/03/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 16/06/2020 | 1 | 1 | 1 | GOLD | OK | 
H205 | 1 | 11/06/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | SILVER | OK | OK |  |  |  |  |  |  |  |  |  | 
I202 (175) | 1 | 15/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 22/06/2020 | 1 | 1 | 1 | GOLD | OK | 
I203 (187) | 1 | 16/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 26/06/2020 | 1 | 1 | 1 | GOLD | OK | 
I204* | 1 | 17/06/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
I205 (266) | 1 | 22/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 26/06/2020 | 1 | 1 | 1 | GOLD | OK | 
J201* | 1 | 23/06/2020 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
J202 (207) | 1 | 24/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 16/07/2020 | 1 | 1 | 1 | GOLD | CAN | 
J203 (245) 345 right | 1 | 29/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 17/07/2020 | 1 | 1 | 1 | GOLD | CAN | 
J204 (252) | 1 | 30/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 03/07/2020 | 1 | 1 | 1 | GOLD | OK | 
J206 (260) | 1 | 01/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 03/07/2020 | 1 | 1 | 1 | GOLD | OK | 
K202 (122) | 1 | 07/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 18/08/2020 | 1 | 1 | 1 | GOLD | OK | 
K203 (125) | 1 | 08/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 18/08/2020 | 1 | 1 | 1 | GOLD | OK | 
K204 (129) | 1 | 09/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 04/09/2020 | 1 | 1 | 1 | GOLD | OK | 
K205 (128) | 1 | 13/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 04/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
K206 (347) | 1 | 14/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 28/09/2020 | 1 | 1 | 1 | GOLD | OK | 
Stave Production meeting
with CERN, 1/19/2021
6 new stave metrology done

## Slide 8
 | STAVE-production summary table |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IBSTAVE ID | HIC assembly | HIC assembly date | Ins. after glue | Bonding | Pull test (>=2 lifts + F <7g) | Ins. after bonding | HIC PWR test | Qualification test | Threshold cluster | HIC Matrix | HIC DTU | HIC DTU (new) | HIC+SF+C -> Stave | Stave PWR test | Stave test | STAVE test date | STAVE metrology | Stave PWR test (long PWR extn.) | STAVE final test (PT100) | Final STAVE Matrix | Final STAVE DTU | STAVE Deliverd
L202 (130) | 1 | 23/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 08/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
L203 (139) | 1 | 24/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 08/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
L204 (127) | 1 | 27/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 14/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
L205 (136) | 1 | 28/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 14/09/2020 | 1 | 1 | 1 | GOLD | OK | 
J205* | 1 | 05/08/2020 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | CAN | CAN |  |  |  |  |  |  |  |  |  | 
I201* | 1 | 06/08/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
L206* | 1 | 13/08/2020 | 1 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
L201 (169) | 1 | 14/08/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 30/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
S201 (359) | 1 | 03/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 30/09/2020 | 1 | 1 | 1 | GOLD | OK | 
S202 | 1 | 04/09/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | SILVER | CAN | CAN |  |  |  |  |  |  |  |  |  | 
S203 (235) | 1 | 08/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 16/11/2020 | 1 | 1 | 1 | GOLD | OK | 
S204 (237) | 1 | 15/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 30/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
S205 (142) | 1 | 16/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 01/10/2020 | 1 | 1 | 1 | GOLD | CAN | 
S206 (98) | 1 | 17/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 02/10/2020 | 1 | 1 | 1 | GOLD | OK | 
T201 (277) | 1 | 04/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 17/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
T202 (279) | 1 | 06/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | GOLD | CAN | CAN | 1 | 1 | 1 | 19/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
T203 | 1 | 09/11/2020 | 1 | 1 | 0 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
U201 (291) | 1 | 10/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | SILVER | CAN | CAN | 1 | 1 | 1 | 24/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
U202 (238) | 1 | 11/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 26/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
U203 (126) | 1 | 12/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 20/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
U204* | 1 | 13/11/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
U205 (89) | 1 | 16/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 27/11/2020 | 1 | 1 | 1 | GOLD | OK | 
U206 (111) | 1 | 17/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 25/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
Q201 (155) | 1 | 18/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | SILVER | CAN | CAN | 1 | 1 | 1 | 27/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
Q202 | 1 | 19/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 03/12/2020 | 1 | 1 | 1 | GOLD | CAN | 
T204 | 1 | 23/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 03/12/2020 | 1 | 1 | 1 | GOLD | CAN | 
T205 | 1 | 24/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 03/12/2020 |  |  |  |  |  | 
T206 (232) | 1 | 25/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 14/01/2021 |  |  |  |  |  | 
R201 (119) | 1 | 27/11/2020 | 1 | 1 | 8 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 08/12/2020 |  |  |  |  |  | 
R202 (109) | 1 | 30/11/2020 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 17/12/2020 |  |  |  |  |  | 
W201 (52) | 1 | 01/12/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | ?? data line broken |  |  |  |  |  |  |  |  | 
W202* | 1 | 02/12/2020 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | CAN | CAN |  |  |  |  |  |  |  |  |  | 
W203 (212) | 1 | 03/12/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | SILVER | CAN | CAN | 1 | 1 | 1 | 05/01/2021 |  |  |  |  |  | 
W204 (271) | 1 | 07/12/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 3 | GOLD | OK | OK | 1 | 1 | 1 | 05/01/2021 |  |  |  |  |  | 
W205 (275) | 1 | 08/12/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 18/01/2021 |  |  |  |  |  | 
W206 | 1 | 09/12/2020 | 1 | 1 | 0 | 1 | ?? Digi short |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R203 | 1 | 06/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 20/01/2021 |  |  |  |  |  | 
R204 | 1 | 11/01/2021 | 1 | 1 | 0 | 1 | 0 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
Q203 | 1 | 12/01/2021 | 1 | 1 | 0 | 1 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
X201 | 1 | 13/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 |  |  |  |  |  |  |  |  | 
X202 | 1 | 14/01/2021 | 1 | 1 | 0 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
X204 | 1 | 18/01/2021 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
X205 | 1 | 19/01/2021 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
From last stave Production
meeting with CERN, 1/19/2021