## Slide 1
MVTX Status
Ming Liu for the MVTX Group
sPHENIX Collaboration Meeting (Online)
January 21-22, 2021
https://indico.bnl.gov/event/10568/
MVTX + INTT
X-Wing
From Dan Cacace

## Slide 2: Outline
MVTX detector introduction
Readout and control
Mechanical system
Detector assembly
Stave production, shipping and QA
Services: power and cooling system

## Slide 3: MVTX Detector
3-layer sensor barrel:
- pixel size: 27 x 29 um
- stave thickness: 0.35%X0
- Timing resolution: 5us
- 48 staves, 27.1cm long
MVTX beam view
7/6/20
MVTX Status @sPHENIX Collaboration Meeting
Excellent track DCA resolutions in pp, pAu and AuAu

## Slide 4: Track DCA Resolutions: to True Collision VTX
10um
DCA_XY
DCA_Z
25um
Joe Osborn
MDC-1
Latest work in progress …

## Slide 5: Status & Plan
Pre-COVID19 Schedule
Today
Assembly review
Some delay in CFC production,
but still on track for completing
the assembly work in 2021
Readout, Control and Electrical System Integration
60 RU 1st round test completed
FW/SW synced to latest ALICE/ATLAS code
Low-level slow control under testing
mGTM in progress at BNL (40MHz/LHC)
Readout and service cables and power system
production started
@LBNL
MVTX
installation
~9/2022

## Slide 6
48th Gold Stave Produced at CERN in 12/2020!
(One full MVTX detector)

## Slide 7: MVTX Readout, Power and Controls Overview
Power Board
Flex PCB Filtering Capacitors
Samtec Twinax “FireFly”, ~10m
9 Data (1.2Gbps)
1 Clock
1 Control/Trigger
Readout Unit
Front End
Regulated Power
FELIX
Back End
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
GBT Optical Links
9-sensor Stave
DCS
CAN BUS
CAEN Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
MVTX electronics consists of three main parts
Sensor-Stave (9 ALPIDE chips) | Front End-Readout Unit | Back End-FELIX/DAM
one pixel
ALPIDE pixel:
Shaping
Digitization
Zero-suppression
3x buffer
ATLAS Front-End Link eXchange (FELIX):
also used by TPC, INTT
mGTM
(40MHz)

## Slide 8: MVTX Readout and Slow Control
RU test @ ORNL
Tested all 60 production RUs at ORNL
  Additional 10 RUs for LANL R&D already tested 2019
  Debugging of failing RUs in progress
  2 shipped to LANL for R&D
  More spare VTRx/VTTx optical transceivers desired
Produced and calibrated all 30 production PUs
  2 shipped to LANL for R&D
FELIX production (8) in progress (w/ TPC)
Updated FW/SW to the latest ALICE/ITS code
  Receive triggers from GTM
  One readout data path tested
  GBT Slow Controls tested
  CANBUS low level communication tested
In progress:
  New data format (ALICE ITS) and Continuous Readout (CR)
  Full bandwidth readout w/ 3-fiber
  DCS slow control and monitoring (ALICE) software integration
  Detector safety interlock into sPHENIX (T, V, I etc.)
  mGTM integration and a full detector system test (8-stave telescope)
60+10 RUs QA Summary, from Jo
Power Board @LBNL

## Slide 9: Slow Control and Detector Safety System - take advantage of ALICE and ATLAS development work
Low-level Server
FELIX driver interface (libflxCard) provided by ATLAS
ATLAS interface connected to ALICE Online-Offline (O2) interface via FELIXwrapper library
  Status: working for PCIe Base Address Register (BAR) access
Modified version of Low-Level Arbitration (LLA) library from ALICE O2
  FELIXwrapper replaces external O2 dependency (except for a single logging library)
  Status: working (pending more comprehensive testing)
Modified version of ALICE Low-level Frontend server (ALF)
  Status: in progress (SWT and LLA done)
Middle-level command translation server (FRED / ITSCommLayer)
  Status: awaiting ALF completion
High-level slow control software
  Status: details TBD – can use large existing software base using WinCC-OA
Front-End Electronics
FELIX card
ALF
FRED / ITSCommLayer
High-level control software (WinCC-OA)
libflxCard
FELIX wrapper
LLA
Michael Peters
Detector safety system concept draft recently developed, beginning to iterate with infrastructure and detector safety personnel

## Slide 10: mGTM Development for MVTX (40MHz/LHC)
MVTX,
N x 40MHz
MVTX
MVTX
RHIC
RHIC
RHIC
N1xComma + (Fixed length MVTX gtm packet) + N2xComma;
Comma == various length, to keep the MVTX GTM packet within one RHIC CLK;
LVL-1 Trigger
With N(4) x 40MHz CLK, we can keep a full MVTX gtm packet within one RHIC CLK;
 Use the same sPHENIX GTM mode bit pattern
the same 1st bit of the GTM Bit Number 9 to send the physics trigger to MVTX;
This trigger timing will be slightly off from the sPHENIX LVL-1 trigger by a fraction of RHIC CLK, depending on the length of Comma words;
User mode bits:
Flag MVTX readout mode:
Triggered mode
Cont. readout mode (C.R.)
For C.R.
  A user-bit to flag “readout strobe”, associated with a specific RHIC Xing bunch, like start of the abort-gap etc.
  Readout per revolution (~12.7us)
1 RHIC CLK
1 RHIC CLK
1 RHIC CLK
sPHENIX GTM Bits: RHIC_CLK x 6
A special GTM for MVTX under development at BNL – mGTM, aim to test the system at next TB (if possible) in 2021
GTM
mGTM
Yasser, Cameron, Jo, Gerd, Martin/Joe et al

## Slide 11: Mechanical Supporting Structure Designed
One-Piece Endwheel design to simplify production – Results of Al EW test pieces are good
Service Barrel (SB)
CYSS
Layer-2
Layer-1
Layer-0
Jason, Joe, Walt, Jim, Camelia et al
Carbon Fiber Composite Structures (CFC)

## Slide 12: CFC Test Article: Layer-0
EW designed and Layer-0 prototyped, met all design specs
  3rd-party inspection confirmed the results from manufacturer
  Layer-0,1,2 are the most complex components with the tightest tolerances
CFC structure full production started @WorkShape: EW, CYSS, SB
  Successful Production Readiness Review, 12/15/2020
  1st half delivery in March, the 2nd half in April
WorkShape (France)

## Slide 13: FEA Studies: Nose Roller and Sagging
Nose Roller that interconnects ends of MVTX halves effectively reduces sag by over 0.3 mm
Sagging ~ 0.3mm
MVTX/BP clearance ~1.5mm
3-D mockup of Nose Roller
Jason, Walt et al

## Slide 14: MVTX Detector Insertion System Designed
Final position:
mounted on X-Wing
X-Wing
Insertion system
New beam pipe supports
to minimize sagging
From Brian Brenton/BNL
sPHENIX integration 1/19/2021
MVTX
MVTX
Jason, Joe, Walt et al

## Slide 15: Detector Assembly Fixture Designed
Assembly procedure document drafted and reviewed @PRR 12/2020
Joe, Jason, Walt et al
MIT+LANL+LBNL

## Slide 16: Simplified Half-Layer Assembly Procedure

## Slide 17: Stave Production at CERN
4 STAVEs (3 Gold + 1 Silver) delivered to LBNL
45 Gold Staves are ready to deliver
6 new Gold Staves passed metrology
  Rate: ~4-stave/week
  Complete full production by 3/2021
~80cm long
Stave Production Meetings with CERN every 3 weeks
to keep track of progress and address issues timely, latest meeting 1/20/2021
Stave production steps and QA chart

## Slide 18: Stave Shipping and Reception Test
The original plan: hand-carry on airplane, CERN->LBNL
New - commercial option due to COVID travel restriction
Modified rifle case for staves
~80cm long
Yuan, Hanseul, Ho-San et al
From DaveM

## Slide 19: Commercial Transportation Checked
- Shock, temperature, pressure variations during the transportation
Shocks logged during the transportation LBNL -> CERN (9/21 - 10/1)
Vibration test @CERN
Also did drop tests to the floor,
dragging, car-riding etc.
Reproduce transportation “shocking” at Lab, with a test stave

## Slide 20: Stave Wire Bonds Pull Test
More details of the vibration test: https://docs.google.com/presentation/d/14iu-azMwnL_OYsT7XyApULv_z7TGYQZZ7IP8hkWnOyI/edit#slide=id.ga48628e3f0_4_41
No difference observed after the tests (pull test, electrical functionality check)
Status | Mean (gm) | StdDev (gm)
HIC | 9.874 | 0.828
Before test | 10.137 | 0.529
After shock test | 9.938 | 0.586
After vibration test | 9.811 | 0.512
Stave
First test shipment in December: 1 Silver + 3 Gold staves to LBNL

## Slide 21: Stave Reception Test at LBNL
Setup an identical stave test station at LBNL
Follow the same test procedures used at CERN
Yuan, Hanseul, Ho-San, Yasser, Cameron et al
Stave storage
4 staves @LBNL

## Slide 22: Stave QA Results - A204 (Gold)
(Digital, Analogue, Digital Grd, Analogue Grd)
(0.32, 0.32, 0.16, 0.16)
(0.246, 0.372, 0.0, 0.0)
(0.246, 0.372, 0.123, 0.186)
(0.246, 0.372, 0.246, 0.372)
(0.123, 0.186, 0.123, 0.186)
Most of the test results from LBNL are consistent with those from CERN
Threshold scan results need to be checked by CERN folks before drawing conclusions
Next stave shipment is under discussion

## Slide 23: Other MVTX Detector Services
Power system, grounding
Cable routing
Cooling system
sPHENIX AC/DC Review 7/15/2020
DC
7V, 3.3V, -5V
DC to MVTX
detector
1.8V, -3V
Rack 2, 2E3
Yuan, Ho-San, Jo, Yasser, Cameron
Russ, Joel et al

## Slide 24: Cabling and Crate Setup
27’’ subrack designed and ordered for testing
  subrack for power boards & readout units
  standard 19’’ will make 2E1 too crowded with cables.
  Two VME backplanes (for groundings) joint
Cable plan developed
https://docs.google.com/drawings/d/1AeE-mCyG4cHCX9HjtLNjmEs3yVwiJ6QZpsQ4mHUnRmw/edit?usp=sharing
Custom 27” wide VME crate (Std 19”)
Ho-San, Yuan, Jo et al
ITS/IB RUs+PUs+cables

## Slide 25: MVTX Cable Routing Plan: from MVTX to 2E1 and 2E3
Roland Wimmer /BNL
@MVTX Electrical system integration
Meeting, 12/4/2020
MVTX
cables
Section | Longest cable length estimate (m)​
Patch Panel to 2E1 | 7.8m​ *
2E1 to 2E3 | 5.6m​ *

## Slide 26: RU and PU Cooling (ITS/IB ~ MVTX)
“negative” pressure water cooling
For staves, RUs and PUs

## Slide 27: Preliminary MVTX Cooling System Designed and Tested
Robert P. Pisani
@BNL
Propose to use same chiller system, for MVTX & INTT,
- share spare and cost
Jason, Joe, Walt, Jim et al

## Slide 28: Summary and Outlook
Accomplished a lot, still many challenges ahead
  Mechanical system
  Electrical system
  Integration
Half-detector assembly at LBNL
  Stave shipping and test
  CFC production and test fitting
  Assembly half-detectors and QA
Readout & control system integration
  New data format, continuous readout etc
  mGTM development and integration
  Slow control, monitoring and detector safety
Other services
  Cooling system final design and test
  Clean tent at BNL in late Fall 2021 for commissioning
Upcoming reviews
  sPHENIX MVTX/INTT/BP integration Review: ~ Mar/Apr 2021
    Complete MVTX insertion system mockup
  Cables safety review/approval, early 2021
    Racks and cable layout
    Power and data cable procurements and QA
  Half-detector assembly review, ~May 2021

## Slide 29: Backup slides

## Slide 30
* Partial/Not functioning
 | STAVE-production summary table |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IBSTAVE ID | HIC assembly | HIC assembly date | Ins. after glue | Bonding | Pull test (>=2 lifts + F <7g) | Ins. after bonding | HIC PWR test | Qualification test | Threshold cluster | HIC Matrix | HIC DTU | HIC DTU (new) | HIC+SF+C -> Stave | Stave PWR test | Stave test | STAVE test date | STAVE metrology | Stave PWR test (long PWR extn.) | STAVE final test (PT100) | Final STAVE Matrix | Final STAVE DTU | STAVE Deliverd
TOTAL | 83 |  | 83 | 80 |  | 80 | 76 | 62 |  |  |  |  | 58 | 57 | 57 |  | 49 | 49 | 49 |  |  | 4
A201 (326) | 1 | 03/10/2019 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 01/11/2019 | 1 | 1 | 1 | GOLD | OK | 1
A202* | 1 | 07/10/2019 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
A203 (144) | 1 | 08/10/2019 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 04/11/2019 | 1 | 1 | 1 | GOLD | OK | 1
A204 (158) | 1 | 22/10/2019 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 07/11/2019 | 1 | 1 | 1 | GOLD | OK | 1
A205 (167) | 1 | 23/10/2019 | 1 | 1 | 4 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 08/11/2019 | 1 | 1 | 1 | GOLD | OK | 
A206 (204) | 1 | 30/10/2019 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | GOLD | CAN | CAN | 1 | 1 | 1 | 24/01/2020 | 1 | 1 | 1 | GOLD | CAN | 
B201 (352) | 1 | 30/10/2019 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 28/05/2020 | 1 | 1 | 1 | GOLD | OK | 
B202* | 1 | 31/10/2019 | 1 | 1 | 0 | 1 | 1 | 0 |  | Broken |  |  |  |  |  |  |  |  |  |  |  | 
B203 (114) | 1 | 07/11/2019 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 29/05/2020 | 1 | 1 | 1 | GOLD | CAN | 
B204 (116) | 1 | 13/11/2019 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | SILVER | CAN | CAN | 1 | 1 | 1 | 28/05/2020 | 1 | 1 | 1 | SILVER | CAN | 1
B205 (115) | 1 | 14/01/2020 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 02/06/2020 | 1 | 1 | 1 | GOLD | OK | 
B206 (295) | 1 | 15/01/2020 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 02/06/2020 | 1 | 1 | 1 | GOLD | OK | 
F201* | 1 | 27/02/2020 | 1 | 1 | 1 | 1 | 1 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
F202 (230) | 1 | 28/02/2020 | 1 | 1 | 3 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 04/06/2020 | 1 | 1 | 1 | GOLD | CAN | 
F204 | 1 | 29/02/2020 | 1 | 1 | 5 | 1 | 1 | 1 | 2 | GOLD | CAN | OK |  |  |  |  |  |  |  |  |  | 
G202 (234) | 1 | 10/02/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 04/06/2020 | 1 | 1 | 1 | GOLD | OK | 
G203 | 1 | 12/02/2020 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN |  |  |  |  |  |  |  |  |  | 
F203* | dummy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H202 (294) | 1 | 24/02/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 05/06/2020 | 1 | 1 | 1 | GOLD | OK | 
H203 (302) | 1 | 26/02/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 05/06/2020 | 1 | 1 | 1 | GOLD | OK | 
H204 (354) | 1 | 27/02/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 11/06/2020 | 1 | 1 | 1 | GOLD | OK | 
H206* | 1 | 04/03/2020 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
E204 (110) | 1 | 05/03/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 22/06/2020 | 1 | 1 | 1 | GOLD | CAN | 
E201* | 1 | 12/02/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 3 | PARTIAL | CAN | OK |  |  |  |  |  |  |  |  |  | 
E202 | 1 | 10/03/2020 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | CAN (bad driver) | CAN (bad driver) |  |  |  |  |  |  |  |  |  | 
E206 (101) | 1 | 12/03/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 16/06/2020 | 1 | 1 | 1 | GOLD | OK | 
H205 | 1 | 11/06/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | SILVER | OK | OK |  |  |  |  |  |  |  |  |  | 
I202 (175) | 1 | 15/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 22/06/2020 | 1 | 1 | 1 | GOLD | OK | 
I203 (187) | 1 | 16/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 26/06/2020 | 1 | 1 | 1 | GOLD | OK | 
I204* | 1 | 17/06/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
I205 (266) | 1 | 22/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 26/06/2020 | 1 | 1 | 1 | GOLD | OK | 
J201* | 1 | 23/06/2020 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
J202 (207) | 1 | 24/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 16/07/2020 | 1 | 1 | 1 | GOLD | CAN | 
J203 (245) 345 right | 1 | 29/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 17/07/2020 | 1 | 1 | 1 | GOLD | CAN | 
J204 (252) | 1 | 30/06/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 03/07/2020 | 1 | 1 | 1 | GOLD | OK | 
J206 (260) | 1 | 01/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 03/07/2020 | 1 | 1 | 1 | GOLD | OK | 
K202 (122) | 1 | 07/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 18/08/2020 | 1 | 1 | 1 | GOLD | OK | 
K203 (125) | 1 | 08/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 18/08/2020 | 1 | 1 | 1 | GOLD | OK | 
K204 (129) | 1 | 09/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 04/09/2020 | 1 | 1 | 1 | GOLD | OK | 
K205 (128) | 1 | 13/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 04/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
K206 (347) | 1 | 14/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 28/09/2020 | 1 | 1 | 1 | GOLD | OK | 
Stave Production meeting
with CERN1/19/2021

## Slide 31
 | STAVE-production summary table |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IBSTAVE ID | HIC assembly | HIC assembly date | Ins. after glue | Bonding | Pull test (>=2 lifts + F <7g) | Ins. after bonding | HIC PWR test | Qualification test | Threshold cluster | HIC Matrix | HIC DTU | HIC DTU (new) | HIC+SF+C -> Stave | Stave PWR test | Stave test | STAVE test date | STAVE metrology | Stave PWR test (long PWR extn.) | STAVE final test (PT100) | Final STAVE Matrix | Final STAVE DTU | STAVE Deliverd
L202 (130) | 1 | 23/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 08/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
L203 (139) | 1 | 24/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 08/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
L204 (127) | 1 | 27/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 14/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
L205 (136) | 1 | 28/07/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 14/09/2020 | 1 | 1 | 1 | GOLD | OK | 
J205* | 1 | 05/08/2020 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | CAN | CAN |  |  |  |  |  |  |  |  |  | 
I201* | 1 | 06/08/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
L206* | 1 | 13/08/2020 | 1 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
L201 (169) | 1 | 14/08/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 30/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
S201 (359) | 1 | 03/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 30/09/2020 | 1 | 1 | 1 | GOLD | OK | 
S202 | 1 | 04/09/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | SILVER | CAN | CAN |  |  |  |  |  |  |  |  |  | 
S203 (235) | 1 | 08/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 16/11/2020 | 1 | 1 | 1 | GOLD | OK | 
S204 (237) | 1 | 15/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 30/09/2020 | 1 | 1 | 1 | GOLD | CAN | 
S205 (142) | 1 | 16/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 01/10/2020 | 1 | 1 | 1 | GOLD | CAN | 
S206 (98) | 1 | 17/09/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 02/10/2020 | 1 | 1 | 1 | GOLD | OK | 
T201 (277) | 1 | 04/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 17/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
T202 (279) | 1 | 06/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | GOLD | CAN | CAN | 1 | 1 | 1 | 19/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
T203 | 1 | 09/11/2020 | 1 | 1 | 0 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
U201 (291) | 1 | 10/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | SILVER | CAN | CAN | 1 | 1 | 1 | 24/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
U202 (238) | 1 | 11/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 26/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
U203 (126) | 1 | 12/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 20/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
U204* | 1 | 13/11/2020 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
U205 (89) | 1 | 16/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 27/11/2020 | 1 | 1 | 1 | GOLD | OK | 
U206 (111) | 1 | 17/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 25/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
Q201 (155) | 1 | 18/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | SILVER | CAN | CAN | 1 | 1 | 1 | 27/11/2020 | 1 | 1 | 1 | GOLD | CAN | 
Q202 | 1 | 19/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | OK | 1 | 1 | 1 | 03/12/2020 | 1 | 1 | 1 | GOLD | CAN | 
T204 | 1 | 23/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 03/12/2020 | 1 | 1 | 1 | GOLD | CAN | 
T205 | 1 | 24/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | OK | 1 | 1 | 1 | 03/12/2020 |  |  |  |  |  | 
T206 (232) | 1 | 25/11/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 14/01/2021 |  |  |  |  |  | 
R201 (119) | 1 | 27/11/2020 | 1 | 1 | 8 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 | 1 | 1 | 08/12/2020 |  |  |  |  |  | 
R202 (109) | 1 | 30/11/2020 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 17/12/2020 |  |  |  |  |  | 
W201 (52) | 1 | 01/12/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | ?? data line broken |  |  |  |  |  |  |  |  | 
W202* | 1 | 02/12/2020 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | CAN | CAN |  |  |  |  |  |  |  |  |  | 
W203 (212) | 1 | 03/12/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | SILVER | CAN | CAN | 1 | 1 | 1 | 05/01/2021 |  |  |  |  |  | 
W204 (271) | 1 | 07/12/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 3 | GOLD | OK | OK | 1 | 1 | 1 | 05/01/2021 |  |  |  |  |  | 
W205 (275) | 1 | 08/12/2020 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | CAN | 1 | 1 | 1 | 18/01/2021 |  |  |  |  |  | 
W206 | 1 | 09/12/2020 | 1 | 1 | 0 | 1 | ?? Digi short |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R203 | 1 | 06/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | OK | 1 | 1 | 1 | 20/01/2021 |  |  |  |  |  | 
R204 | 1 | 11/01/2021 | 1 | 1 | 0 | 1 | 0 | 0 | ?? | PARTIAL | OK | OK |  |  |  |  |  |  |  |  |  | 
Q203 | 1 | 12/01/2021 | 1 | 1 | 0 | 1 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
X201 | 1 | 13/01/2021 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | CAN | 1 |  |  |  |  |  |  |  |  | 
X202 | 1 | 14/01/2021 | 1 | 1 | 0 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
X204 | 1 | 18/01/2021 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
X205 | 1 | 19/01/2021 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 32: Transportation conditions
Pressure
LBNL -> CERN (9/21 - 10/1)
LBNL -> CERN (12/8 - 12/15)
?
?

## Slide 33: Stave test - B204
Previous tests (for the silver stave) used various resistance values, which were determined based on the voltage on the adaptor
Some configurations reproduced similar test results as those from CERN, but some failed or produced different results
In addition to the cable resistances, FPC power extension resistances were measured, and added to the calibration
Cable + FPC power extension resistance for Digital and Analogue are 0.246 Ohm and 0.372 Ohm, respectively
We compare results of 4 calibration configurations
(Digital, Analogue, Digital Grd, Analogue Grd)
(0.246, 0.372, 0.246, 0.372)
(0.246, 0.372, 0.123, 0.186)
(0.246, 0.372, 0, 0)
(0.32, 0.32, 0.16, 0.16)
Previous configuration
1.8V at the adaptor

## Slide 34: VTRx Issue at LHC
Link loss threshold
Single Mode (trigger) relative signal, 100% ≈ 40 µA
Multi Mode (data) relative signal, 100% ≈ 340 µA
Link loss threshold
Interventions
Interventions
4 Months
4 Months
In many VTRx modules we observed a degrading optical signal,
This happens for both Multi Mode (MM) modules (data) and Single Mode (SM) modules (trigger)
From Jo

## Slide 35: Accounting of VTRx problem in ALICE ITS
good if it never dropped below 10% of the expected RSSI .
warn if the measured RSSI dropped more than 10% once or more during its operations.
bad is the current ever dropped below the broken link threshold.
L0_09 (SM) lens after scalpel cut
VTRx 301350 (SM) lens BEFORE heating
VTRx 301350 (SM) lens AFTER heating

## Slide 36: Cable Routing Plan
MVTX cable routing plan
Roland

## Slide 37: Beam Pipe Analysis
Old Beampipe FEA results and changes (Target 0.5mm Defletion)
New design/Integration of New design
Brian

## Slide 38: Stiffener (0.91mm)

## Slide 39: Beam Pipe, MVTX, INTT and MBD Integration
Need to run FEA on New Beampipe Support
Deflection can be compensated by adjusting New Beampipe Support height on North end.
Additional/temporary supports on South end during MVTX install may need to be added.
Brian

## Slide 40
Jo is testing the sPHENIX readout cables @CERN

## Slide 41: MVTX Readout and Power Cable Route
sPHENIX MVTX: 7.9+m to 2E1
  Cable-A: 1.4 m
  Cable-B: 6.5+ m
  Power cable:4.7+ m
Desired ~10m
PWR
RU
PU
BNL has approved “non-halogen free” cables for sPHENIX

## Slide 42: Cabling & Crate Setup (ITS/IB)

## Slide 43: Study MAPS Performance with Laser @LANL
Inject “MIP” signal, focused laser beam
  850 nm laser, 4ns wide pulse, ~1 MIP
  50kHz trigger
  Find optimal MAPS operating parameters
Pixel hits
Laser system
MOSAIC Testbench

## Slide 44: Laser Scan Data – Pixel Hit Efficiency vs Trigger Delay
One of “Stretched Settings” for sPHENIX trigger
Expected trigger latency: ~4us
MAX: 64 cells x 106nS = 6.8uS
~ 4.7 us
sPHENIX Trigger
Pixel (Row-Col)
~ 4.7 us
sPHENIX Trigger latency
Pixel (Row-Col)