## Slide 1: Project Planning & Milestones
ALICE ITS Upgrade
Stave Production Readiness Review
CERN, 27 April 2017
Luciano Musa - CERN

## Slide 2
Outline
  Summary of Project Review Milestones
  R&D and Construciton Milestones
  Overall Simplified Planning
Project Planning & Milestones
ALICE ITS Upgrade

## Slide 3
  Pixel Sensor Chip - EDR (Oct’ 15)
  Stave - EDR (May’ 16)
  Detector Barrel Mechanics - EDR (Jul ’16)
  Cooling – EDR (Jul ’16)
  Pixel Sensor Chip - PRR (Nov ’16)
  Detector Barrel Mechanics - PRR (Dec ’16)
  Service Barrel Mechanics - EDR (Dec ‘16): done
  Cooling – PRR (Dec ’16): done
  Readout Electronics – EDR (Jan ‘17): done
  Stave - PRR (Apr ‘17)
  Service Barrel Mechanics – PRR (May ‘17)
  Readout Electronics – PRR (Dec ’17)
Project Review Milestones
ALICE ITS Upgrade

## Slide 4
Project R&D and Construction Milestones
ALICE ITS Upgrade
Nov-16 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
ALPIDE EDR (10/15) |  |  |  |  |  | 
ALPIDE PRR (25/11/16) |  |  |  |  |  | 
ALPIDE product. and test (end 12/17) |  |  |  |  |  | 
IB stave EDR (3-4/5/16) |  |  |  |  |  | 
IB stave PRR (27/4/17) |  |  |  |  |  | 
IB FPC production end (12/17) |  |  |  |  |  | 
IB space frame & cold plate prod. end (9/17) |  |  |  |  |  | 
IB-1 stave production end (1/18) |  |  |  |  |  | 
IB-1 assembly end (3/18) |  |  |  |  |  | 
OB stave EDR (3-4/5/16) |  |  |  |  |  | 
OB stave PRR (27/4/17) |  |  |  |  |  | 
OB FPC production end (6/18) |  |  |  |  |  | 
OB space frame & cold plate prod. end (1/18) |  |  |  |  |  | 
OB HIC production end (6/18) |  |  |  |  |  | 
OB stave production end (8/18) |  |  |  |  |  | 
OB stave assembly end (10/18) |  |  |  |  |  | 

## Slide 5
Project R&D and Construction Milestones
ALICE ITS Upgrade
Mar-17 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
RO electronics EDR (27/1/17) |  |  |  |  |  | 
RO electronics PRR (12/17) |  |  |  |  |  | 
RO electronics prod. end (12/18) |  |  |  |  |  | 
Detector barrel EDR (20/7/16) |  |  |  |  |  | 
Detector barrel PRR (14/12/16) |  |  |  |  |  | 
Detector barrel prod. end (7/17) |  |  |  |  |  | 
Service barrel/cage EDR (14/12/16) |  |  |  |  |  | 
Service barrel/cage PRR (5/5/17) |  |  |  |  |  | 
Service barrel/cage prod. end (9/17) |  |  |  |  |  | 
Cooling plant EDR (21/7/16) |  |  |  |  |  | 
Cooling plant PRR (16/12/16) |  |  |  |  |  | 
Cooling plant ready (9/18) |  |  |  |  |  | 
Commissioning surface end (5/19) |  |  |  |  |  | 
Installation during LS2 (4/20) |  |  |  |  |  | 
11 months contingency

## Slide 6
Sensor Series Production
Stave Develop
2016
2017
2018
2019
2020
Commissioning @ Surface
Installation
Commissioning in ALICE
Stave Mechanics
HIC Production
CMOS processing, thinning & dicing, test
Hic and Stave
Stave Production
Mechanical Support Structures
Design & Prototyping
Design & Prototyping
Production & Test
PRR
PRR
Global Assembly
EDR
PRR
Development
Production
2016
2017
2018
2019
2020
EDR
PRR
Readout Electronics
Commissioning
11 months
Dry Assembly Test
ALICE ITS Upgrade
Overall ITS Planning (Simplified Global View)