## Slide 1: OB Flexible Printed Circuit
ALICE ITS Upgrade
Stave Production Readiness Review
CERN, 27 April 2017
Paolo Camerini – INFN Trieste

## Slide 2
Outline
  Layout: changes wrt EDR
    Tab extension
    Vias for wire bonds
    New connection for BB
  Prototype production
    Metrological tests
    Data transmission tests
  Test Stages and Setups
    Tender Procedure
    Components mounting
    Production Schedule
  Acceptance and Preparation for Assembly
    Quality assurance
    Cross cables mounting
    Transport to assembly sites

## Slide 3
LAYOUT DETAILS

## Slide 4
Length: 210.9 mm width: 33 mm
WINGS with precise holes for alignment during HIC assembly:
TAB for test purpose (cut after tests)
TOP LAYER:DIGITAL AND ANALOG power planes
BOTTOM LAYER: GND PLANES
Back Bias voltage supply line
2 rows of 7 chips: each row with 1 master + 6 slaves
MASTER-SLAVE Communication
  internal single ended data bus for: data (4 lines), ctrl (1 line), busy (1 line)
  internal differential CLK line
CTRL and CLK lines from end of stave to MASTER chip
14 DIFFERENTIAL DATA lines
length: 210.9 mm
TAB: 37 mm
width: 33 mm
Wings for alignment
OB FPC: Overall View

## Slide 5
Copper (top, bottom) thickness: 18 μm
Substrate (dielectric) thickness: 75 μm
Soldermask (top, bottom) thickness: 18 μm
MATERIALS
Substrate (dielectric) type: Pyralux AP8535R by Dupont (double-sided, copper-clad laminate, Cu thickness 18 um, polyimide core 75 um)
Finishing: ENIG (Ni layer: 3-5 um Au layer: of 60-100 nm)
OB FPC Layer Stack-up

## Slide 6
0;0
DVDD
GND
AVDD
BB
GND
DVDD
CC type A:
DVDD-GND- AVDD
5 per module
CC type B:
Back-bias
1 per module
x
y
Cross Cables for Connections to PB

## Slide 7
SMD 0402 on all chips (up to 22 mF each)
  AVDD and DVDD: 2 SMD 0402
  SUB/PWELL: 1 SMD to AVDD and 1 SMD to AVSS
on DVDD
on AVDD
on SUBPWELL
0402 dec. capacitor
Decoupling Capacitors

## Slide 8
VIAs Optimized for Wire Bonding
Oblong symmetric shapes
hole 400 x 1200 mm2
metallized crown 600 x 1600 mm2
soldermask opening: 700 x 1800 μm2
bonding area: 200 mm
1200 µm
1600 µm
400 µm
600 µm
200
µm
200
µm
100 µm
100 µm
700 µm
1200 µm
400 µm
600 µm
200
µm
200
µm
100 µm
700 µm
100 µm
1600 µm
Example of via for power
Example of via for ground

## Slide 9
FPC Type A – Type B
Version with TAB has been designed and produced
TYPE B is for the first module of the Half-Stave (HS)
TAB needs to be removed after test before module assembly on HS
TAB cutting procedure developed: more details in “OB HIC test” presentation
9
length: 210.9 mm
TAB: 37 mm
width: 33 mm
Wings for alignment
TAB cut line
Wings for alignment
width: 33 mm
TAB: 31.9 mm
length: 216 mm
TAB cut line
TYPE A
TYPE B

## Slide 10
A dedicated version of the FPC is necessary for the first module of the Half-Stave to allow a reliable and safe connection to the “external electronics”  see next slide
 The FPC for the first module of the Half-Stave is extended by a few mm.
TYPE A
FPC Type B

## Slide 11
The extension is needed to transmit data, clock and control to/from the external electronics
One extension for each HS
At the end, 2 Firefly connectors are soldered
288 extensions + spares needed
Estimated cost: 30KEu  no tendering needed
Prototypes designed and produced (SwissPCB)
Pads for the connector
Second column for data, clk, ctrl transmission
Second column for connection to ground
Pads for connection with TAB B FPC
External electronics
FPC Extension

## Slide 12
FPC Procurement

## Slide 13
Technical Specifications
List of main dimensional requirements
Central dowel pin hole diameter: | -0,+20
Oblong holes/vias (major and minor axis) | ±50
Strips width, distance | ±10
Cu thickness Surface (solder mask) flatness | ±2 ±5
Distance between the centre of the central dowel pin hole and | Required tolerances (mm)
Right edge | ±25
upper and lower edges | ±25
Holes center | ±50
Pads center (all pads types) | ±50

## Slide 14
FPC Prototype Characterization
Vendor selection is the result of a long and intensive R&D with several companies.
Main fabrication challenges
Dimensional tolerances of structures and circuit
Tolerance on position of FPC edges and structures wrt reference dowel pin hole ~0.2‰
Surface (soldermask) flatness: ±5mm (crucial for proper and safe HIC gripping)
Copper thickness tolerance: (18±2) mm
Improvements with all companies;
SwissPCB only company to fulfil all requirements (special procedure for guaranteeing uniform soldermask thickness)

## Slide 15
FPC Prototype Characterization – Some Examples
Metrological tests (by Modus97 company) of all structures of a (SwissPCB) prototype FPC
Y
Holes Position relative to alignment hole
→ X maximum deviation from nominal position = (-40,+50) μm [tol.:± 50mm]
→ Y maximum deviation from nominal position = (-10,+25) μm [tol.:± 50mm]
X
Measurement of some critical dimensions parameters of a (S.PCB) prototype FPC

## Slide 16
FPC Prototype Characterization – Some Examples
Solder mask thickness guarantees good planarity also in regions around strips
Micro-sections of a prototype fpc (by Swiss-PCB) and reference stack up for the prototype
←Soldermask →
←Soldermask →
Polyamide
Cu
Cu
Cu
Encapsulating epoxy
Encapsulating epoxy
Soldermask →
Soldermask →
polyamide →
Cu →

## Slide 17
FPC Metallization Quality
Pad plating: Electroless Nickel Immersion Gold (ENIG)
Focused Ion Beam (FIB) (30 keV gallium ions) measurement to
  Measure the thicknesses of the pad/via finishing
Finishing layer thicknesses expected (above copper):
    3-5 μm of Nickel
    60-100 nm of Gold
Via metallization
Gold on vias
73nm
Results:
  Nickel thickness: 4.5 μm (average).
  Gold thickness: .
ZOOM

## Slide 18
Electrical Tests on Prototypes
Swiss PCB ver 2 production
Test on CLK and DATA lines:
  Measured the s-parameters to quantify
    the attenuation of differential lines
    the cross-talk between differential lines (Near-End and Far-End Xtalk).
Results:
  Attenuation: up to -3.6 dB on a single FPC.
  Cross-talk between data lines: cross-talked signal attenuated of - 40 dB wrt aggressor's signal
Cross-talk
Attenuation
Max frequency to consider
Max frequency to consider
Setup with a Vector Network Analyzer

## Slide 19
FPC Planarity Test
Measurement of FPC planarity using touch probe (SMART SCOPE). Corrected for jig planarity (top figure)
Measurement along 3 different lines, (each is average of 3 measurements)
Note: red line higher than other lines; no vacuum holes underneath
FPC under test: dummy (no finishing) by SwissPCB

## Slide 20
1692 FPCs to be mounted on staves
+20 % spares 2030
+25% (assuming 80% production yield) 2537 FPCs needed
Firm selected with a tendering procedure.
Tender based on technical + economical evaluation
5 companies invited to tender
Only one company capable of fulfilling all technical requirements.
Successful bidder: GS Swiss PCB AG
Automated Components mounting by Hybrid SA
Automated Assembly procedure not validated yet but test assembly by Hybrid of a first batch of FPCs presently under way.
Manual mounting still a viable option in case of need (all prototypes mounted manually up to now)
FPC Procurement - Tender

## Slide 21
Production Quality Assurance (Vendor)
Quality of delivered items verified by company QA tests
SwissPCB will guarantee compliance to Technical Specs by means of exhaustive tests
Defects search, geometrical compliance of structures (e.g. strip width) by Automated Optical Inspection
Dimensional requirements of Techical Specs checked with measuring machine
Cu (soldermask) thickness: sample micro sections
Isolation of all lines (AOI and electrical)
Continuity of lines (electrical)
Flatness of FPC
General visual inspection
Plating quality: visual inspection
SMD mounting quality: visual inspection

## Slide 22
Production Schedule
Two production phases
pre-production for process validation
production
Pre-production: 100 (+200) assembled FPCs (within 45 days from contract signature)
Validation (<45 days)
  Electrical
  Metrological
  Finishing/Bonding verification
  Assembly
Production: 320 assembled fpcs/45 days (10 fpcs/week/assembly site)

## Slide 23
FPC Quality Assurance

## Slide 24
Electrical Acceptance test
Test of DATA,CTRL and CLK lines
  Open
  Shorts
  Resistance ( Cu strips thickness and width)
Tests Carried out on a Sample of FPC of each Batch
  Data transmission parameters: s-parameters, attenuation, eye diagram
  Bondability test
Electrical Tests Carried-out on All FPCs

## Slide 25
Metrological Inspection
General visual inspection
  Plating quality, presence of defects on strips, …
Verify overall dimensions (measuring machine)
  Distance of right fpc edge w.r.t. reference hole
    Relevant for HIC assembly and HS assembly;
    Tolerance: ± 25mm
  Position and shape of a subset of holes w.r.t. reference hole to be within tolerances
Flatness
SAMPLE TESTS ON SELECTED FPCS
  Full metrology @ metrological company
    Check overall dimensions
    Check positions of ALL bonding holes and pads vs. central reference hole
  Thickness of substrate/Cu lines/cover layer: micro-section, tomography
  Planarity

## Slide 26
Final Operations
  Once electrical and metrological tests are passed
  Cleaning
  Cross cables soldering
    Will be done in house
    Manual soldering (with soldering iron)
    Note: soldering performed before silicon sensors mounting
  Delivery to assembly centers using same carrier plates as for HICs

## Slide 27
Summary
Layout finalized
  A few changes w.r.t. EDR:
    Tab extension finalized, lines and pads optimization, vias for wire bonding optimized, new connection for substrate bias
Prototypes production
  Several small productions with different companies (new company SwissPCB)
  Metrology, data transmission, soldering and bonding tests on prototypes for proper characterization and evaluation of different productions
Procurement
  Tender finished and job assigned to
  SWISS PCB AG for FPC construction (HYBRID SA will perform smd assembly)
FPC acceptance and preparation for assemby
  Quality assurance
  Cross cables soldering
  Distribution to HIC assembly sites

## Slide 28
Additional Material

## Slide 29
Test on CLK, CTRL and DATA line
  Measured I-V curves to calculate resistance of lines
  V: <200 mV, I: max. 50 mA
Results
  No shorts, no opens encountered
  Contact+cables introduce 0.8 Ω
  resistance for data lines<4Ω
  resistance on power planes: 10-20mΩ
CTRL line
~3.7 Ω
Electrical Tests on Prototypes

## Slide 30
Measurement at SEM and surface profile machine to
Measure the planarity of the pads
Verify the quality of the industrial process
Via
Pad metallization
Via metallization
Max roughness of 1.4 μm
Pad surface profile
Via high cross-section quality
FPC Metallization Quality