## Slide 1: Power Distribution
ALICE ITS Upgrade
Stave Production Readiness Review
CERN, 27 April 2017
Leo Greiner - LBNL

## Slide 2
  Requirements
  Review of Power System Design
  Design and Prototype/Production Status
  System Modularity/Granularity, Characteristics
  Most of the material in this presentation is available in greater detail in a system description document available at the link below
Comprehensive baseline power system description available at:
https://twiki.cern.ch/twiki/pub/ALICE/Presentations20on20power20system/2017_04_08_ITS_upgrade_power_system_description.docx

## Slide 3
Power System Requirements
The requirements for the powering system are closely inter-dependent with the sensor and module FPC requirements in that all of these components need to work together to meet the overall detector requirements for the ALICE ITS upgrade. These are most succinctly expressed as:
Supply power (sensor supply and bias) to the modules/half-staves such that:
  Module sensor efficiency ≥ 99%
  Module sensor noise rate < 10-6
Radiation length of the power bus in the fiducial volume is < 0.4%
Survive the radiation environment at the power board location.
Interface to the ALICE ITS RDO board for control of PS functions and readout of parameters.
Fit into the space allocated in the ITS upgrade integration envelopes.
To this end, the design of the powering system is intended to be compatible with meeting these requirements. This design will be tested in the development of individual modules and extended into the fabrication of half and full staves.
The desirable functional attributes for system include:
Overcurrent protection for each power channel
Remote current readout for each power channel
Remote voltage readout for each power channel
Remote voltage setting capability for each channel

## Slide 4
Baseline System Design
Half-stave
Power bus
Filter
Board
RDO
unit
Power Supply
and Bias
Control board
CAEN
Main
Power
Power
power, bias
monitor, control
data, config, control
CAEN
bias
supply
Power, sense
bias, sense
PP0
Racks (low rad)
Control Room (no rad)
Magnet face
(10k rad)
Inside TCP field cage (100k rad)
Bias bus
bias
PP1
CANbus
Breakout board
FB-BOB

## Slide 5
Functional System Design

## Slide 6
Stack up end view of stave
End of Stave Structure for ML / OL

## Slide 7
reg
reg
reg
reg
V, I mon/buffer
Power in
32 reg
PT100 interface
Overcurrent
detection
Overcurrent
reset
Power Board
RDO
interface
Overcurrent
threshold
Filtering board
reg
reg
V adjust
Power Bus
Bias Bus
Isolated bias section
reg
V, I mon/buffer
switch
x8
Breakout Boards
FB BOB
CAEN Supplies
Main power
Bias
Power Bus
Bias Bus
Filter Board
FB-BOB to PB-BOB cable
Power Board
CAEN Supplies
Power System Components

## Slide 8
Three piece power bus structure with power bus extension pieces soldering to the filter board
Module with cross-pieces
1 module of power bus
Updates from EDR
Aluminum conductor with individual VDDD, VDDA traces to each module. Common GND return.
Equalized resistance trace structure.
Solders directly to Filter Board.
100 um Al thickness on both sides (2 layer)
Filter
Board
Power Bus Design

## Slide 9
This allows the solder tabs to me fabricated from 100 um thick aluminum for strength in the solder connection to the bias bus.
Because the bias bus is no longer centered on the PB axis, we need separate BB and BB extensions for each half-stave type (or possibly separate filter board designs, TBD).
OL Bias bus is a 2 piece design like the power bus
BB + extension piece
Extension piece
Bias bus
The ML power and bias bus is the same basic design as the OL power and bias bus, but modified for the ML 4 module stave.
Bias Bus Design

## Slide 10
The full design for the OL and ML power bus, bias bus and cross pieces is completed and the fabrication packages are complete. These may be found at:
https://twiki.cern.ch/twiki/pub/ALICE/Presentations20on20Power20Bus/2017_03_20_ITS_power_bus_spec_files.zip
A full specification for the production fabrication procurement has been written and the price enquiry has been released.
A set of prototypes fabricated at Kharkov is complete containing prototype OL & ML power buses, OL & ML bias buses and cross pieces. These are expected to be delivered shortly.
These will be tested with the stave prototypes and assessed for functionality.
A previous set of prototypes including full length assemblies have been produced and tested, the results of the testing are very promising and links to the descriptions and testing results are below. https://twiki.cern.ch/twiki/pub/ALICE/Presentations20on20Power20Bus/2015_08_26_Report_on_Al_cable_preliminary_tests.docx https://twiki.cern.ch/twiki/pub/ALICE/Presentations20on20Power20Bus/2016_02_09_Kharkov_power_bus_test_results.pdf https://twiki.cern.ch/twiki/pub/ALICE/Presentations20on20Power20Bus/PowerBus-03032016-7-F.pptx
Power Bus and Bias Bus Status

## Slide 11
Filter Board Status
The design for the prototype Filter board and filter board breakout board are complete.
The design has been fabricated and prototypes are at Bari, CERN and Torino
The Filter Board fabrication package is available at: https://twiki.cern.ch/twiki/pub/ALICE/Presentations20on20Power20Bus/filter_board.zip
For this round of testing, the OL and ML filter board design is the same.
The prototype Filter Board uses one design for both OL and ML.
The granularity is 1 filter board per half-stave for the ML and OL staves.
Filter Board
Filter Board break out board

## Slide 12
The FB-BOB has been designed and fabricated (see previous slide).
The PB-BOB has been designed and is currently being fabricated. PCBs are at LBNL and being loaded.
An external company has been contacted to get a quotation for the full production of custom cable harnesses using the two board designs and following the granularity shown earlier.
~5 m
OL contains:
7 x module power VDDD (16 AWG)
7 x module power VDDA (18 AWG)
7 x module GND (16 AWG)
7 x module GND (18 AWG)
7 x bias (22 AWG)
4 x PT100 (22 AWG)
FB-BOB
PB-BOB
FB-BOB to PB-BOB Cable Status

## Slide 13
Power Board Status
The power board design has 2 power board halves. Each contains a separately controlled set of 16 channels of regulated power and 8 switched bias outputs

## Slide 14
A Power Board design that meets the requirements shown earlier has been designed.
An internal review of the prototype power board design was held on March 9, 2017. The review results and material may be found at https://twiki.cern.ch/twiki/bin/view/ALICE/Prod_proto_PB_review.
Based on this review, the design for the prototype PB was released for layout and fabrication.
The layout is complete and the purchase requisition for 10 prototype turnkey loaded boards was released.
The fabrication package including design, gerber, BOM and assembly files may be found at https://twiki.cern.ch/twiki/pub/ALICE/Prototype_power_board/2017_04_04_ITS_prototype_power_board_fab_package.zip.
We expect to take delivery of the prototype PBs in the second week of May.
After a week of validation testing, an order for 20-25 prototype PBs will be released to allow delivery of testing PBs to the module and stave assembly sites.
Power Board Status

## Slide 15
Layout of prototype power board
6U x 340 mm format
8 layer, 0.062” thick
Power Board Status

## Slide 16
Prototype heat exchanger
We dissipate up to 22.6 W in the power boards in operation with ML staves.
This requires a rear mounted heat exchanger to keep the boards from overheating.
These must be in place for the power boards to be distributed and used.
A simple prototype heat exchanger has been designed and fabricated for use with the prototype PBs.
These will be mounted to the prototype PBs for testing and distribution.
Note that this requires assembly sites to have a chiller/recirculator.
Power Board Status

## Slide 17
This is a commercial system and will be a procurement
We will have a meeting with CAEN in the next months to specify the system and understand the options
We have existing CAEN systems on hand for testing with the power board prototypes
x1 SY4527B Mainframe
x2 A1676A - Easy3000 Branch Controller
x8 Easy3000 Remote Crates
x4 A3486 - AC/DC bulk power supply 2x 2kW
x43 A3009 - 12Ch/8V/9A/45W
CR4
RB24 - SideA
Baseline Main PS Design Status

## Slide 18
8 power ch.
8 power ch.
8 bias ch.
8 power ch.
8 power ch.
8 bias ch.
Power Board
CAEN PS 1
CAEN PS 2
CAEN PS 3
CAEN PS 4
CAEN BIAS
CAEN BIAS
Inner Layers Modularity
PB
PB
1.67 A
0 A
1.67 A
0 A
IL stave
IL stave
2 staves per PB
(4/32 ch utilization)
The baseline modularity is four CAEN supply channel per stave. Each half-power board is controlled by 1 RU.
Modularity of Power System

## Slide 19
8 power ch.
8 power ch.
8 bias ch.
8 power ch.
8 power ch.
8 bias ch.
Power Board
ML half-stave
ML half-stave
ML half-stave
ML half-stave
CAEN PS 1
CAEN PS 2
CAEN PS 3
CAEN PS 4
CAEN BIAS
CAEN BIAS
Middle Layers Modularity
PB
PB
4.474 A
3.724 A
4.474 A
3.724 A
2 staves per PB
(full PB utilization)
The baseline modularity is four CAEN supply channel per stave. Each half-power board is controlled by 1 RU.
931 mA / module combined digital and analog @ 1.8V nominal
Modularity of Power System

## Slide 20
8 power ch.
8 power ch.
8 bias ch.
8 power ch.
8 power ch.
8 bias ch.
Power Board
OL half-stave
CAEN PS 1
CAEN PS 2
CAEN PS 3
CAEN PS 4
CAEN BIAS
CAEN BIAS
Outer Layers Modularity
OL half-stave
PB
PB
3.724 A
3.724 A
3.543 A
3.543 A
The baseline modularity is four CAEN supply channel per stave. Each half-power board is controlled by 1 RU.
1 staves per PB
(28/32 ch utilization)
931 mA / module combined digital and analog @ 1.8V nominal
Modularity of Power System

## Slide 21
 | QTY | CAEN power channels per stave | CAEN bias channels per power board | Power Boards per stave | Total CAEN power channels | Total CAEN bias channels | Total Power boards
Inner layer staves | 48 | 1 | 0.2* | 0.5 | 48 | 5 | 24
Middle Layer staves | 54 | 2 | 0.2* | 0.5 | 108 | 6 | 27
Outer Layer staves | 90 | 4 | 0.2* | 1 | 360 | 18 | 90
Total |  |  |  |  | 516 | 29 | 141
* Assuming bias power daisy chains to 5 PB per CAEN channel
Modularity of Power System

## Slide 22
ALPIDE Power Consumption
Data: combination of available measurements and simulations
Estimated uncertainty ± 10%
Values scaled for readout at 100 kHz rates and max occupancies
Clock gating enabled
Nominal ALPIDE Outer/Middle Layer Modules consist of:
2 x Master @ 184 mW
12 x Slave @ 109 mW
1676 mW/module @ 1.8 V nominal operating voltage
(VDDA = 163 mA and VDDD = 768 mA)
Power Board dissipation
in regulators (nominal):
Middle Layer PB => 22.6W
Outer Layer PB => 20.1W
Inner Layer PB => 6.3W
In board logic:
2.5W/power board half
Power Dissipation

## Slide 23
 | Number of staves | Dissipation per stave | Dissipation per layer
Layer 0 (IL) | 12 | 1.656 W | 19.9 W
Layer 1 (IL) | 16 | 1.656 W | 26.5 W
Layer 2 (IL) | 20 | 1.656 W | 33.1 W
Layer 3 (ML) | 24 | 13.408 W | 321.8 W
Layer 4 (ML) | 30 | 13.408 W | 402.2 W
Layer 5 (OL) | 42 | 23.464 W | 985.5 W
Layer 6 (OL) | 48 | 23.464 W | 1126.3 W
Total dissipation |  |  | 2915.3 W
There is also a small amount of power (single digit watts) dissipated in the power bus and in the connecting cabling
Stave Power Dissipation

## Slide 24
Voltage drops in system
Power bus resistances and voltage drops as a function of module position
Nominal
VDDD = 768 mA
VDDA = 163 mA
High Current
VDDD = 1.3 A
VDDA = 163 mA
target | resistance to power via x-location (ohm) | voltage drop (V) - nominal current | voltage drop (V) - no clock | voltage drop (V) - High current
module 1 VDD via 1 | 0.01253 | 0.00962 | 0.00351 | 0.01629
module 2 VDD via 1 | 0.04508 | 0.03462 | 0.01262 | 0.05861
module 3 VDD via 1 | 0.05609 | 0.04308 | 0.01570 | 0.07291
module 4 VDD via 1 | 0.06137 | 0.04713 | 0.01718 | 0.07978
module 5 VDD via 1 | 0.06413 | 0.04925 | 0.01796 | 0.08337
module 6 VDD via 1 | 0.06628 | 0.05091 | 0.01856 | 0.08617
module 7 VDD via 1 | 0.06773 | 0.05201 | 0.01896 | 0.08804
module 1 VDA via 1 | 0.13070 | 0.02130 | 0.01072 | 0.01072
module 2 VDA via 1 | 0.32212 | 0.05251 | 0.02641 | 0.02641
module 3 VDA via 1 | 0.34257 | 0.05584 | 0.02809 | 0.02809
module 4 VDA via 1 | 0.30032 | 0.04895 | 0.02463 | 0.02463
module 5 VDA via 1 | 0.35719 | 0.05822 | 0.02929 | 0.02929
module 6 VDA via 1 | 0.36172 | 0.05896 | 0.02966 | 0.02966
module 7 VDA via 1 | 0.36167 | 0.05895 | 0.02966 | 0.02966

## Slide 25
Voltage drops in system
0.6 m
2.0 m
2.0 m
2.0 m
2.0 m
2.0 m
2.0m
Module position | 1 | 2 | 3 | 4 | 5 | 6 | 7
Summed current | 6.517 A | 5.586 A | 4.655 A | 3.724 A | 2.793 A | 1.862 A | 0.931 A
Voltage drop | 3.9 mV | 11.2 mV | 9.3 mV | 7.4 mV | 5.6 mV | 3.7 mV | 1.9 mV
All power returns are common
Power bus return broken into module length segments.
Each conductor is 210.9 mm long, 30.4 mm wide and 0.1 mm thick
(note that first segment has connection close to the beginning of the power bus and lower resistance)
Sum to get voltage drop at particular location

## Slide 26
Voltage drops in system
PB
Out
FB
11 m
Power Bus supply
0.768A
PB extension
17 m
Voltage drops come from spreadsheet
Cross piece
5 m
Cross piece
5 m
Module
? m
Wire 66 m
OL Fixed voltage drops for digital power (VDDD) at nominal operating condition
(VDDD=0.768A, VDDA=0.163A, calculated from geometry and material)
50.7 mV
8.4 mV
13.1 mV
2.0 mV
Cross piece
5m
Cross piece
5 m
Power Bus return
PB extension
1.54 m
FB
0.7 m
Wire 5.75 m
Voltage drops come from table
2.0 mV
1.43 mV per
operating module
0.65 mV per
operating module
5.35 mV per
operating module

## Slide 27
Voltage drops in system
PB
Out
FB
11 m
52.0 mV
0.768A
PB extension
17 m
Cross piece
5 m
Cross piece
5 m
Module
? m
Wire 66 m
50.7 mV
8.4 mV
13.1 mV
2.0 mV
Cross piece
5 m
Cross piece
5 m
43.0 mV
PB extension
1.54 m
FB
0.7 m
Wire 5.75 m
2.0 mV
10.01 mV
4.55 mV
37.45 mV
Example: VDDD voltage drop for OL module 7
Total voltage drop is 223.21 mV

## Slide 28
https://twiki.cern.ch/twiki/pub/ALICE/Presentations20on20power20system/2017_04_09_Power_system_SPICE_simulation_report.docx
System simulated in SPICE including power board components.
Response looks as expected and reasonable.
Spice model for VDDA, VDDD for one module
SPICE model response to latch-up overcurrent. Note that the response time of the current measured in the shunt lags the current applied in the module by 1.5 ms. The power (cyan) is removed after 10 ms (to 0.5V).
Baseline System Simulation

## Slide 29
There have been a significant set of design changes since the last review (EDR).
The new design is well advanced and meets the needs of the ITS upgrade well.
The prototype power system is prototyping progressing and will soon have a full set of prototypes for all of the components required to perform a full set of tests with the prototype staves.
Any questions?
Summary

## Slide 30
BACKUP

## Slide 31
Preliminary production
power board design
Select components
for rad testing
Radiation test
components
Select new components/
update design
Complete design,
layout and produce production prototypes
Develop 2 module
Testing power board
Test functionality
PASS
FAIL
Extend design to 7 module
Testing power board
Produce and distribute 2
module testing power boards
Produce and distribute
7 module testing
power boards
Complete
In progress
Testing power boards
Production power boards
New direction decided 12/2016. Prototype 8-ch testing PBs delivered to CERN and Bari
Prototype production PBs will be used for testing.
Simplified Power Boards Development Path

## Slide 32
PB
Out
FB
33 m
Power Bus supply
0.163A
PB extension
56 m
Voltage drops come from spreadsheet
Cross piece
5 m
Module
? m
Wire 105 m
OL Fixed voltage drops for analog power (VDDA) at nominal operating condition
(VDDD=0.768A, VDDA=0.163A, calculated from geometry and material)
17.1 mV
5.4 mV
9.1 mV
1 mV
Cross piece
5 m
Power Bus return
PB extension
1.54 m
FB
0.7 m
Wire 5.75 m
Voltage drops come from table
1 mV
1.43 mV per
operating module
0.65 mV per
operating module
5.35 mV per
operating module

## Slide 33
Time response in power bus return path
for module 7 loss of power in nominal operating conditions
(VDDD = 0.8A, VDDA = 0.18A in all modules)
5 mV / division
Time
100 us / division
Voltage at module

## Slide 34
Current peak at the power enable

## Slide 35
Total dose testing at the BASE facility at LBNL 88” cyclotron for power system and RDO Unit components
DUT board
ADC/RDO boards
Resistor loads for regulators
Full Power System Design (Component Testing)

## Slide 36
Middle Layers
½ PB
½ PB
½ stave
½ stave
½ stave
½ stave
2 staves per PB
(full PB utilization)
Outer Layers
½ PB
½ PB
½ stave
1 staves per PB
(28/32 ch utilization)
½ stave
Inner Layers
½ PB
½ PB
1 stave
1 stave
2 staves per PB
(4/32 ch utilization)
Modularity of Power System