## Slide 1: MVTX Status - WBS 3.2
Ming Liu
sPHENIX L2 Meeting
11/29/2018

## Slide 2: Project Status
RU and Stave procurement in progress
  Tom is working on the paperwork through OSP at UTK, more news in two weeks
  Technical doc and paperwork were prepared and sent to UTK from BNL
MVTX project in P6
  Work in progress on funding details
    Split engineering/tech T&E among LANL, MIT, LBNL, BNL etc.
  Adjustment in WBS scope (some moved to WBS 2.x) to keep the total cost under $5M cap
  To be updated at Dec. sPHENIX collaboration meeting
MVTX Interim Design Review, 11/19/2018
  Led by John Haggerty, draft recommendations being circulated
    no evident showstoppers
  https://indico.bnl.gov/event/5351/

## Slide 3: Progress with MVTX Global Mechanical Integration
L = 350.0 cm
MVTX service barrel design proposed, with two parts:
  Part-1: from MVTX to PP-1b, all power PCB, 40cm
  Part-2: length TBD later, from PP-1b to PP-2
TPC
TPC
R= 209.6cm
INTT
MVTX
PP-1a:
short signal cables
PP-2:
Signal and power cables
PP-1b:
power cables
Service Barrel

## Slide 4: Near Term Plan
CERN/ALICE visit planned ~end of January 2019
  Walt, Ming, and MIT/Bolek, Jim, Ross et al
  Mechanical design and integration
  Produce 5 staves for MVTX telescope
Preparation for MVTX stave production at CERN
  One LANL PD hired at CERN
  MIT student/postdoc/tech help at CERN, under discussion
  LBNL will start preparing the MVTX detector lab as soon as funds will transferred
Fermilab beam test with INTT, ~May 2019
  Waiting for HDI cables for INTT
  MVTX telescope will be ready ~March 2019
  A joint test beam proposal being developed
  Test global tracking, timing etc.
Possible MVTX beam test at LBNL
  MVXT sensor and readout electronics characterization etc.
  Details under discussion

## Slide 5: MVTX & Tracking Workfest at FUS, 12/5, 8-9
Update project cost & schedule
Discuss and update institution roles
  Tasks, resources and schedules
Improve MVTX related tracking and analysis
  Decision regarding number of layers of the INTT during the collaboration meeting
  Update tracking software
  Update physics plots
Draft agenda,
https://docs.google.com/document/d/1oqJOvoqNYKJQM1N8acV2lidam84iOIE4uLY1kfrC20o/edit?usp=sharing