## Slide 1: MVTX Status and Plan WBS 3.12
Ming Liu
LANL
06/21/2018

## Slide 2: Technical Status
Preliminary readout integration completed
  4-sensor telescope with full sPHENIX readout chain demonstrated
MVTX/INTT mechanical integration design in progress
  A new engineer from MIT will join the effort in September
  A possibility of a designer joining the effort earlier
  A MIT researcher (~0.5FTE) will join soon to coordinate MVTX activities between MIT and Bates
MVTX readout cable & FPC power extension R&D
  LANL R&D
BNL/MIT working on stave and RU production at CERN
  Targeted production starting date ~Oct. 2018
MVTX BNL Directors Review – July 19
  Review charged will be released soon
  Received some feedbacks from the collaboration

## Slide 3: Cost and Schedule
MS Project updated, under review
  RU and Stave production in FY19
  Funding profile smoothing
  Updated BNL overhead rates
    Extraordinary Project Rates (EPR), same as rest of other sPHENIX
Transition into P6
  Eric, Glenn et al, with MVTX group
Ongoing discussion with DOE on project integration
  MIE, or non-MIE etc.

## Slide 4: Project Activities for Next 3 months
MS Project transition into P6
Prepare for July 19 MVTX BNL Directors Review
  Production readiness for RU and staves, system integration
Draft QA plan documents for staves and RU production
  Template received (sPHENIX EMCal)
  Will follow exactly the same procedure of ALICE QA
Prepare for stave and RU production
  BNL/MIT working on bridge fund, ~$1.5M
  Maria visits CERN in July
  A LANL postdoc starts at CERN ~August
Mechanical integration
  Work in progress, MVTX and INTT, weekly meetings under OSI
LANL R&D
  FPC power extension cables, singla cables
  Sensor operation optimization
  Negative pressure cooling system test
Update from ALICE,
ITS plenary meetings early this week:
Final RU, 1st test boards available ~July 15
Staves, 1st IB complete by July, 2nd IB production starts in ~August, 4 staves/week
Readout cable layout finalized, ~7.9m for IB signal