## Slide 1: MVTX Status Monthly Report
Ming Liu
LANL
10/3/2018

## Slide 2: MVTX Detector
MVTX RUs, PUs & other services
3-layer sensor barrel
- 48 staves, 432 chips
Service cone: signal, power, cooling
and mechanical support
Figure for ALICE ITS/IB design
(slightly modified mechanically for sPHENIX)
MVTX
parameters
End-Wheel
CYSS: Cylindrical Shell Structure

## Slide 3: MVTX Plan - WBS 3.12 (renumber?)
About $5M to be added to the sPHENIX Management Portfolio
  When will the fund be available for procurement?
Have an updated baseline cost and schedule by January 2019
Will NOT be part of CD-2/3 DOE review
Monthly report to sPHENIX and BNL upper management
Early procurements of staves and readout units (RU) through US-Alice, a separate funding from the above $5M budget, ~$1.5M

## Slide 4: Scope of the MVTX Project
MAPS Staves & Electronics
  Readout Integration R&D (LANL LDRD)
    Frontend: ALICE/ITS, RU
    Backend: ATLAS FELIX
    Reprogram RU & FELIX for sPHENIX
  Production:
    84 ALICE/ITS-IB staves from CERN
      Acceptance test @LBNL
      48+spares(36)
    58 ALICE/ITS-RU from CERN
      Acceptance test @UT-Austin, 48+spares(10)
    sPHENIX production, 8 ATLAS/FELIX
      Acceptance test @LANL
    Final detector assembly in US
      LBNL and BNL
  Ancillary systems, “adopt” ALICE system
Mechanics & Cooling
  Changes to ALICE/ITS inner tracker mechanical structures,
    End Wheels
    Cylindrical structure shells
    Detector half barrels
    Detector and Service half barrels
  Mechanical Integration,
    Conceptual design by LANL LDRD
    Prototype by sPHENIX R&D, MIT/LANL
    Design integration frames
    Composite structures, LBNL
    Installation tooling etc.
  Adopt ALICE cooling plant design
    Modifications to fit sPHENIX
    Much smaller heat load than ALICE ITS
- Early R&D by LANL LDRD, $5M, FY17-19, readout, mechanical design and physics
- Established LANL-ALICE MoU in 12/2016 for joint R&D for MVTX
From BNL Director’s Review
July 19-20, 2018

## Slide 5: Proposed Schedules and Milestones
CY-2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU
production
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel
design & production
End Wheels
CYSS
Half barrel #1
Half barrel #2
Half barrels
arrive @BNL
MVTX installation & commissioning @BNL
RU, FELIX, PS, cables etc.
Install half barrels
@sPHENIX IR
Ready for beam;
sPHENIX day-1 run
FELIX
production
Barrel Assembly & Testing @LBNL
ALICE IB stave done;
Facilities available for
sPHENIX production;
A window of opportunity:
Low technical risk
Cost saving
sPHENIX: CD1/3a CD2
MVTX
1st collisions
Installation
From BNL Director’s Review
July 19-20, 2018
Note:
updated 10/3/2018
Stave production:
Starting ~ Jan, 2019
Last for ~12months

## Slide 6: Schedule
MS Project updated during the summer, now moved into P6
  Stave and RU production through ALICE, moved out of the scope
  The rest of tasks, some still evolving, need to optimize funding profile
  An updated baseline cost and schedule by January 2019;
Early procurement of staves and readout units(RU)
  Try to complete all paperwork approvals by ~mid November, then will have better understanding of sPHENIX stave and RU production schedules
  RU production through ALICE: 60 RUs
    Being started at CERN, first batch of full production ~ Dec., 2018
    sPHENIX RUs available ~Summer 2019
    Acceptance test and QA at UT-Austin: ~summer 2019
  Stave production through ALICE: 84 staves
    Starts ~ January 2019, following the completion of ALICE ITS IB stave production
      3 months (Wafer production) + 1 month (dicing & testing) + 12months (assembly)
    Acceptance test and QA at LBNL, ~Summer 2019

## Slide 7
Lead time
Lead time
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jul
ALICE RU Production – Timeline
2019
2018
Both RUs and Data Cables are at the DAI. Goal is having 20 RUs before Christmas Break, as well as enough data cables to connect the whole IB (24 assemblies, equal to 40 data cables).
Data cables
DAI
(26)
Tendering
DAI
Batch 1b
(46 A+B)
Batch 2 (90 A+B)
Batch 3 (90 A+B)
Batch 4 (90 A+B)
Tendering
DAI
Prototypes (20)
Batch 1 (140)
Batch 2 (150)
Acpt. (extensive)
Acpt. (40 b/w)
(standard)
IB covered
RUs
Microsemi
Xilinx
DAI
Tendering
Tendering
TP
TP
Batch 1a (24 A+B)
Ref.
Acpt. (40 b/w)
(standard)
150 RU
140 RU
180 Lnk
180 Lnk
180 Lnk
92 Lnk
48 Lnk
Acpt.
sPHENIX RU
production
Presented at ITS Plenary Meeting, 9/24/2018

## Slide 8: Procurement Status
Stave and RU, through ALICE production
  Near final technical spec and cost estimate document under discussion with ALICE now, plan to complete the document in this week;
  All approvals and final green light to CERN/ALICE ~ mid of November 2018
  Total ~ $1.5M, will be purchased through US-ALICE, in coming weeks
Near term procurement plan
  To be ready for stave acceptance test & QA at LBNL
    Clean room, standalone test stand, manpower etc.
  To be ready for RU acceptance test & QA at UT-Austin
    Test equipment, manpower
  Design and produce carbon structures like End-Wheels etc.
    LANL, LBNL, BNL…
  Funding is needed immediately or the schedule will slip

## Slide 9: Recent Progress
Completed sensor/HIC/stave evaluations at CERN
  Built and tested two HICs with 40cm and 60cm long power FPC
    Confirmed sensor performance comparable with the ALICE default configuration
  Sensors irradiated up to 2.7MRad, no problem (updated 9/18/2018).
  Confirmed low magnetic field in RU/PU racks, <50Gauss; RU/PU designed for 0.5T
  Addressed all recommendations on stave/sensor R&D and RU from recent BNL review
MVTX/INTT mechanical integration
  Mechanical design being updated and 3-D mockup in progress
  Inner tracking simulation task force, good progress
  SamTec cables
    ALICE confirmed signal performance with 8m long readout cables
    This eases mechanical integration and layout of the services
Final documentation to address July MVTX Director’s Review recommendations
  MVTX/INTT mechanical integration, draft available
  Inner tracking optimization near final, optimal INTT layers, in ~1-2 weeks

## Slide 10: Backup slides