## Slide 1: MVTX Status and Plan
Camelia, Grazyna and Ming
09/22/2020
sPHENIX L2 Project Meeting

## Slide 2: Project Status & Plan
Mechanical design and vendor selection
  WorkShape won the competition to fabricate the carbon structures
    3 vendors responded, including LBNL and one commercial company in CA
    Experience, cost and schedule - within MVTX projected budget
    First test article (one layer of EndWheels) by the end of November this year
  Production Readiness Review planned, ~early December, 2020
    Full production complete by April 2021 (15~17 weeks)
  Cooling system designed, v2
    Performance test at BNL planned
  Insertion system design and mockup in progress
Readout and control electronics production
  all 30 power boards assembled and tested at LBNL
  60 RUs and cooling plates produced and arrived at ORNL for testing
    Testbench setup in progress, all testing done by the end of November at ORNL
  RU and FELIX firmware/software updated
  Full readout chain system test
    LANL – restart lab work, paperwork submitted for COVID-19 approval
    ORNL - will receive one FELIX card soon from BNL
Stave production and transportation
  Good progress at CERN, 25+ produced
  Stave QA test bench under preparation at LBNL
Stave transportation
case produced @LBNL
Stave test station @ LBNL
RU @ORNL
Cooling plate production at UT-Austin Machine shop
8-chip/stave full readout &
control system @LANL

## Slide 3
25 golden staves ready for shipping;
2nd batch of 6 staves ready for metrology, and final tests in next week or two
 | STAVE-production summary table |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IBSTAVE ID | HIC assembly | Ins. after glue | Bonding | Pull test (>=2 lifts + F <7g) | Ins. after bonding | HIC PWR test | Qualification test | Threshold cluster | HIC Matrix | HIC DTU | HIC+SF+C -> Stave | Stave PWR test | Stave test | STAVE metrology | Stave PWR test (long PWR extn.) | STAVE final test (PT100)
TOTAL | 53 | 53 | 50 |  | 50 | 49 | 40 |  |  |  | 32 | 32 | 32 | 25 | 26 | 25
A201 (326) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
A202* | 1 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK |  |  |  |  |  | 
A203 (144) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
A204 (158) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
A205 (167) | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
A206 (204) | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
B201 (352) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
B202* | 1 | 1 | 1 | 0 | 1 | 1 | 0 |  | Broken |  |  |  |  |  |  | 
B203 (114) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
B204 (116) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | SILVER | CAN | 1 | 1 | 1 |  | 1 | 
B205 (115) | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
B206 (295) | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
F201* | 1 | 1 | 1 | 1 | 1 | 1 | 0 | ?? | PARTIAL | OK |  |  |  |  |  | 
F202 (230) | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
F204 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2 | GOLD | CAN |  |  |  |  |  | 
G202 (234) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
G203 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | CAN |  |  |  |  |  | 
F203* | dummy |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H202 (294) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
H203 (302) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
H204 (354) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
H206 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | ?? | PARTIAL | OK |  |  |  |  |  | 
E204 (110) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
E201* | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 3 | PARTIAL | CAN |  |  |  |  |  | 
E202 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | CAN (bad driver) |  |  |  |  |  | 
E206 (101) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
H205 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | SILVER | OK |  |  |  |  |  | 
I202 (175) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
I203 (187) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
I204* | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | OK |  |  |  |  |  | 
I205 (266) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
J201* | 1 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK |  |  |  |  |  | 
J202 (207) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
J203 (245) 345 right | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
J204 (252) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
J206 (260) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
K202 (122) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
K203 (125) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
K204 (129) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 |  |  | 
K205 (128) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | 1 | 1 | 1 |  |  | 
K206 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN |  |  |  |  |  | 
L202 (130) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 |  |  | 
L203 (139) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 |  |  | 
L204 (127) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 |  |  | 
L205 (136) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 |  |  | 
J205 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | CAN |  |  |  |  |  | 
I201 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | CAN |  |  |  |  |  | 
L206 | 1 | 1 | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 
L201 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN |  |  |  |  |  | 
S201 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN |  |  |  |  |  | 
S202 | 1 | 1 | 1 | 0 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
S203 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
S204 | 1 | 1 | 1 | 0 | 1 |  |  |  |  |  |  |  |  |  |  | 
S205 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Reported at 09/17/2020
Stave production meeting
- Next meeting in 3 weeks
Plan at CERN:
- Continue ~10staves/month, finish 84 staves ~ Jan 2021; expect no impact on detector assembly work at LBNL
CERN can hold ~40 staves for ~5 weeks;
- We need to get them to US soon, working with CERN to test commercial transportation options

## Slide 4: Issues and Concerns
Schedule delays due to COVID-19
  Carbon structure production and test/QA
    3~4 months delay in detector design and prototyping
    FDR(7/2020) postponed to ~Dec. 2020
  Detector assembly work
    Lab access at LBNL, schedule etc.
  Stave transportation plan change
    Use commercial option
Funding for FY21
  Need to use some contingency reserve for engineering work
    MIT and LANL
  ORNL – to support RU and other electronics test work
    Previously assigned to UT-A, under Jo’s responsibility
    Draft SOW ready for review
Pre-COVID19 Schedule

## Slide 5: Backup slides

## Slide 6: Hardware Progress
All 100 cooling plates for electronics produced at UT-A and LANL
Stave transportation case designed and fabricated at LBNL
Power board assembly and test completed at LBNL
Readout Units and Cooling plates received at ORNL
  RU test under preparation
Cooling plate production at UT-Austin Machine shop
Stave test station @ LBNL
Stave transportation case
@LBNL
RU and PU Cooling Plates @UT-A

## Slide 7
60 RU plus VTRx/VTTx at ORNL
Readout Units
VTRx / VTTx
Cold Plates
RUs and Cold Plates @ORNL

## Slide 9: Testing Readiness at ORNL
Received so far:
  30 cold plates (from UT)
  Mechanical components (from UT)
  Thermal Mats (from UT)
  CANbus dongle
  Various electrical components (resistors, FPGA fans, USB cables, …)
  Tools
  Scope
  Multimeter
  Power Supplies
  Clock Generator
  GBTx programmer
Ordered:
  Workstation
  FPGA programmers (Xilinx, ProAsic3)
  40 additional cold plates (from UT)
  Cables (CANbus, power, …)
Loan from Utrecht:
  RUv0 with associated cables
  Loopback PCBs
  Loopback cables
  Power Cables
  Fiber patch cables