## Slide 1: MVTX Status and Plan
Camelia, Grazyna and Ming
09/25/2020
MVTX Bi-Weekly Meeting

## Slide 2: Project Status & Plan (I)
Mechanical design and vendor selection
  WorkShape (France) won the competition to fabricate the carbon structures
    3 vendors responded, including LBNL and one commercial company in CA
    Experience, cost and schedule - within MVTX projected budget
    First test article (one layer of EndWheels) by the end of November this year
  Setup FAB account at MIT, ready to make the first payment
    30% of the first test article, ~EU$15K
CF Production Readiness Review planned
  Early December, 2020
  Full CF production complete ~April 2021 (15~17 weeks)
Cooling system designed, v2
  Piping & Instrumentation Diagram sent to BNL this week for OK/discussion before purchases
  Cooling plant tests at BNL to decide on the needed customization
Insertion system design and mockup in progress
Service Barrel
EW,
CYSS
First test article schedule & milestones:
10 wks, already started 9/21/2020
MVTX insertion &
support system

## Slide 3: Project Status & Plan (II)
Readout and control electronics production
  All 30 power boards assembled and tested at LBNL
  60 RUs and cooling plates produced and arrived at ORNL for testing
    Testbench setup in progress
    All testing done by the end of November
  RU and FELIX firmware/software updated
  Full readout chain system test in progress
    LANL – restart lab work, paperwork submitted for COVID-19 approval
    ORNL - will receive one FELIX card soon from BNL
  SamTec readout cable designed and tested 11.4m, final length TBD, pending final sPHENIX cable route layout plan
Stave production and transportation
  Good progress at CERN, 25+ golden staves produced
    >50% of MVTX (48 staves), finish all ~Jan/Feb 2021
  Transportation case produced, stave QA test bench under preparation at LBNL
Stave transportation
case produced @LBNL
Stave test station @ LBNL
RU Test @ORNL
Cooling plate production at UT-Austin Machine shop
8-chip/stave full readout &
control system @LANL

## Slide 4
25 golden staves ready for shipping;
2nd batch of 6 staves ready for metrology, and final tests in next week or two
 | STAVE-production summary table |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IBSTAVE ID | HIC assembly | Ins. after glue | Bonding | Pull test (>=2 lifts + F <7g) | Ins. after bonding | HIC PWR test | Qualification test | Threshold cluster | HIC Matrix | HIC DTU | HIC+SF+C -> Stave | Stave PWR test | Stave test | STAVE metrology | Stave PWR test (long PWR extn.) | STAVE final test (PT100)
TOTAL | 53 | 53 | 50 |  | 50 | 49 | 40 |  |  |  | 32 | 32 | 32 | 25 | 26 | 25
A201 (326) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
A202* | 1 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK |  |  |  |  |  | 
A203 (144) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
A204 (158) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
A205 (167) | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
A206 (204) | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
B201 (352) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
B202* | 1 | 1 | 1 | 0 | 1 | 1 | 0 |  | Broken |  |  |  |  |  |  | 
B203 (114) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
B204 (116) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | SILVER | CAN | 1 | 1 | 1 |  | 1 | 
B205 (115) | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
B206 (295) | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
F201* | 1 | 1 | 1 | 1 | 1 | 1 | 0 | ?? | PARTIAL | OK |  |  |  |  |  | 
F202 (230) | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
F204 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2 | GOLD | CAN |  |  |  |  |  | 
G202 (234) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
G203 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | CAN |  |  |  |  |  | 
F203* | dummy |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H202 (294) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
H203 (302) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
H204 (354) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
H206 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | ?? | PARTIAL | OK |  |  |  |  |  | 
E204 (110) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
E201* | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 3 | PARTIAL | CAN |  |  |  |  |  | 
E202 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | CAN (bad driver) |  |  |  |  |  | 
E206 (101) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
H205 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | SILVER | OK |  |  |  |  |  | 
I202 (175) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
I203 (187) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
I204* | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | OK |  |  |  |  |  | 
I205 (266) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
J201* | 1 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK |  |  |  |  |  | 
J202 (207) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
J203 (245) 345 right | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
J204 (252) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
J206 (260) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
K202 (122) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
K203 (125) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
K204 (129) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 |  |  | 
K205 (128) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | 1 | 1 | 1 |  |  | 
K206 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN |  |  |  |  |  | 
L202 (130) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 |  |  | 
L203 (139) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 |  |  | 
L204 (127) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 |  |  | 
L205 (136) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 |  |  | 
J205 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | CAN |  |  |  |  |  | 
I201 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | CAN |  |  |  |  |  | 
L206 | 1 | 1 | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 
L201 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN |  |  |  |  |  | 
S201 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN |  |  |  |  |  | 
S202 | 1 | 1 | 1 | 0 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
S203 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
S204 | 1 | 1 | 1 | 0 | 1 |  |  |  |  |  |  |  |  |  |  | 
S205 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Reported at 09/17/2020
Stave production meeting
- Next meeting in 3 weeks
Plan at CERN:
Continue ~10staves/month, finish 84 staves ~ Jan 2021;
minimal impact on detector assembly work at LBNL (CF schedule driven)
CERN can hold ~40 staves for
~5 weeks;
- We need to get them to US soon, working with CERN to test commercial transportation options

## Slide 5
Electronics & Power
(J. Schambach)
ORNL - WBS - 3.02.02
Readout Units
LANL/ORNL WBS 3.2.2.1
Y. CorraJes/J. Schambach
Back-end
LANL WBS 3.2.2.2
Y. Corrales/C. Dean
Power systems
LBNL WBS 3.2.2.3
Y. Mei
Mechanics & Detector Assembly (G. Odyniec)
LBNL - WBS 3.02.03
Staves
LANL WBS 3.2.3.1
Y. Corrales/C. da Silva
Mechanical Detector Design
LANL/MIT WBS 3.2.3.2.1
W. Sondheim/J. Kelsey
Barrel Assembly
LBNL WBS 3.2.3.3
Y. Mei
Integration & Infrastructures (C. Mironov)
MIT - WBS 3.02.04
Cooling
MIT WBS 3.2.4.1
J. Kelsey
Safety System
MIT WBS 3.2.4.2
C. Mironov
Global Mech. Support
MIT/LANL WBS 3.2.4.3
C. Mironov/W. Sondheim
MVTX (WBS 3.02)
L2 Project Manager: M. Liu (LANL)
Deputy PMs: G. Odyniec (LBNL), C. Mironov(MIT)
ES&H Liason: W. Sondheim (LANL)/A. Franz(BNL)
Installation & Commissioning
BNL/all WBS 3.2.4.4
sPHENIX Integration
sPHENIX DAQ
Carbon Structures Fabrication
MIT/LBNL WBS 3.2.3.2.3
C. Mironov/Y. Mei
sPHENIX Project Office
Project Org Update

## Slide 6: Issues and Concerns
Schedule delays due to COVID-19
  Carbon structure production and test/QA
    3~4 months delay in detector design and prototyping
    FDR(7/2020) postponed to ~Dec. 2020
  Detector assembly work
    Lab access at LBNL, schedule etc.
  Stave transportation plan changed
    Commercial options
    Minimal impact on assembly schedule
  Tight schedule to meet the installation dates
Funding for FY21
  Need to use some contingency reserve for engineering work
    MIT and LANL
  ORNL – to support RU and other electronics test work
    Some tasks previously assigned to UT-A, under Jo’s responsibility
    Draft SOW ready for sPHENIX review
Pre-COVID19 Schedule
Today